## DL_FM_039
Business Management System (BMS)
PROJECT DELIVERY PROCESS
Risk and Opportunity Register
Document Date: |  |  |  | 2020-10-01 | [5 empty] | Project Phase: |  |  | Tender Phase
REVISION No. |  |  |  | 1A
Project Name: |  |  |  | Construction Excelence centre
ID. | Risk (R)/ Opportunity(O) | Category | Risk/ Opportunity Area (include details of specific risk) | Consequences of Event (e.g. Time/Quality/ Cost/ Environment etc) | RATING |  |  | Current Risk/ Opportunity Owner (Organisation e.g. Principle Contractor, Client, Subcontractor etc.) |  | AGREED ACTION TO (a) MITIGATE AND/OR REMOVE RISK OR (b) REALISE OPPORTUNITY
[5 empty] | Probability | Impact | Overall Priority |  | IK Comments | ACTION | BY WHOM? | BY WHEN?
[9 empty] | Pre construction (PC) STAGE ACTION |  |  | proposed | actual
SITE ABNORMALS
1` | R | Physical | Geotechnical. Ground conditions | Tender information will likely assume more favourable ground conditions. Additional engineering work would result in additional costs | Medium | High | High | Principle contractor | Further Soil investigating (SI) during Pre constuction (PC) stage to eliminate any unknown factors in finalising sub-structure design solutions for all areas. Understand all costs and incorporate these into work packages. engineering consultant should prepare a schedule of further investigation works. Review the current SI information records | SI to be detailed and carried out at earliest opportunity as soon as contract is awarded | Project Manager | Week 1
2 | R | Physical | Geotechnical. Contamination | Potential for significant additional costs if remediation or disposal of contaminated material is required | Low | High | Medium | Principle contractor | Further soil inventigatetion during Pre Construction stage to eliminate unknown factors in finalising sub-structure design solutions for all areas. Understand all costs and incorporate these into work packages. Check suitability of arisings with local tips. Confirm anticipated quantities? | Ground investigation to be scoped and carried out at earliest opportunity. | Project Manager | Week 1
3 | R | Physical | Drainage. Capacity/Attenuation/ SUDS | Attenuation required to restrict discharge into water course to acceptable levels. Ensuring enough space as building area is large | Medium | Medium | Medium | Principle contractor | approval of the drainage scheme solutions required during pre contstruction stage to allow cost and design certainty. Lease with design team to find out possible locations. | Tender stage assessment has been made. Full design TBC | Design and Technical Manager | Week 3 PC
| R | Statutory | Drainage. Adoption Agreements sections 104/106/185 | Final legal agreements can significantly affect the overall programme. | High | Medium | Medium | Principle contractor | focuss on Progressing development of the sectional agreements during PC stage to technical approval. | Design team to engage with Local Authority Drainage board and welsh water to determine preferred option for discharge. | Design and Technical Manager | Week 2 PC
6 | R | Physical | Highways. sections 38/278 works | Technical Approval will be required with Highways for entrance alterations and on site 38 works | Medium | Medium | Medium | Principle contractor | focuss on Progressing development of the sectional agreements during PC stage to technical approval. | having Early engagement with Highways essential. | Design and Technical Manager | Week 2 PC
7 | R | Physical | services. Capacity and New Connections | Potentially very costly in particular if local infrastructure does not have capacity. High capacity plant being used | Medium | Medium | Medium | Principle contractor | Utility enqueries will be obtained. Verify loadings for new service requirements during pc stage. | Tender Stage searches conducted. Loadings/requirements to be frozen at an early stage to allow quotations to be procured. Its important Principle contractor appoints a M&E specialist ASAP to assist with this | Design and Technical Manager | Week 3 PC
8 | R | Physical | M&E - ensuring comprehensive design | late design changes will have detremental effect on both programme and cost | Medium | High | High | Principle contractor | ensuring close relationship with M&E consultants and suppliers at earlierst stages - appointment of contractor and consultant week 1. | ensure m&e design is signed off and approved at earliest stage possible to ensure earliest lead times and any buildability issues may occure can be contracturally covered | Design and Technical Manager | throughout disnign process
9 | R | Physical | lead times - specialist plant and machinery | long lead times on specialist plant can have detremental effects on project programmme also affecting costs | Medium | High | High | principle contractor | ensure lead times and locked in at the earliest stage, As soon as products are specified, place orders. | deadlines for material and plant orderes should be highlighted on the critical path on the project programme | Project Manager | throughout disnign process
PLANNING
13 | R | Statutory | Planning Programme | Planning process is on critical path of pre-construction programme. Delays will effect project delivery | High | Medium | High | Principle contractor | Planning officer to report on level of risk at progress points through the building stage. | planning applications-contract programme to be closely monitored to avoid delays. | Design and Technical Manager | Week 1 PC
14 | R | Statutory | Ecological Surveys/Tree Surveys/ Bat Surveys | Further ecology works will be required. Presence of protected species likely to affect programme | High | Medium | High | Principle contractor | ecological survey to be Carried out by 3rd party consultant. And act on any findings asap | PC to allow 10 days watching brief during early investigation works to determine any mitigation required. | Project Manager | Week 1 PC
| R | Statutory | Material- Approval (cladding) | potential to lose progress on design programme if theres kate change to cladding systems | Medium | High | High | Principle contractor | Planning officer to report on level of risk at progress points through the building stage. | close contact with planning officer to avoid items being missed | technical amanager and design | week 1
| R | Statutory | Noise impact - environmental conerns | planning will have environmental concerns over noise polution of the plant | Medium | Medium | Medium | principle contrctor | get educated estimates of dB levels of plant required. Ensure apprived at ealry stages | ensure contractor sticks with tested products and machinery what have been approved | technical amanager and design | PC STAGE
COMMERCIAL/ FINANCIAL/ CONTRACTUAL
18 | R | Contractual | Contractual certainty and agreement. | Lack of collaboration | Low | Low | Low | All | Collaborative working and transparecncy through the PC stage. | it is envisaged that via active collaboration and communication during the PC stage there will be Contractual certainty which will negate risk for all parties. | Commercial Manager | PC STAGE
19 | R | Construction | Managing the Budget - variations at design stage | Throughout the project development budget will need to be managed to ensure scheme viability | Medium | Medium | Medium | Principle contractor | design team / consultants to be in close mmunication with commercial team. This negates drift from the cost plan and limits variations at ealry stages | Stage 1 tender will be costed using live data for schemes of similar construction including known abnormals, supplemented by market tested key packages. Changes and abnormals will be identified and reported throughout scheme development. | Commercial Manager | PC STAGE
20 | R | Programme | Change | Change to design through stakeholder engagement, unforeseen conditions, planning requirements will impact on project costs | Medium | Medium | Medium | Employer | Suggest we agree any potential changes quickly during early stages of PC to allow correct pricing and allocation. Propose a decision deadline for changes. Any post-contract changes would be covered by the contract. Close comunication with the client on these change risks to ensure certainty of contractual protection | the contractor is experienced at managing projects through this process. Robust change control process to be utilised. Balanced approach to risk and opportunity and application of Value Engineering to keep within budget. | Commercial Manager | PC STAGE
CONSTRUCTION (including Health & Safety & Procedural)
22 | R | Physical | Main HV cable to be extended | Time, Cost, | High | High | High | Principle contractor | correspondance with western power to commence asap, lock in quotes and timescales | Main HV Cable to be extended to allow construction. Payment to be made by the client, currently 12 weeks lead time with 1 week of works. | Project Director | PC STAGE
23 | R | Construction | Fire/arson during the construction of the site. | Time, Cost | High | High | High | Principle contractor | ensure comprehensicve security is priced into welfare and prelims | Due to the risk of fire during the construction phases and the consequence of such a event contractor would construct the key units using steel, lightweight steel and concrete. Cladding used should be fire resistant including insulation | Project Director | Week 1 PC
24 | R | Construction | Construction Noise during site works | Environmental | Medium | Medium | Medium | Principle contractor | ensure subcontractors contracts include keeping track of and monitoring sound levels of their own work. Engage with university on exam periods etc | • Engage with the local authority and enter into a Section 61 Consent during and after planning to ensure noise restrictions suit our programme of works. Work closly with universitly when planning noisy works or movement of programme related to noisy wokrs | Project Director | Prior to works commencing
25 | R | Physical | Managing the interface with residents and student during early construction works | Environmental | Low | Low | Low | Principle contractor | letter drops / social media posts should go out to residents and the university to froward to student before any work commences | Initial engagement with local residents and councillors to inform all parties of the proposed works using various communications techniques such as:- letter drops, community meetings, social media, site information boards etc… Regular updates will be provided to residents in the vicinity with further updates provided to the wider occupants of the area. | Project Director | Prior to works commencing
27 | R | Construction | Community | Time | Low | Low | Low | Principle contractor | ensure plan templates are in place and csr manager to commence reaserch on local area to ensure relevance | • Risk of bad publicity for contractor and client during the construction phases. • Stake holder management plan and Corporate Social Responsibilities plan will be developed to inform engagement and drive community benefits. | Project Director | Prior to works commencing
28 | R | Construction | Community Engagement | Time | Low | Low | Low | Principle contractor | ensure plan templates are in place and csr manager to commence reaserch on local area to ensure relevance | • Excellent record for delivering the CSR Plan • Opportunities for local employment and supply chain | Project Director | Prior to works commencing
29 | R | Construction | Site Security | Time | Low | Medium | Low | Principle contractor | make sure adequate pricing for security includes full coverage and call outs costed for security | • Break-ins and damage will cause disruption to the scheme. A dedicated CCTV System will be installed to cover the whole site including a web camera for monitoring progress and timeline for the scheme. | Project Director | Prior to and as works progress
30 | R | Construction | Traffic management | health and safety - site traffic using university access roads | High | High | High | principle contractor | ensure a robust traffic management plan is in place for the full duration of the project, and sufficient traffic management team priced into the budget for the full duration | ensure traffic management plan is kept up to date and altered as required as the job progressess, making sure in is reviews on at least a monthly basis | Project Director | throughout constrcution process

## Validation (hidden)
Probability and Impact | Select: | Select from the list below: | Select:
Select from the list: | R | Tender Phase | Construction
High | O | Construction Phase | Programme
Medium |  | Completion Phase | Statutory
Low |  |  | Physical