## Communication Plan (Example)
PSA - Communication Plan
Interested Parties/Stakeholder | Stakeholder Status | Nature of Information | Delivery Method | Frequency | Meeting Notice Period | Responsible Owner | Comments/ key messages to be delivered
Programme Board | Key Player | Highlight report (HLR) | Via e-mail | Monthly |  | Project Manager | Project progress, updates
Programme Board | Key Player | Risk & Issue Rgister | Via Project Board | Ad-hoc as required |  | Project Manager | Project progress, updates
Programme Board | Key Player | End Stage report (ESR) | Via e-mail | End of stage |  | Project Manager | Project progress, updates and documentation to support decision making
Programme Board | Key Player | Escalation reports | Via e-mail | Ad-hoc as required |  | Project Manager | Project progress, updates and documentation to support decision making
Programme Board | Key Player | Meeting minutes | Via e-mail | Monthly |  | Project Manager | Project progress, updates
Programme Board | Key Player | Project plans/timelines | Via Project Board | Ad-hoc as required |  | Project Manager | Project progress, updates
Programme Board | Key Player | Go live assurance matrix | Via Project Board | Prior to go live |  | Project Manager | Project progress, updates and documentation to support decision making
Programme Board | Key Player | Closure report | Via e-mail | At end of project |  | Project Manager | Project progress, updates and documentation to support decision making
CCIO (Robin Rice) | Keep Informed | Highlight report (HLR) | Via e-mail | Monthly |  | Project Manager | Project progress
Example Only

## Communication Plan
(Name of Project) - Communication Plan
Interested Parties/Stakeholder | Stakeholder Status | Nature of Information | Delivery Method | Frequency | Meeting Notice Period | Responsible Owner | Comments/ key messages to be delivered
Who | Key player keep informed etc | What | How | When

## Timeline of Comms Activities
KEY | C = Complete
G = Planned & on track
A = Planned but is a risk target date will not be met
R = Planned but target date will not be met
Week Commencing
Ref | Communication | Comments | Required by | Who is responsible | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date

## Stakeholder Engagement
Digital Community - MH&LD - Stakeholder Engagement Plan
Interested Parties/ Stakeholder | Stakeholder Status | Area of Influence / Interest | Priority | Project Phase | Resistance identified that requires management | Engagement activity | Who will lead on this activity | Role in the activities | Engagement Strategy | Engagement Tools | Frequency
Who | Key player keep informed etc | Service, Teams | Gold, Silver, Bronze | e.g. All, Phase 1 | Yes / No Any resistance management should be included in the resistance management plan | WOW Workshops, steering groups, shadowing, process mapping, Surveys etc. | BCM, PM, System Manager | What will this person bring - decision making, knowledge of business processes etc. | How will you engage this stakeholder in these activities? | What tools will support these activities? | How frequently will this engagement take place?
Operational Manager / Divisional Lead | Key Player | All Services | Gold | Phase 1 | No | Steering Group Follow up meetings from WOW Workshops | BCM | Decision Maker | Invite to Steering Group Email Follow up meetings | Engagement template Action Logs Email Escalation | Monthly or appropriate
Service Improvement Manager (SIM) | Key Player | All Services | Silver | Phase 1 | No | Steering Group WOW Workshops Surveys Process Mapping SOPs | BCM BCF | Bring knowledge of the processes and the dynamics of the teams Influencial in decision making | Invite to Steering Group Email Follow up meetings Invite to WOW Workshops | Engagement template Action Logs Email Escalation | Monthly or appropriate
Super User | Key Player Subject matter expert | All Services | Silver | Phase 1 | No | WOW Workshops Process Mapping Surveys Shadowing UAT SOPs | BCM BCF | Knowledge of the processes Knowledge of the system Training 1st point of contact | Email Invite to WOW Workshops Enhanced Training Additional Support | Engagement Template Action Logs Email Training Packages Enhanced permissions within the system | As appropriate
Team Leads | Key Player | All Services | Silver | Phase 1 | No | Steering Group WOW Workshops Surveys Process Mapping SOPs | BCM BCF | Bring knowledge of the processes and the dynamics of the teams Influencial in decision making | Invite to Steering Group Email Follow up meetings Invite to WOW Workshops | Engagement template Action Logs Email Escalation | Monthly or appropriate
Clinicians | Key Player Subject matter expert | All Services | Bronze | Phase 1 | TBC | WOW Workshops Surveys Shadowing Process Mapping 1-2-1 Engagement | BCM BCF | Knowledge of the processes Knowledge of the system Training | Email Invite to WOW Workshops Enhanced Training Additional Support | Engagement Template Action Logs Email Training Packages | As appropriate
Administrators | Key Player Subject matter expert | All Services | Bronze | Phase 1 | TBC | WOW Workshops Surveys Shadowing Process Mapping 1-2-1 Engagement | BCM BCF | Knowledge of the processes Knowledge of the system Training | Email Invite to WOW Workshops Enhanced Training Additional Support | Engagement Template Action Logs Email Training Packages | As appropriate
Senior Nurse
General Manager
Clinical Lead
Execs
Supplier
DHCW
3rd Party Organisations (Police, ME Office etc.)
GP's
SRO
Other Organisations (Health and Social)