## Sheet1
| June |  |  |  | July |  |  |  | August
| Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
Log Book
Proteus Design of Schematic | bar: June Week 1
Testing of Schematic and Results | bar: June Week 2 to June Week 3
Constructing Breadboard of the Circuit | bar: June Week 4 to July Week 1
Testing the Breadboard and Results | bar: July Week 2
Design of PCB using Easy PC | bar: July Week 3 to July Week 4
Purchasing PCB | bar: July Week 4
Soldering Components onto PCB | bar: August Week 1 to August Week 2
Testing the PCB and Results | bar: August Week 3 to August Week 4