## Cover Sheet
Elemental Cost Plan
Client;
Issue Date; April 2024
Author; Max James

## Table Of Contents
Table Of Contents
Reference | Item
Tab 3 | Information Used
Tab 4 | Assumptions & Exclusions
Tab 5 | Initial Feasibility Estimate
Tab 6 | Cost Plan Summary
Tab 7 | 0 Facilitating Works
Tab 8 | 1 Substructure
Tab 9 | 2 Superstructure
Tab 10 | 3 Internal Finishes
Tab 11 | 4 FF&E
Tab 12 | 5 Services
Tab 13 | 6 Prefab & Building Units
Tab 14 | 7 Works to Existing Building
Tab 15 | 8 External Works
Tab 16 | 9 Main Contractors Preliminaries
Tab 17 | 10 Main Contractors Overheads & Profits
Tab 18 | 11 Project Design Team Fees
Tab 19 | 12 Other Project Costs
Tab 20 | 13 Project Risks
Tab 21 | BCIS Indicies

## Information Used
Information Used
Drawing No. | Drawing Description
74734 | Decision Notice
78671 | Design Statement
74211 | Planning Application
70361 | Site Elevation to Dockside
59493 | Site Elevation to Langdon Road
59694 | Site Elevation to Plot
59695 | Site Elevation to Plaza
32644 | Site Location Plan
59696 | Site Plan
7364 | Proposed Ground Floor Plan
70362 | Proposed First Floor Plan
59697 | Proposed Second Floor Plan
59698 | Proposed Third Floor Plan
70363 | Proposed Fourth Floor Plan
59699 | Proposed Fith Floor Plan
59700 | Proposed Roof Plan

## Assumptions & Exclusions
Assumptions & Exclusions
1.0 Basis for Estimate
1.01 This elemental cost plan has been created in accordance with NRM1.
1.02 The scope of works is restricted to the drawings submitted for planning.
1.03 All specifications are assumed and are to be confirmed.
1.04 The rates have been taken from SPON's 2020, with the current
tender index being multiplied against the 2020 rate.
1.05 The tender index has been based on the 4th quarter in 2023
1.06 The latest tender & cost indicies have been downloaded from BCIS
and are part of this cost report
1.07 The take-off's have been completed by using the drawings on the
planning portal. A point to note is that due to the drawings being acessed
via the portal, they have been scanned in therefore accuracy of measurement
isn't precisley to scale.
1.08 The overall GIFA has been taken from the first floor plan as GIFA
excludes areas such as fire escapes, open sided cover ways, open parking
areas, therefore the basement has been excluded.
1.09 Take offs should be taken as approximate estimates due to the
accuracy of the avaliable drawings.
1.10 Purple comments have been added to each take off to give context as to
where the figure has been derived at.
2.0 Assumptions & Exclusions
2.01 VAT is excluded.
2.02 The cost estimate is issued as a preliminary elemental cost plan and
contains numerous assumptions on the scope and specification of the
proposed works.
2.03 It is assumed that the drawings would be further developed to RIBA
Stage 4, to which a more detailed cost plan could be generated utilising
NRM2.

## Initial Feasibility Estimate
Initial Feasibility Estimate
PROJECT BRIEF
Construction of 6 storey mixed use development comprising of 1 No. Ground Floor retail unit,
and 1 No. Ground Floor food and drink unit and 132 No. bedroom hotel with 10 No. car parking
spaces and delivery/service yard.
Retail - Cost Per Person; Note - No rate in SPON's for retail so rate for Office been taken
forward (similar specification so rate is applicable)
No. People | Unit | Rate | Total Cost
50 | Nr | 16000 | 800000
Hotel - Cost Per Bed
No. Beds | Unit | Rate | Total Cost
132 | Nr | 83000 | 10956000
Car Parking - Cost Per Car / Space
No. Spaces | Unit | Rate | Total Cost
10 | Nr | 2700 | 27000
Subtotal at 1Q 2020 |  |  | 11783000
TPI Adjustment
Year | Tender Index |  | Total
1Q2020 | 121.1
3Q2023 (Assumed) | 184
17903154.4178
Location Adjustment
Location | % Factor |  | Total
Outer London | 1%
Wales | 0.9%
16112838.9761

## Cost Plan Summary
Cost Plan Summary
PROJECT: | SA1 Mixed Use Developtment
DESCRIPTION: | Mixed Use Developtment
GIFA: | 1571
BUILDING WORKS ESTIMATE
GROUP ELEMENT | ELEMENT DESCRIPTION |  | COSTS | £/m2
GROUP ELEMENT 0 | FACILITATING WORKS |  | 54304.4 | 34.5668
GROUP ELEMENT 1 | SUBSTRUCTURE |  | 1388428.5 | 883.7864
GROUP ELEMENT 2 | SUPERSTUCTURE |  | 2478849.6 | 1577.8801
GROUP ELEMENT 3 | INTERNAL FINISHES |  | 948240.8 | 603.5906
GROUP ELEMENT 4 | FITTINGS & FURNISHINGS |  | 500000 | 318.2686
GROUP ELEMENT 5 | SERVICES |  | 500000 | 318.2686
GROUP ELEMENT 6 | PREFABRICATED & BUILDING UNITS |  | 0 | 0
GROUP ELEMENT 7 | WORKS TO EXISTING BUILDINGS |  | 0 | 0
GROUP ELEMENT 8 | EXTERNAL WORKS |  | 1085575 | 691.0089
GROUP ELEMENT 9 | MAIN CONTRACTORS PRELIMS |  | 834647.796 | 531.2844
GROUP ELEMENT 10 | MAIN CONTRACTORS OHP |  | 233701.3829 | 148.7596
GROUP ELEMENT 11 | PROJECT DESIGN TEAM FEES |  | 240712.4244 | 153.2224
GROUP ELEMENT 12 | OTHER PROJECT COSTS |  | 0 | 0
GROUP ELEMENT 13 | PROJECT RISKS |  | As Below | 0
WORKS ESTIMATE TOTAL (SUB TOTAL A) |  |  | 8264459.9032
FACTORS
CURRENT TPI |  | 124
CURRENT TPI FORECASTED Q3 2023 (Assumed) TPI |  | 184
12263392.1145
CURRET COSTS (Outer London Factor) |  | 1%
FACTORED COSTS (Wales Factor) |  | 0.9%
11037052.903
FACTOR TOTAL (SUB TOTAL B) |  |  | 2772592.9998
PROVISIONAL SUMS (ACCOUNTED FOR)
FITTINGS & FURNISHINGS (FIXED FURNITURE) |  |  | 350000
FITTINGS & FURNISHINGS (SIGNAGE) |  |  | 50000
SERVICES |  |  | 500000
EXTERNAL DRAINAGE |  |  | 150000
EXTERNAL SERVICES |  |  | 150000
PROVISIONAL SUM (SUB TOTAL C) |  |  | 1200000
DESIGN FEES
PROJECT DESIGN TEAM FEES @ 12% OF CONSTRUCTION VALUE
DESIGN FEES (SUB TOTAL D) |  |  | As above
RISK ALLOWANCES
DESIGN CONTIGENCY - RISK ALLOWANCE @ 2.5% |  |  | 275926.3226
CONSTRUCTION RISK - RISK ALLOWANCE @ 2.5% |  |  | 275926.3226
EMPLOYERS CHANGE RISK - RISK ALLOWANCE @ 2.5% |  |  | 275926.3226
OTHER ASSOCIATED RISK - RISK ALLOWANCE @ 2.5% |  |  | 275926.3226
DESIGN FEES (SUB TOTAL E) |  |  | 1103705.2903
TOTAL ESTIMATE
SUB TOTAL (A+B+C+E) |  |  | 12140758.1933
SUB TOTAL M2 (A+B+C+E) |  |  | 7728.0447

## Take Off Sheet
PROJECT: SA1 MIXED USE DEVELOPMENT
COST PLAN GROUP ELEMENT: TAKE OFF SHEET
TIM | DIM | SQ | Description
Calculation of Wall Thickness
Half Brick Wall 102.5
Cavity 75
Steel Frame 200 (assumed column thickness)
377.5
Trench Width (Pile Diameter) 500
Less Wall 377.5
122.5
Outer Edge of Pile Foundations
W B
43 43
Removal of Topsoil (Average 150mm Thick)
43
43
1849
Material Arising from Pile Foundations
Pile Diameter: 500mm
Pile Depth: 15m
πr2h = r= pile h = height
π0.25 x 15 = 11.78
11.78
125
1472.5
Element 3.1 Wall Finishes
Internal wall finishes to be
taped and jointed
Take off room area and x by 131 (hotel room number)
Window Schedule
Elevation to Plot
3 x rows of 4 = 12
3 x rows of 5 = 15
27
Elevation to Langdon
3 x rows of 4 = 12
12
Elevation to Dockside
2 x rows of 4 = 8
2 x rows of 3 = 6
14
Elevation to Plaza
5 x rows of 4
20
TOTAL
73
Door Schedule (External)
Elevation to Plot
2 x single leaf
1 x double leaf
Elevation to Langdon
1 x Glazed Shop Entrance
1 x Glazed Shop Front
Elevation to Dockside
1 x Glazed Shop Rear
1 x Rolling Shutter Garage Door
Elevation to Plaza
1 x Rolling Shutter Garage Door
TOTAL
2 x Single Leaf
1 x Double Leaf
1 x Glazed Shop Entrance
1 x Glazed Shop Front
1 x Glazed Shop Rear
2 x Rolling Shutter Garage Doors
8
Door Schedule (Internal) - As per scanned in drawings
Ground Floor
13 x Single Leaf
7 x Double Leaf
First Floor
28 x Single Leaf
1 x Double Leaf
Seond Floor
67 x Single Leaf
1 x Double Leaf
Third Floor
67 x Single Leaf
1 x Double Leaf
Fourth Floor
67 x Single Leaf
1 x Double Leaf
Fifth Floor
67 x Single Leaf
1 x Double Leaf
309 x Single Leaf
12 x Double Leaf
Hotel Area SFS System
132 rooms, 25m2 each - 5 linear metres of stud work per room
132 x 5 = 660m
Retail Area SFS System
Assume 150m
Break Out Areas, Lobbies Etc
Extra Over allowance for above - 50m
860
Note on B34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Number of Piles

## 0 Facilitating Works
PROJECT: SA1 MIXED USE DEVELOPMENT
COST PLAN GROUP ELEMENT: 0 FACILITATING WORKS
Ref | Description | Qty | Unit | Rate | £ p
Element 0.1 Toxic / Hazadous
material treatment
0.111 A | Allowance for asbestos found | 1 | Item | 15000 | 15000
within ground
0.112 B | Allowance for contaminated | 1 | Item | 20000 | 20000
land (disposal of material). Based
on historic information on ground
conditions / surveys.
| To Summary |  |  |  | 35000
Element 0.3 Temporary
Support to Adjacent Structures
0.311 A | Support to existing structure | 10 | nr | 1230.44 | 12304.4
adjacent to car park
12304.4
To Summary
Element 0.4 Specialist
Groundworks
0.431 A | Ground gas venting for radon gas | 1 | Item | 5000 | 5000
due to area - allowance for gas
venting
| To Summary |  |  |  | 5000
Element 0.6 Extraordinary Site
Investigation Works
0.621 A | Allowance for ecology mitigation | 1 | Item | 1000 | 1000
methods - desktop study
0.631 B | Allowance for UXO Survey due to | 1 | Item | 1000 | 1000
area of build
| To Summary |  |  |  | 2000
TO SUMMARY |  |  |  |  | 54304.4

## 1 Substucture
PROJECT: SA1 MIXED USE DEVELOPMENT
COST PLAN GROUP ELEMENT: 1 SUBSTRUCTURE
Ref | Description | Qty | Unit | Rate | £ p
Element 1.1 Substructure
A | Removal of topsoil - assumed | 1850 | m2 | 22.55 | 41717.5
150mm deep
| To Summary |  |  |  | 41717.5
Element 1.2 Specialist Foundations
1.21 A | Piling mat - assumed 150mm | 1850 | m3 | 13.7 | 25345
thick
1.22 B | Piling Plant - assumed 1 rig | 1 | Item | 23000 | 23000
1.24 C | Supply and install piles including | 125 | nr | 4100 | 512500
carting away of soil - assumed
600mm diameter reinforced
concrete piles
1.25 D | Pile Casings - Assumed | 125 | nr | 11.2 | 1400
ground survey data)
1.27 E | Material arising from pile foundations | 1472.5 | m3 | 75.6 | 111321
including disposal of material
1.28 F | Allowance for breaking through | 1 | Item | 15000 | 15000
tarmac
1.29 G | Cutting off tops of concrete piles & | 125 | nr | 910 | 113750
preparing heads (Nr of piles)
1.210 H | Pile tests - using tension piles as reaction: | 6.25 | Item | 9500 | 59375
typical loading test 1000KN to 2000KN
integrity testing (per 20 piles)
1.212 I | Pile caps - 2100mm x 2100mm x 1000mm; | 42 | nr | 910 | 38220
2-3 piles
| To Summary |  |  |  | 899911
Element 1.3 Lowest Floor
Construction
1.31 A | Ground Floor Slab - 200mm thick concrete | 1850 | m2 | 125 | 231250
slab with 1 layer of A252 fabric reinforcement
1.33 B | Extra over for forming of lift pit | 150 | m2 | 37 | 5550
1.37 C | Drainage below ground - allowance | 1 | Item | 150000 | 150000
1.38 D | Gullies / Floor outlets - allowance | 1 | Item | 50000 | 50000
1.310/311 | Testing / comissioning of drainage | 5 | % | Above | 10000
outlets
| To Summary |  |  |  | 446800
TO SUMMARY |  |  |  |  | 1388428.5
Note on C10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: GIFA of Building
Note on C22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1 Pile per 1.2m2 (assumption) based on ground conditions
Note on C30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: As per take off sheet
Note on E30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Rate inclusive of material arising & disposal (£63 for material arising, £12.60 for disposal / storage if necessary)
Note on C39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 125 piles / 20 piles (cost per 20)
Note on C43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 125 / 3 (cot per 3 piles, allowance for 1 more)
Note on C51: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: GIFA
Note on C54: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Allowance

## 2 Superstructure
PROJECT: SA1 MIXED USE DEVELOPMENT
COST PLAN GROUP ELEMENT: 2 SUPERSTRUCTURE
Ref | Description | Qty | Unit | Rate | £ p
Element 2.1 Frame
2.11 A | Structural steel frame | 250 | tonne | 2500 | 625000
inclusive of fittings and fixtures
2.12 B | Fire protection to steel frame - | 1850 | m2 | 37.5 | 69375
allowance for intermesent paint
| To Summary |  |  |  | 694375
Element 2.2 Upper Floors
2.21 A | Suspended floor slabs - assumed | 9250 | m2 | 48 | 444000
200mm thick 6.0m span: 8.50kN/m2
2.22 B | Formwork details to suspended | 5 | nr | 25000 | 125000
| floors - allowance per floor |  | (per floor)
2.23 C | Joints / Details between concrete | 5 | nr | 10000 | 50000
| suspended floor & steel frame - |  | (per floor)
allowance per floor
2.24 D | Surface treatment to suspended | 1 | item | 15000 | 15000
floor - allowance
| To Summary |  |  |  | 634000
Element 2.3 Roof
2.34 A | Flat roof detail - specification to | 1950 | m2 | 93 | 181350
be determined - assumption made
for a warm deck detail
2.34 B | Allowance for plant deck - including | 45 | m2 | 53 | 2385
area for water storage, air handling
unit, mechanical riser and external
chiller zone (as per roof detail on
drawing)
2.311 C | Roof covering - allowance made for | 1950 | m2 | 83 | 161850
warm roof detail inclusive of;
waterproofing layer, ridgid
insulation, vapour control layer,
structural deck, ceiling & support
structure - roof detail listed within
cost report
2.322 D | Extra over roof covering - allowance | 100 | m2 | 47 | 4700
for walkways for maintance
2.322 E | Extra over roof covering - allowance | 45 | m2 | 47 | 2115
for re-inforced roof covering for
plant deck area
2.324 F | Edge protection to roof - allowance | 86 | m2 | 55 | 4730
2.341G | Channel gutters - allowance for | 86 | m2 | 94 | 8084
perimetre of building
2.342 H | Rainwater downpipes / outlets - | 86 | m2 | 83 | 7138
allowance
2.345 I | Comissioning / testing of outlets | 5 | % | above | 18617.6
| To Summary |  |  |  | 390969.6
Element 2.4 Stairs & Ramps
2.411 A | Stairs to floors (inclusive of staircase | 6 | nr | 5700 | 34200
up to roof deck) - assumed
precast concrete
2.421 B | Stair finish detail - finishes to | 10.8 | m | 105 | 1134
landings between floor levels
2.431 C | Balustrades & handrails to stairs - | 10.8 | m | 190 | 2052
allowance
2.441 D | Access ladder - allowance for | 1 | nr | 900 | 900
ladder to roof deck
| To Summary |  |  |  | 38286
Element 2.5 External Walls
2.511 A | External walls - brick external skin | 1950 | m2 | 130 | 253500
2.514 B | Extra over allowance for forming | 72 | nr | 28.6 | 2059.2
of openings (windows) - assumption
2.514 C | Extra over allowance for forming | 8 | nr | 28.6 | 228.8
of openings (doors) - assumption
2.5111 D | Allowance for pointing to external
| walls | 1 | Item | 10000 | 10000
2.5111 E | Allowance for stone arch opeing | 1 | Item | 5000 | 5000
to front façade
2.541 F | External soffits - allowance | 1 | Item | 15000 | 15000
2.544 G | Access hatch - allowance for | 1 | Item | 5000 | 5000
hatch to roof deck
| To Summary |  |  |  | 290788
Element 2.6 Windows & External
Doors
2.611 A | Window details as follows;
| UPVC 1400 x 900 mm | 18 | nr | 245 | 4410
| UPVC 1600 x 1400 mm | 18 | nr | 265 | 4770
| UPVC 1100 x 900 mm | 18 | nr | 220 | 3960
| UPVC 1100 x 400 mm | 18 | nr | 220 | 3960
2.613 B | Shop front opening | 3 | nr | 950 | 2850
2.621 C | External Door details as follows;
2.623 D | Shop enterance door - twin leaf | 2 | nr | 11500 | 23000
glazed automatic sliding door
2.621 E | Steel door to roof deck, twin leaf | 1 | nr | 2125 | 2125
2.621 F | Back of House entrance door, | 1 | nr | 260 | 260
1.5 leaf aluminum
2.621 G | External fire exits, aluminium | 2 | nr | 2700 | 5400
twin leaf with push openings
| To Summary |  |  |  | 50735
Element 2.7 Internal walls and
partitions
2.711 A | 140mm block load bearing wall | 86 | m2 | 54 | 4644
2.711 B | Extra over for plaster board allowance | 1 | item | 1500 | 1500
2.711 C | New internal metal stud parititions (SFS | 860 | m2 | 93 | 79980
system)
2.711 D | Extra over for skim & plaster to both | 860 | m2 | 23 | 19780
sides
2.721 E | Internal baulstrade to staircase | 10.8 | m | 190 | 2052
2.741 | Toilet cublicles in sections of 4 | 66 | nr | 1125 | 74250
(per 2 rooms - due to layout)
| To Summary |  |  |  | 182206
Element 2.8 Internal Doors
partitions
2.811 A | Fire rated doors single leaf, veneer | 309 | nr | 610 | 188490
with vision panel
2.811 C | Double leaf internal doors (corridoors) | 12 | nr | 750 | 9000
| To Summary |  |  |  | 197490
TO SUMMARY |  |  |  |  | 2478849.6
Note on C10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assumed - based on building with similar GIFA
Note on C13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: GIFA
Note on C20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: (1850*5) - Allowance for all floors
Note on C37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Allowance for overhang of 100mm
Note on C41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Allowed area - based on similar building
Note on C47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Allowance for overhang of 100mm
Note on C58: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Allowed area - based on similar building
Note on C62: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Outside of roof area
Note on C64: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Outside of roof area
Note on C67: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Outside of roof area
Note on C80: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assumed staircases 1.8m * no of staircases
Note on C83: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assumed staircases 1.8m * no of staircases
Note on C119: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Window Schedule / 4 - to be determined throughout design development
Note on C121: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Window Schedule / 4 - to be determined throughout design development
Note on C123: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Window Schedule / 4 - to be determined throughout design development
Note on C125: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Window Schedule / 4 - to be determined throughout design development
Note on C127: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Inclusive of 1 x Shop Entrance Front, 1 x Shop Entrance Rear & 1 x Glazed Entrance
Note on C147: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Span of Building - Assumed this would be required due to the span of the building
Note on C151: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Calculation on Take-Off Sheet
Note on C154: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Calculation on Take-Off Sheet
Note on C157: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assumed staircases 1.8m * no of staircases
Note on C159: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Rooms halved - due to layout of building partitioning could be halved (backs onto another room)

## 3 Internal Finishes
PROJECT: SA1 MIXED USE DEVELOPMENT
COST PLAN GROUP ELEMENT: 3 INTERNAL FINISHES
Ref | Description | Qty | Unit | Rate | £ p
Hotel Area
Element 3.1 Wall Finishes
3.11 A | Internal wall finishes to be | 3425 | m2 | 16 | 54800
taped and jointed
3.11 B | Emulsion paint - base coat & | 3425 | m2 | 23 | 78775
second coat allowance
3.11 C | Internal walls to be finished | 3425 | m2 | 12.8 | 43840
with paint
| To Summary |  |  |  | 177415
Element 3.2 Floor Finishes
3.21 A | Floors to be finished with | 3425 | m2 | 36 | 123300
laminate throughout
3.21 B | MDF Skirtings with one coat | 3425 | m2 | 20 | 68500
of gloss paint
| To Summary |  |  |  | 191800
Element 3.3 Ceiling Finishes
3.31 A | Taped and jointed plasterboard | 3425 | m2 | 16 | 54800
ceiling
3.31 B | Emulsion paint - base coat & | 3425 | m2 | 23 | 78775
second coat allowance
3.31 C | Ceiling grid system & tiles to | 3425 | m2 | 43 | 147275
underside of plasterboard ceiling
| To Summary |  |  |  | 280850
Commericial (Shop) Area
Element 3.1 Wall Finishes
3.11 A | Internal wall finishes to be | 1571 | m2 | 16 | 25136
taped and jointed
3.11 B | Emulsion paint - base coat & | 1571 | m2 | 23 | 36133
second coat allowance
3.11 C | Internal walls to be finished | 1571 | m2 | 12.8 | 20108.8
with paint
| To Summary |  |  |  | 81377.8
Element 3.2 Floor Finishes
3.21 A | Floors to be finished with | 1571 | m2 | 36 | 56556
laminate throughout
3.21 B | MDF Skirtings with one coat | 1571 | m2 | 20 | 31420
of gloss paint
| To Summary |  |  |  | 87976
Element 3.3 Ceiling Finishes
3.31 A | Taped and jointed plasterboard | 1571 | m2 | 16 | 25136
ceiling
3.31 B | Emulsion paint - base coat & | 1571 | m2 | 23 | 36133
second coat allowance
3.31 C | Ceiling grid system & tiles to | 1571 | m2 | 43 | 67553
underside of plasterboard ceiling
| To Summary |  |  |  | 128822
TO SUMMARY |  |  |  |  | 948240.8
Note on C12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hotel rooms 25m2 * 132 for No. of Rooms
Note on C15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hotel rooms 25m2 * 132 for No. of Rooms
Note on C18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hotel rooms 25m2 * 132 for No. of Rooms
Note on C25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hotel rooms 25m2 * 132 for No. of Rooms
Note on C28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hotel rooms 25m2 * 132 for No. of Rooms
Note on C35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hotel rooms 25m2 * 132 for No. of Rooms
Note on C38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hotel rooms 25m2 * 132 for No. of Rooms
Note on C41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hotel rooms 25m2 * 132 for No. of Rooms
Note on C50: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Gross Internal Floor Area
Note on C53: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Gross Internal Floor Area
Note on C56: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Gross Internal Floor Area
Note on C63: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Gross Internal Floor Area
Note on C66: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Gross Internal Floor Area
Note on C73: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Gross Internal Floor Area
Note on C76: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Gross Internal Floor Area
Note on C79: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Gross Internal Floor Area

## 4 FF&E
PROJECT: SA1 MIXED USE DEVELOPMENT
COST PLAN GROUP ELEMENT: 4 FF&E
Ref | Description | Qty | Unit | Rate | £ p
Element 4.1 Fittings, furnishings
and equiptment
4.11 A | Allowance for FF&E (Provsional | 1 | item | 350000 | 450000
sum for fixed furniture)
4.41 B | Allowance for signs & notices | 1 | item | 50000 | 50000
(Provisional sum for signage)
| To Summary |  |  |  | 500000
TO SUMMARY |  |  |  |  | 500000

## 5 Services
PROJECT: SA1 MIXED USE DEVELOPMENT
COST PLAN GROUP ELEMENT: 5 SERVICES
Ref | Description | Qty | Unit | Rate | £ p
Element 5.1 Sanitary Installations
| Provisional Sum allowance | 1 | Item | Listed Below
for services
Element 5.2 Service Equipment
| Provisional Sum allowance | 1 | Item | Listed Below
for services
Element 5.3 Disposal Installations
| Provisional Sum allowance | 1 | Item | Listed Below
for services
Element 5.4 Water Installations
| Provisional Sum allowance | 1 | Item | Listed Below
for services
Element 5.5 Heat Source
| Provisional Sum allowance | 1 | Item | Listed Below
for services
Element 5.6 Space Heating & A/C
| Provisional Sum allowance | 1 | Item | Listed Below
for services
Element 5.7 Ventillation
| Provisional Sum allowance | 1 | Item | Listed Below
for services
Element 5.8 Electrical Installation
| Provisional Sum allowance | 1 | Item | Listed Below
for services
Element 5.9 Fuel Installations
| Provisional Sum allowance | 1 | Item | Listed Below
for services
Element 5.10 Lift & Conveyor
| Provisional Sum allowance | 1 | Item | Listed Below
for services
Element 5.11 Fire & Lighting
| Provisional Sum allowance | 1 | Item | Listed Below
for services
Element 5.12 Comms Systems
| Provisional Sum allowance | 1 | Item | Listed Below
for services
Element 5.13 Specialist Installations
| Provisional Sum allowance | 1 | Item | Listed Below
for services
Element 5.14 BWIC
| Provisional Sum allowance | 1 | Item | Listed Below
for services
TO SUMMARY |  |  |  |  | 500000

## 6 Prefab & Building Units
PROJECT: SA1 MIXED USE DEVELOPMENT
COST PLAN GROUP ELEMENT: 6 PREFABRICATION & BUILDING UNITS
Ref | Description | Qty | Unit | Rate | £ p
Element 6.1 Prefabricated Buildings
& Units
Not Applicable to Project
TO SUMMARY |  |  |  |  | 0

## 7 Works to Existing Buildings
PROJECT: SA1 MIXED USE DEVELOPMENT
COST PLAN GROUP ELEMENT: 7 WORK TO EXISTING BUILDINGS
Ref | Description | Qty | Unit | Rate | £ p
Element 7.1 Minor Demolition Works
& Alteration Works
Not Applicable to Project
Element 7.2 Repairs to Existing
Services
Not Applicable to Project
Element 7.3 Damp Proof Courses /
Fungus & beetle eradication
Not Applicable to Project
Element 7.4 Façade Retention
Not Applicable to Project
Element 7.5 Cleaning Existing Surfaces
Not Applicable to Project
Element 7.6 Renovation Works
Not Applicable to Project
TO SUMMARY |  |  |  |  | 0

## 8 External Works
PROJECT: SA1 MIXED USE DEVELOPMENT
COST PLAN GROUP ELEMENT: 8 EXTERNAL WORKS
Ref | Description | Qty | Unit | Rate | £ p
Element 8.1 Site Preparation Works
8.11 A | Clearance of vegitation | 3 | nr | 2475 | 7425
(m2 allowance - site survey
to inform)
8.21 B | Formation of new site contours | 1850 | m2 | 62 | 114700
site to be leveled (m2 allowance -
site survey to inform)
8.22 C | Breaking out of concrete (m2 | 500 | m2 | 49 | 24500
allownce - site survey to inform)
8.24 D | Grubbing up old drainage pipelines | 200 | m2 | 195 | 39000
(m2 allowance - site survey
to inform)
| To Summary |  |  |  | 185625
Element 8.2 Roads, Paths, Pavings
and Surfacing
8.21 A | Road to car park, coming in from | 250 | m2 | 295 | 73750
Langdon Road - Road width 3.5m
8.22 B | Paved areas - (m2 allowance - | 500 | m2 | 98 | 49000
further developed drawings to
inform)
8.25 C | Allowance for two road crossings | 2 | nr | 47000 | 94000
8.213 D | Repairs to existing pavings located | 100 | m2 | 211 | 21100
on incoming road (Langdon Road)
| To Summary |  |  |  | 237850
Element 8.3 Soft landscaping,
planting and irrigation systems
8.321 A | Allowance for nr planters to be | 6 | nr | 1000 | 6000
placed on new incoming road
8.324 B | Allowance for nr trees planted adjacent | 6 | nr | 150 | 900
to new incoming road
| To Summary |  |  |  | 6900
Element 8.4 Fencing, Railings and
Walls
8.41 A | Allowance for fencing around the | 200 | m2 | 240 | 48000
permeter of whole site (block boundary
wall)
8.44 B | Allowance for control barriers to | 6 | nr | 1200 | 7200
car park for out of hours traffic control
| To Summary |  |  |  | 55200
Element 8.6 External Drainage
8.6 A | Provisonal Sum Allowance for External | 1 | Item | 150000 | 250000
Drainage - To be specified in developed
drawings
| To Summary |  |  |  | 250000
Element 8.7 External Services
8.7 A | Provisonal Sum Allowance for External | 1 | Item | 150000 | 350000
Services - To be specified in developed
drawings
| To Summary |  |  |  | 350000
TO SUMMARY |  |  |  |  | 1085575

## 9 Main Contractors Prelims
PROJECT: SA1 MIXED USE DEVELOPMENT
COST PLAN GROUP ELEMENT: 9 MAIN CONTRACTORS PRELIMINARIES
Ref | Description | Qty | Unit | Rate | £ p
A | Main Contractors Preliminaries | 12 | % | 6955398.3 | 834647.796
at 12% of works cost
To Summary
TO SUMMARY |  |  |  |  | 834647.796

## 10 Main Contractors OHP
PROJECT: SA1 MIXED USE DEVELOPMENT
COST PLAN GROUP ELEMENT: 10 MAIN CONTRACTORS OHP
Ref | Description | Qty | Unit | Rate | £ p
A | Main Contractors over heads | 3 | % | 7790046.096 | 233701.3829
and profit (OHP) at 3% of works
cost
To Summary
TO SUMMARY |  |  |  |  | 233701.3829
Note on E8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Works cost + preliminaries

## 11 Project Design Team Fees
PROJECT: SA1 MIXED USE DEVELOPMENT
COST PLAN GROUP ELEMENT: 11 PROJECT DESIGN TEAM FEES
Ref | Description | Qty | Unit | Rate | £ p
A | Project Design Team Fees | 3 | % | 8023747.4789 | 240712.4244
and profit (OHP) at 3% of works
cost (Assumption of traditional
procurement design method)
To Summary
TO SUMMARY |  |  |  |  | 240712.4244
Note on E8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Contractors works cost + preliminaries + OHP

## 12 Other Project Costs
PROJECT: SA1 MIXED USE DEVELOPMENT
COST PLAN GROUP ELEMENT: 12 OTHER PROJECT COSTS
Ref | Description | Qty | Unit | Rate | £ p
A | Allowances made within
cost report
To Summary
TO SUMMARY |  |  |  |  | 0

## 13 Project Risks
PROJECT: SA1 MIXED USE DEVELOPMENT
COST PLAN GROUP ELEMENT: 13 PROJECT RISKS
Ref | Description | Qty | Unit | Rate | £ p
A | Risks withincost report
To Summary
TO SUMMARY |  |  |  |  | 0

## Roof Detail (Assumed)
ROOF DETAIL
ROOF DETAILED - ASSUMED WARM DECK
Source;
Flat Roof Design Considerations (bauder.co.uk)

## BCISIndices
Series: | BCIS All-in TPI |  |  | BCIS General Building Cost Index
Series number: | 101 |  | quarterly | 1111 |  | monthly
Base: | 1985 mean = 100 |  |  | 1985 mean = 100
Last updated: | 15-Sep-2023 |  |  | 24-Oct-2023
Notes:
Downloaded: | 26-Oct-2023 13:45
Date | Index | Status | Equivalent sample | Index | Status
2020-10-01 |  |  |  | 362.6 | Firm
2020-11-01 | 328 | Provisional |  | 363.6 | Firm
2020-12-01 |  |  |  | 366.2 | Firm
2021-01-01 |  |  |  | 367.1 | Firm
2021-02-01 | 328 | Provisional |  | 370.4 | Firm
2021-03-01 |  |  |  | 373.5 | Firm
2021-04-01 |  |  |  | 375.6 | Firm
2021-05-01 | 331 | Provisional |  | 378.4 | Firm
2021-06-01 |  |  |  | 381.4 | Firm
2021-07-01 |  |  |  | 388.2 | Revised
2021-08-01 | 339 | Provisional |  | 395.6 | Revised
2021-09-01 |  |  |  | 399.6 | Revised
2021-10-01 |  |  |  | 402.4 | Revised
2021-11-01 | 344 | Provisional |  | 404.7 | Revised
2021-12-01 |  |  |  | 405 | Revised
2022-01-01 |  |  |  | 406.4 | Revised
2022-02-01 | 349 | Provisional |  | 408.1 | Revised
2022-03-01 |  |  |  | 413.2 | Revised
2022-04-01 |  |  |  | 425.1 | Revised
2022-05-01 | 365 | Provisional |  | 433.7 | Firm
2022-06-01 |  |  |  | 440.6 | Revised
2022-07-01 |  |  |  | 440.7 | Revised
2022-08-01 | 371 | Provisional |  | 444.7 | Revised
2022-09-01 |  |  |  | 441.9 | Firm
2022-10-01 |  |  |  | 442.9 | Firm
2022-11-01 | 375 | Provisional |  | 441.7 | Revised
2022-12-01 |  |  |  | 440.4 | Revised
2023-01-01 |  |  |  | 440.9 | Firm
2023-02-01 | 379 | Provisional |  | 442.3 | Firm
2023-03-01 |  |  |  | 443.4 | Firm
2023-04-01 |  |  |  | 445.5 | Firm
2023-05-01 | 383 | Provisional |  | 446.7 | Firm
2023-06-01 |  |  |  | 443.9 | Firm
2023-07-01 |  |  |  | 454.1 | Provisional
2023-08-01 | 386 | Provisional |  | 453.6 | Provisional
2023-09-01 |  |  |  | 452.3 | Provisional
2023-10-01 |  |  |  | 454.1 | Forecast

## BCISIndicies2
Series: | BCIS All-in TPI
Series number: | 101 |  | quarterly
Base: | 1985 mean = 100
Last updated: | 08-Dec-2023
Notes:
Downloaded: | 29-Feb-2024 10:01
Date | Index | Status | Equivalent sample
2022-02-01 | 349 | Provisional
2022-05-01 | 365 | Provisional
2022-08-01 | 371 | Provisional
2022-11-01 | 375 | Provisional
2023-02-01 | 379 | Provisional
2023-05-01 | 383 | Provisional
2023-08-01 | 386 | Provisional
2023-11-01 | 388 | Provisional
2024-02-01 | 389 | Forecast
2024-05-01 | 391 | Forecast
2024-08-01 | 393 | Forecast
2024-11-01 | 396 | Forecast
2025-02-01 | 399 | Forecast

## BCISIndices - Location
Series: | BCIS Regional TPI: Greater London
Series number: | 228 |  | quarterly
Base: | 2010 mean = 100
Last updated: | 15-Sep-2023
Notes: | Derived index based on BCIS Tender Price Studies
Downloaded: | 31-Oct-2023 11:05
Date | Index | Status | Equiv. Sample | Percentage change
|  |  |  | On year | On quarter
2021-11-01 | 184 |  | 11 | 5.1 | 1.7
2022-02-01 | 187 |  | 11 | 7.5 | 1.6
2022-05-01 | 195 |  | 10 | 10.8 | 4.3
2022-08-01 | 198 |  | 9 | 9.4 | 1.5
2022-11-01 | 200 |  | 9 | 8.7 | 1.0
2023-02-01 | 203 |  | 8 | 8.6 | 1.5
Series: | BCIS Regional TPI: Wales
Series number: | 232 |  | quarterly
Base: | 2010 mean = 100
Last updated: | 15-Sep-2023
Notes: | Derived index based on BCIS Tender Price Studies
Downloaded: | 31-Oct-2023 11:05
Date | Index | Status | Equiv. Sample | Percentage change
|  |  |  | On year | On quarter
2021-11-01 | 166 |  | 3 | 4.4 | 1.2
2022-02-01 | 169 |  | 3 | 6.3 | 1.8
2022-05-01 | 177 |  | 2 | 10.6 | 4.7
2022-08-01 | 180 |  | 2 | 9.8 | 1.7
2022-11-01 | 181 |  | 2 | 9.0 | 0.6
2023-02-01 | 183 |  | 2 | 8.3 | 1.1

## Regional TPI's
Series: | BCIS Regional TPI: Wales
Series number: | 232 |  | quarterly
Base: | 2010 mean = 100
Last updated: | 08-Mar-2024
Notes: | Derived index based on BCIS Tender Price Studies
Downloaded: | 09-Apr-2024 11:09
Date | Index | Status | Equiv. Sample
2022-05-01 | 176 |  | 2
2022-08-01 | 179 |  | 2
2022-11-01 | 181 |  | 2
2023-02-01 | 182 |  | 2
2023-05-01 | 184 |  | 2