## Sheet1
total estimated cost | 3600 |  | By Catergory | Atual Cost of catergory
total actual cost | 4315 |  | painting | 475
remaining money | -715 |  | Floor Layers | 500
contingency | 540 |  | Window Installations | 0
|  |  | Gas installations | 0
|  |  | Plumbing | 640
|  |  | Carpentering | 400
Items | Catergory | Estimated Cost | Actual Cost | Net
Paint | painting | 300 | 275 | 25
Flooring panels | floor layers | 400 | 500 | -100
double glazing windows | window Installation | 1000 | 1000 | 0
boiler | gas Instillation | 600 | 1000 | -400
cooker | Plumbing | 300 | 290 | 10
wall tiles | painting | 150 | 200 | -50
windows fitting | window Installation | 150 | 300 | -150
door | carpentering | 400 | 400 | 0
bath | Plumbing | 300 | 350 | -50