## Organising the conference

## Theme – Contemporary Issues facing the Hotel and Hospitality Industry

Every great conference needs a theme. What’s the unifying message that your speakers will deliver and what’s the key takeaway for conference attendees?

The best themes are catchy, relatable, and trigger an emotional response. You want the conference to inspire and stimulate conversation. Your theme has to enable that.

The theme is more than just a rallying cry for all participants; it will also guide your branding and promotion, from designing a logo to coming up with social media hashtags to printing your posters, brochures, and other collateral.

## Assemble your team

You will be organising a whole conference all by yourselves.

You’ll need a dedicated team of people to assume responsibility for different aspects of the planning, negotiations, and promotion. Your core team will likely include:

- Planning team: Conference venue, accommodation, activities, catering.

- Administration team: Budgeting, attendee registration, ticket sales. This team/person will also be the main point of contact for questions related to the conference.

- Marketing team: Contacting the media, creating promotional material, managing your website, blog, and social media activities.

- Sponsorships team: In charge of securing sponsors, applying for grants, and fundraising.

- Volunteers: Helping with all on-site activities on the day of the conference: door management, ticket scanning, keeping track of the guest list, manning the wardrobe, guiding people, etc.

- You will need to meet to coordinate the team, set priorities, and delegate tasks. All meetings should be chaired, and a record of each meeting should be kept.

Prepare a budget & business plan

You’ll have to put together a budget. You need to know where your money is being earned and spent.

Having a budget will also help you set the price for participating in the conference. Here are the most common items you’ll want to budget for:

- Venue

- Accommodation

- Transportation

- Catering

- Speaker fees

- Activities

- Marketing

- Team members

Preparing a budget with realistic estimates will also come in handy when searching for venues and negotiating contracts.

## Find sponsors & grants [optional]

If you decide that you’re financing the conference on your own and are not looking for external sources of revenue, you can safely skip this step.

If not, you’ll want to go out looking for sponsors or arrange fundraisers. The key thing to keep in mind is that the sponsors and their values should align with the theme of your conference. (Would you want a building firm to sponsor your “Hospitality conference?)

Start by finding sponsors that fund similar events or are generally associated with your conference’s main themes (e.g. the Marriott).

Decide how much say the sponsors should have in how the conference is run. Will you allow their branding and logo on every piece of equipment? Will they be able to bring in their own speakers?

Remember: It’s a fine balance between getting funded and sacrificing the integrity of your conference. You’re the judge of where to draw that line.

## Settle on a date (8th June in this case)

Now it’s time to decide when your conference will take place. As discussed, that date should be anywhere from six months to a year ahead.

You also need to find out how long the conference will last. Industry consensus suggests that a conference with around 150 participants calls for one full day. Larger, more in-depth conferences may stretch for even longer.

Here are some great rules of thumb to keep in mind:

- Pick a date that doesn’t conflict with other major events like festivals. City-wide events make booking flights more expensive and generally hinder transportation to and from the conference. Besides, you don’t want your conference to compete for attention with big events.

- Avoid summer and winter holiday periods when people tend to go on vacation. It’s best to aim for a date between the middle of March and end of June or from early September to late November.

- Never plan a conference during the weekend. For most participants, attending a conference is a part of their job, so schedule it during the workweek.

- Try to aim for the end of the week, so that traveling attendees get the chance to stay behind and sightsee during their time off. The best days for a conference are Thursday and Friday.

Setting a date will give you a fixed point to count back from to better plan your preparations.

Book the venue

As you know the date, you can start looking for available venues that match your requirements.

In general, venues might fall into three categories:

- University campuses: These are best suited for smaller, academic events and are relatively cheap to hire.

- Hotels: These typically have dedicated conference facilities and own catering. They’re the best all-in-one choice since they offer both accommodation and conference space. They also tend to be the most expensive option.

- Independent venues: This category includes all other types of venues that can host conferences. Many of these specialise in specific types of events.

But the cost of the venue is just one part of the puzzle. Here are a few other factors to consider when looking for the right venue:

- Size: Booking a too-small venue where everybody has to squeeze into a tiny room is clearly a bad idea. Similarly, securing a giant venue for a relatively modest crowd will not only hurt your wallet but also make the conference feel empty and poorly attended.

- Location: It’s best to pick a somewhat secluded location so that participants are better able to focus on the conference itself. Even better if the venue has calming, picturesque surroundings to help people relax.

- Atmosphere: It’s crucial that the vibe of the venue suits your target audience and theme. You don’t want to host a business conference inside a giant gym, for instance.

- Facilities: Does the venue have the proper layout and the right conference room styles for your needs? Does it have the necessary facilities like e.g. smaller rooms for breakout sessions?

- Accommodation: Does the venue provide accommodation or are there hotels nearby? Do you needaccommodation

- Catering: Is catering included or can external catering companies easily get to and work inside the venue? If not, are there suitable restaurants and cafes in the area? (Keep in mind any special dietary requirements: vegan, kosher, nut-free, etc.)

- Transportation: How easy is it for participants to travel to the venue by public transport? Are there enough parking spots for those who drive?

- Technical aspects: Does the venue have the right IT, audio, and video equipment? You’ll need projection screens, microphones, plenty of charging spots for participants, and---of course---solid WiFi access.

When negotiating with potential venues, try to arrange for early access to the place so that you can do a “dry run” or a walkthrough with your team prior to the conference. You should be able to ensure that every detail is in place before the big day.

Quick tip: If you find a great venue that’s just out of your budget, see if you can negotiate a lower fee in return for a multiyear contract (provided you’re organising a recurring conference).

## Arrange catering & other vendors [optional]

Typically, a dedicated conference venue will also provide on-site catering. If that’s not the case, you’ll need to bring in external vendors.

Decide on what type of refreshments you want to offer and how many breaks there’ll be for food. Reserve up to an hour for lunch and a few 15-20 minute breaks for coffee and snacks. Remember: If there’s room in your budget, it’s always best to go for proper hot meals instead of sandwiches when it comes to lunch.

You want to be sure that the catering company can handle the logistics on the day of the event. Your best bet is to find a local company close to the conference venue to avoid potential traffic-related issues and delays.

Don’t forget to check how far in advance the caterer needs to know the final headcount, the menu, and any special dietary requirements. That way you’ll also know what “RSVP by” date to put on the conference invite.

Think about any other external vendors you might need, such as a decorating company or suppliers of special IT equipment.