## Disertation research timeline
Tentative Disertation Work Timeline
Month | February |  |  |  | March |  |  |  | April |  |  |  | May
Week | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16
Task
Research proposal submission | bar: February Week 1
Ethics submission | bar: February Week 1
Literature review | bar: February Week 1 to March Week 8
Supervisory meetings | bar: February Week 3; March Week 5 to March Week 6; March Week 8; April Week 11; May Week 13 to May Week 15
Concetual framework | bar: February Week 2 to March Week 6
Methodological framework | bar: February Week 3 to March Week 7
Data collection (Preparation and Planning for data collection) | bar: March Week 7 to April Week 9
Data analysis (Systematic review of existing research evedence) | bar: March Week 8 to April Week 11
Writing up | bar: February Week 3 to April Week 12
Finalizing | bar: May Week 13 to May Week 14
First draft-target | bar: May Week 14
Final submission-target | bar: May Week 16
Notes:
1. Research proposal,ethics form and time line to be submitted by the 16th of February 2024
2.Data collection to commence in week 7
3. First draft to be submitted in week 14
4.Final submission of research study by week 16