BA (Hons) Leadership and Management Skills in the Workplace
Module Assignment Submission

| Student Name: | Jessica Rudall |
| --- | --- |
| Student Number: | 2308141 |
| Module No: | BMSK5014 |
| Module Title: | Managing Projects |

Table of Contents

1. Introduction	3

2. Defining the Project Idea – What and WHY	4

2.1 Project Aim	4

2.2 Project Objectives	4

2.3 Business Case	5

3. Application of Project Management Philosophies & Processes (HOW)	9

3.1 Project Management Methodologies	9

3.2 Project Initiation	12

3.3 Environmental Analysis	13

3.4 Work Breakdown Structure	14

3.5 Project Management Tools & Communication Plan	15

3.6 Risk Identification & Management	17

3.7 Monitoring & Project Close Down	18

4. Key attributes of a Project Manager	20

5. Self-Audit & Personal Development Plan	21

5.1 Self Audit Skills Assessment	21

5.2 Strengths & Weaknesses	22

5.3 Personal Development Plan	22

6. Conclusion	23

References	25

Appendix A	29

Appendix B	30

Appendix C	31

Appendix D	32

Appendix E	33

Appendix F	34

Appendix G	36

Bibliography	37

# Managing Projects

# 1. Introduction

The NHS is under increasing pressure from rising patient numbers, workforce shortages, and the need to greater operational efficiency. Outpatient departments within the NHS are particularly vulnerable to inefficiencies caused by manual check-in processes. Patients are often facing long queues at reception desks, creating delays for clinics, and leading to frustration for both patients and staff. The current state of outpatient care in the NHS is unsustainable, the system is overstretched and in increasing demand. The NHS has committed to improving patient care and accessibility and to do this they need to embrace modern, data-driven solutions. This will revolutionise outpatient care, increase efficiency, and improve patient experience and outcomes.

Digital transformation has become a core element of NHS improvement strategies. The introduction of self-service check-in kiosks offers a practical and scalable solution to improve patient experience and allow staff to focus on complex administrative or clinical tasks. This project proposes the acquisition, installation, and integration of a kiosk system into the outpatient departments on an NHS trust. The kiosk system will enable patients to check in by scanning a QR code from their appointment letter or entering personal details, automatically updating the clinic’s appointment system and directing them to the correct waiting area. This approach aligns with the NHS’ goal of modernising patient pathways, reducing unnecessary waiting, and improving service accessibility.

The purpose of the report is to define the concept, objectives, and rationale for the project. Academic project management theories and models will be applied to the planning and delivery of the initiative which include Waterfall Lifecycle, PRINCE2, and Agile. A project charter will be included withing the report which will include stakeholders. An environmental analysis will also be completed using PESTLE analysis and SWOT analysis. The report will critically assess project management tools and techniques using Gantt charts, Kanban boards, and RACI matrix and their usefulness in healthcare projects. It will include risk identification and management, as well as the monitoring and project closure. The report will explore the competencies of an effective project manager and undertake a s self-audit with a personal development plan.

# 2. Defining the Project Idea – What and WHY

## 2.1 Project Aim

The aim of this project is to design, produce, install, and integrate a Digital Patient Self-Check-In Kiosk System into NHS outpatient clinic within six months, improving patient flow, reducing administrative constraints, and enhancing the overall patient experience. As stated by ILX Marketing Team (2024) “a project is a unique and temporary organisation, designed to deliver a tangible output. It has a fixed – generally fairly short – timeframe, and a project manager is responsible for delivering the output on time and on budget.”

As stated by the Department of Health & Social Care & Prime Minister's Office (2025), the NHS 10-year health plan outlines a bold transformation of the NHS into a future-ready model of care. The plan retains the founding principles of free, universal and need-based care that is funded by taxation but reconstructs delivery to give patients genuine control and choice. One key change within the plan is technology-led transformation that leverages science and innovation to move the NHS into a leading health care system globally.

## 2.2 Project Objectives

| Objective | Specific | Measurable | Achievable | Relevant | Time-specific |
| --- | --- | --- | --- | --- | --- |
| Install kiosks in three pilot outpatient departments | Install self-service kiosks in 3 pilot outpatient departments | Number of kiosks installed in target locations | Resources and budget available to install 3 kiosks | Supports project goal of improving check-in efficiency | By Q3 (oct-dec) 2025 |
| Reduce patient check-in time by 40% within three months of implementation | Shorten average patient check-in duration using kiosks | % reduction in check-in time (baseline vs after implementation) | Achievable with streamlined process and kiosk use | Improves efficiency and patient flow | Within 3 months of kiosk launch |
| Improve patient satisfaction scores in Friends and Family Test surveys by 20% within six months of impleme-ntation | Increase positive survey responses | % increase in positive scores compared to baseline | Based on improved service speed and autonomy | Aligns with aim to enhance patient experience | Within 6 months of kiosk launch |
| Achieve 95% data accuracy in check-in records by reducing manual input errors | Improve accuracy of patient data entry | % accuracy rate in records | Kiosks reduce manual input errors | Ensures reliable records for clinical and admin processes | Ongoing after launch |
| Train 100% of reception staff on kiosk troubleshooting and patient support before launch | All reception staff complete training | % of staff trained and certified | Training resources and schedule in place | Staff readiness ensures smooth implementation | Before kiosk launch date |

## 2.3 Business Case

Reasons (project mandate): The NHS is faced with increasing patient volumes, longer waiting times, and mounting administrative pressures, which is challenged by manual check-in processes that cause constraints at reception desks, reduces staff efficiency, and decreases patient satisfaction. Outpatient areas are often overcrowded with patients queueing for manual check-in, resulting in delays, disrupted clinic schedules, and reduces satisfaction (Sehgal et al., 2024). In response, and in line with the NHS’s Long Term Plan emphasis on digital transformation, this project proposes the introduction of self-service check-in kiosks to modernise patient administration, reduce waiting times, improve data accuracy, and enhance the patient journey across both outpatient and primary care settings.

Options: Several options were considered:

Do nothing: To continue with existing manual processes, resulting in no capital investment but maintaining inefficiencies and poor patient experience.

Partial Digital Adoption: Deploy kiosks in selected areas only (high volume outpatient clinics). This reduces upfront costs but risks inconsistency and lower impact.

Full Implementation: Deploy kiosks across all high-volume entry points, supported by staff training and integrated with electronic patient record systems (EPR’s). This maximises long-term benefits, aligning with national digital health priorities proving scalable infrastructure.

Benefits Expected: The project is expected to deliver both quantifiable and qualitative benefits:

Operational Efficiency: Operational: According to Savience Ltd (2023) self-service check-in kiosks have many operational benefits such as reduced waiting times by automating the check-in process. Kiosks reduce patient waiting times by streamlining registration, allowing paperwork to be completed quickly and efficiently. This lowers congestion in outpatient areas and improves overall operations and reduction of administrative workload by approximately 2 FTE staff per year.

Patient Experience: Patient: In a study conducted by West Suffolk NHS Foundation Trust (2024) the self-service check-in kiosks already in use across the NHS, are user-friendly and let patients indicate sight or hearing needs, which are communicated directly to care teams. Staff are available to assist as needed. The kiosks also connect to a dashboard, showing staff which patients have arrived, are waiting, and may require extra help, reducing waiting times and increased autonomy in the check-in process.

Accuracy: Automated data entry reduces errors in patient demographics and appointment records.

Strategic Alignment: Contributes to NHS digitalisation objectives and improves readiness for future innovations (e.g., AI triage or automated referrals). It also enhances compliance with Care Quality Commission (CQC) efficiency and patient experience standards.

Staff Morale: Storey (2024) observes that reduced involvement in complex administrative tasks and increased data security allow staff to allocate more time to other responsibilities and complex tasks. Frontline staff can be redeployed to higher-value, patient-facing activities instead of repetitive admin tasks.

Risks: Key risks that are associated with the project include:

Technical Issues: System downtime or integration problems with existing NHS software.

Cybersecurity: Risks around GDPR compliance and patient data protection.

User Resistance: Some patients may resist using kiosks, particularly the older or less digitally literate groups.

Cost Overruns: Unforeseen implementation or maintenance expenses.

Change Management: Staff reluctance to adopt new systems could slow transition.

The risks identified need mitigation strategies which include robust IT testing, comprehensive training programmes, a clear communication plan, and contingency funding.

Evidence Base: A trial conducted by the University Hospital of Leicester found that there were many targeted benefits to the trust which included: a reduction in missed and late appointments – a 5% reduction in Did Not Attend (DNA) rates was estimated to achieve a saving of up to £672,000 per year. It was found that there was also an improvement in patient quality of care, reduction in disruption to staff productivity, and an improvement in patient and visitor experience (NHS England, 2025). Case studies from other NHS trusts show that kiosks can reduce average check-in times by 50% (NHS England, 2024)

In the study conducted by Digital Health News (2021) it was found that patient check-ins via self-service kiosks are estimated to take somewhere between 6 – 30 seconds for patients to register their arrival using their personal information. In various UK hospitals, the technology has received a 95% patient uptake rate which has reduced the administration load and the cost that is associated with the traditional hospital check-in. In agreement with the evidence stated above, research from Greenhalgh et al. (2022) highlights improved patient satisfaction when digital self-service options are available alongside staffed desks.

Cost and Timescale: The project is scoped over a 6-month implementation timeline:

- Months 1-2: Procurement, system design, and stakeholder engagement.

- Months 3-4: Installation, integration, and pilot testing.

- Months 5-6: Full rollout, staff training, and evaluation.

Estimated Costs (3-Year Horizon):

- Capital expenditure: £40,000 (hardware)

- Operational expenditure: £103,000 (software, training, maintenance, compliance, contingency)

- Total Cost: £143,000

Investment Appraisal (Cost Benefit): The cost–benefit analysis indicates strong financial viability:

- Annual Benefits: £105,000 (admin cost savings, error reduction, patient satisfaction improvements, scalability).

- 3-Year Benefits: £315,000

- Total Project Cost: £143,000

- Net Benefit: £172,000 over 3 years

- ROI: 120%

- Payback Period: 1.4 years

Beyond financial gains, the project supports NHS strategic objectives, reduces staff strain, and improves the patient journey. A cost benefit analysis can be found in Appendix E.

Evaluation: Project success will be evaluated against the following criteria:

- Operational KPIs: Reduction in patient check-in times, decreased reception staff workload, and error rates in appointment data.

- Patient Experience KPIs: NHS Friends and Family Test scores, waiting room satisfaction surveys.

- Financial KPIs: Realised cost savings versus forecast.

- Project Management KPIs: Delivery on time, within budget, and to scope.

A post-implementation review will be conducted 12 months after rollout to assess realised benefits, lessons learned, and scalability potential.

Stakeholders:

| Stakeholder | Interest | Influence | Engagement Strategy |
| --- | --- | --- | --- |
| NHS Trust Management | High | High | Monthly progress reports and budget updates |
| Outpatient Reception Staff | High | Medium | Hands-on training, involvement in design |
| IT Department | Medium | High | Weekly technical planning meetings |
| Patients | High | Low | Clear signage, simple user interface, feedback surveys |
| Kiosk Supplier | Medium | Medium | Contractual obligations, regular supplier meetings |

# 3. Application of Project Management Philosophies & Processes (HOW)

## 3.1 Project Management Methodologies

As defined by Donato (2025), “Project Management is the application of knowledge, skills, methodologies, and techniques to achieve specific and measurable project goals, including successful project completion”. Typically, the project management life cycle consists of five phases: initiation, planning, execution, monitoring and control, and closure.

Selecting the appropriate project management methodology is critical to the success of any NHS initiative, particularly when balancing regulatory compliance with the need for flexibility in responding to user feedback. Three methodologies that are widely used are Waterfall, Agile, and PRINCE2, all three provide contrasting approaches to structuring project delivery.

Waterfall

The Waterfall model, developed by Winston Royce in 1970, is a linear, sequential approach consisting of six stages: Requirements (Discovery Phase), Design, System Testing, Implementation, Verification/Integration, and Maintenance. Each phase must be completed before moving to the next.

- In Requirements, teams collect detailed needs through research and stakeholder input.

- Design produces a fixed project blueprint with little room for change later.

- System Testing checks all components for compatibility and performance.

- Implementation assigns development tasks sequentially to avoid overlap.

- Verification/Integration ensures all parts fit together correctly.

- Maintenance involves fixing bugs and updating the product after launch.

Advantages include a clear structure, ease of tracking progress, early goal setting, and high stability due to defined requirements. However, limitations include high risk and uncertainty, delayed results, lack of flexibility for mid-project changes, and challenges in identifying issues early (Alazzawi, 2023).

Agile Project Management

Agile Project Management (APM) focuses on collaboration, customer feedback, and rapid delivery via short sprints. It breaks work into manageable pieces and incorporates ongoing communication and feedback. Agile delivers functional products incrementally, allowing regular adjustment based on stakeholder input (Good, 2025).

Key benefits:

- Rapid development and delivery

- Flexibility to adapt to changes

- Ongoing customer involvement

- Efficient use of resources

- Early and continuous value delivery

- Stakeholder engagement

- Responsiveness to emerging issues

However, Agile can pose challenges in highly regulated environments like the NHS, such as managing scope creep and compliance needs.

PRINCE2

PRINCE2 is a process-driven methodology dividing projects into stages, each managed independently with defined inputs, outputs, and goals. There are seven processes: Starting Up, Initiating, Directing, Controlling a Stage, Managing Product Delivery, Managing a Stage Boundary, and Closing the Project (Mitchell, 2025).

Benefits:

- Predictable, structured project management

- Effective delivery using standardised processes

- Cost and time efficiency, especially in large organisations like the NHS

- Trusted approach with over 30 years of use

Limitations include excessive administration and slower decision-making. Streamlining processes and empowering teams can help address these issues.

For the Digital Patient Self-Check-In Kiosk project, a hybrid model combining PRINCE2’s structured governance with Agile’s iterative feedback loops is recommended.

Why hybrid works here:

- PRINCE2 ensures compliance with NHS governance, procurement rules, and funding accountability.

- Agile principles allow for patient and staff feedback during kiosk design, ensuring usability and accessibility.

- Early testing in pilot clinics enables refinements before full rollout, reducing risk of costly errors.

This approach delivers governed flexibility, which is a crucial balance for healthcare technology projects in a regulated environment.

## 3.2 Project Initiation

As stated by MacNeil (2025), the project initiation process provides a structure method to present the project’s business case and to establish it is achievable. Project initiation incorporates stakeholder involvement at an early stage, which helps secure necessary resources, increases project visibility, and reduces potential obstacles. The initiation phase defines the foundations of the project by clarifying the purpose, scope and governance structure. This step is important in the NHS due to requirements for public accountability, compliance with procurement regulations, and patient safety considerations.

Project Charter

Project Title: Implementation of a Digital Patient Self-Check-In Kiosk System in NHS Outpatient Clinics.

| Scope | Inclusions | Exclusions | Deliverables | Budget | Timescale |
| --- | --- | --- | --- | --- | --- |
| Pilot outpatient clinics | Procurement and installation of kiosks in three pilot outpatient clinics Integration with existing NHS patient management systems Staff training and patient communication materials Pilot testing and post-implementation review | Expansion beyond pilot clinics in the current project phase Development of new patient management software (integration only) | Fully installed and tested kiosks in pilot clinics Staff trained to assist patients and troubleshoot Operational guidelines and maintenance procedures Post-implementation review report with recommendations | Total estimated cost: £120,000 Hardware: £60,000 Software integration: £25,000 Staff training: £10,000 Contingency: £25,000 | Start date: September 2025 Completion date: March 2026 (6 months total duration) |

Roles and Responsibilities

| Role | Responsibility |
| --- | --- |
| Project Sponsor | Provides strategic oversight and funding approval. |
| Project Manager | Oversees project delivery, manages team, monitors progress. |
| Technical Lead | Manages kiosk installation and system integration. |
| Change Manager | Coordinates staff training and stakeholder engagement. |
| Supplier Account Manager | Ensures timely delivery and technical compliance. |

Governance Structure (NHS)

In the NHS, a clear governance structure defines who is accountable for decisions and how those decisions are made, ensuring effective oversight from executive boards down to frontline staff. Roles and responsibilities are documented to align everyone towards shared organisational goals, with processes in place for monitoring, review, and accountability.

The project will follow a PRINCE2 approach, with approval required at each key milestone:

- Concept approval.

- Procurement approval.

- Pilot site sign-off.

- Final project closure.

## 3.3 Environmental Analysis

A thorough understanding of both the internal and external factors affecting the NHS is crucial for the successful implementation of digital health initiatives. In this section, PESTLE and SWOT analytical frameworks are applied to evaluate the challenges and opportunities surrounding the deployment of the Digital Patient Self-Check-In Kiosk System within NHS Trusts. A PESTLE analysis and SWOT analysis can be found in Appendix F.

The environmental analysis demonstrates that within the NHS, political and technological developments provide a strong foundation for introducing digital check-in kiosks. However, economic constraints and social considerations require thoughtful planning and clear communication with both staff and patients. Effective risk management should prioritise safeguarding patient data, delivering comprehensive training for staff, and ensuring that kiosk designs are accessible to all users.

## 3.4 Work Breakdown Structure

According to Raeburn (2025), a Work Breakdown Structure (WBS) helps NHS teams organise complex projects like Digital Patient Self-Check-In Kiosks by dividing tasks into clear phases and deliverables. A typical NHS WBS covers project scope, stakeholder identification, timelines, and key deliverables such as system installation and staff training. Project managers use the WBS to visualise responsibilities, ensure compliance, and manage resources effectively throughout the lifecycle, supporting quality and safety at each stage. A WBS can be found in Appendix G.

## 3.5 Project Management Tools & Communication Plan

Effective project management within the NHS relies on the use of structured tools and a robust communication plan to ensure clarity, accountability, and timely delivery. Project management tools such as: Gantt charts, Kanban boards, RACI Matrix, Risk registers, project calendars, software platforms, task lists, and templates. These are essential resources that help organise and execute various aspects of a project. They represent the “how” of project management, supporting goals like improving communication, monitoring performance, and facilitating planning, all while balancing the NHS’s formal governance requirements with the flexibility to adapt to operational challenges (Landau, 2024).

Project Management Tools

Gantt Chart – A Gantt chart is a horizontal bar chart used to organise project tasks and timelines, listing tasks vertically and time spans horizontally. Each bar shows the start date, duration, due date, and progress.

- Strengths: Makes scheduling clear and delays easy to spot. Useful for tracking procurement, installation, and training phases.

- Weaknesses: Can be inflexible and complex if the project scope changes often, may not cover resource allocation well.

Application: Used to monitor procurement, installation, and training.

A Gantt chart diagram can be found in Appendix A.

RACI Matrix – Matthews (2024) describes the RACI matrix as a project management tool that maps risk likelihood and impact, helping managers prioritise resources. For the NHS patient kiosk project, risks were identified across technical, operational, financial, and human factors.

Strengths – Improves engagement, planning, communication, leadership sign-off, and accountability.

Weaknesses – Lacks clarity on role scope and verification, requires frequent updates, and is less suited for agile team-based approaches.

Application – Assigning responsibilities to NHS staff, suppliers, and IT teams.

A RACI Matrix diagram can be found in Appendix B.

Kanban Boards – As stated by Rehkopf (2025) a kanban board is a tool used in project management that helps visualise work, limit work-in-progress, and support workflow. Kanban boards use cards, columns, and continuous iteration to assist with planning and tracking the amount of work assigned and completed.

Strengths – Kanban boards are simple, adaptable and they promote transparency.

Weaknesses – Less structured for large, multi-phase projects.

Application – Tracking real-time installation tasks at each pilot site.

A diagram of the Kanban board tool can be found in Appendix C.

Risk Register – A risk register is a tool for identifying potential project risks, usually developed during planning but used throughout execution. Creating it early supports effective risk management (Landau, 2023).

Strengths – Proactive approach to risk mitigation.

Application – Recording risks such as technical failure or patient resistance.

A Risk register can be found in Appendix D.

Critical Assessment

While Gantt charts offer a comprehensive overview, they can lack flexibility in dynamic environments like healthcare. Agile tools such as Kanban boards provide adaptability but may not meet NHS governance requirements alone. A combined approach is most effective, using Gantt charts for high-level planning and Kanban boards for day-to-day task tracking.

Communication Plan

| Purpose/Topic | Owner | Method | Stakeholder(s) | Input/output/ evidence | Frequency |
| --- | --- | --- | --- | --- | --- |
| Ensure alignment with strategic objectives and funding. | PM | Formal progress reports, Steering Group meetings | NHS Trust Management | Strategic plans, funding reports, progress reports, meeting minutes. | Monthly |
| Build confidence, reduce resistance. | PM | Workshops, training sessions, Q&A drop-ins | Reception Staff | Workshop materials, training session feedback, attendance records, Q&A session notes. | Weekly during training phase |
| Inform and reassure users. | PM | Posters, leaflets, on-screen guidance | Patients | Posters, leaflets, on-screen guidance materials, user feedback | At go-live |
| Ensure integration and problem resolution. | PM | Technical meetings, email updates | IT Department | Technical meeting minutes, email updates, issue logs, resolution reports | Weekly |
| Monitor deliverables and resolve supply issues. | PM | Contract review meetings | Suppliers | Contract review meeting minutes, supplier performance reports, delivery schedules | Fortnightly |

Using structured tools in combination with a stakeholder-focused communication plan, enables efficient project delivery, risk management, and supports users during implementation of the self-service check-in kiosk system.

## 3.6 Risk Identification & Management

According to NHS England (2024), effective risk identification and management is essential for successful NHS projects, especially those involving new digital technologies and sensitive patient data. Organisations must identify, analyse, prioritise, and manage risks throughout the project lifecycle, following established standards and best practices. This includes defining risk appetite, using a shared language and scoring system, and implementing robust risk frameworks linked to accountability structures such as Provider Boards, GDPR, Integrated Care Systems, ICBs, and CQC. These frameworks should address quality, operational, and financial risks, referencing guidance like the National Patient Safety Agency’s Risk Matrix (2008). The use of a risk register provides a systematic method for monitoring and mitigating threats, an example of the risk register for this project can be found in Appendix D.

Critical Assessment

From the risk matrix that has been completed, high-priority risks include technical integration and staff resistance, as these could prevent the successful implementation of the project. Early engagement and thorough testing are critical mitigation strategies. The moderate risk is patient resistance, particularly with regards to outpatient clinics with older demographics. Providing parallel check-in options will ensure inclusivity. Cybersecurity presents a high-impact risk despite low likelihood. Due to the involvement of sensitive patient data, robust encryption and compliance with NHS Digital and GDPR standards are non-negotiable. 
Proactive risk management will safeguard project success by minimising disruptions, maintaining compliance, and ensuring acceptance by both staff and patients.

## 3.7 Monitoring & Project Close Down

Monitoring and project closure ensure that the project delivers its intended outcomes, lessons are captured, and responsibility is transferred to operational teams. According to Kerzner (2017), project closure is as important as initiation as it validates success and informs future projects.

Monitoring and Evaluation

Key Performance Indicators (KPIs):

| KPI | Description | Target | Frequency | Responsible |
| --- | --- | --- | --- | --- |
| Operational Efficiency | Reduction in average patient check-in time | 40% | 3 months | Project Manager |
| Patient Satisfaction | Positive responses and scores related to quality of care | Increase by 20% | Within 6 months | Patient Experience Team or Quality Assurance Manager |
| System Reliability | Achieve uptime in kiosk functionality | >95% | During pilot phase | IT Department or System Administrator |
| Staff Utilisation | Reduction in routine reception desk check-in workload | 30% reduction | 3 months | HR Manager |
| Data Accuracy | Accuracy of data transferred from kiosks to NHS systems | 95% | During pilot phase | Data Analyst or IT Department |

The monitoring tools that can be used include monthly performance dashboards, user surveys (patients and staff), IT performance reports, regular stakeholder meetings to review progress against KPIs.

Project Close Down

Steps

- Final Deliverable Handover – Transfer kiosks, documentation, and operational procedures to NHS Trust IT teams.

- Lessons Learned Report – Document challenges (patient adoption, technical integration) and successes to inform future digital rollouts.

- Financial Closure – Reconcile project budget, report variances, and release unused contingency funds.

- Formal Closure Approval – Steering group sign-off confirming project objectives met.

- Transition to Operations – Establish ongoing support contracts with suppliers and internal helpdesk procedures.

By applying structured monitoring and formal closure, the project ensures accountability, captures learning for future NHS digital projects, and embeds sustainability into routine operations.

# 4. Key attributes of a Project Manager

The success of healthcare projects relies on the project manager's skills and behaviours, alongside structured processes. Turner and Müller (2005) note that effective managers blend interpersonal ability, technical knowledge, and strategic vision. These qualities are vital in the NHS due to complex systems, varied stakeholders, and regulatory requirements.

Core Attributes

- Leadership: Project managers must motivate teams and foster innovation during change. For instance, encouraging staff to see kiosks as supportive tools enhances acceptance.

- Communication: Clear communication with management, staff, suppliers, and patients minimises misunderstandings; this includes tailored reports and workshops.

- Stakeholder management: Engaging patients and staff early balances needs and eases adoption.

- Decision-making/problem-solving: Structured models help address challenges like outages or budget issues.

- Risk awareness: Proactively anticipating risks, using risk registers, and ensuring GDPR compliance are essential.

Project managers are responsible for leadership, stakeholder engagement, risk management, task coordination, and communication. These competencies ensure successful deployment and sustainability of NHS outpatient kiosk projects.

# 5. Self-Audit & Personal Development Plan

Self-awareness is a component of project management education. Kolb’s Experiential Learning Cycle (1984) suggests that reflective practice contributes to the development of professional competencies. By performing a self-audit with project manager attributes, individuals can identify strengths and areas for improvement, which create a Personal Development Plan (PDP).

## 5.1 Self Audit Skills Assessment

| Skills/Attribute | Current Strength | Self-Rating (1-5) | Evidence | Development Need |
| --- | --- | --- | --- | --- |
| Leadership | Ability to motivate small teams from previous retail role | 4 | Managed sales team effectively | Develop skills in large multi-disciplinary healthcare teams |
| Communication | Effective at adapting style for customers | 4 | Positive feedback from colleagues | Improve formal reporting for senior stakeholders |
| Stakeholder Management | Moderate | 3 | Experience liaising with suppliers and customers | Need to build skills in complex, multi-stakeholder NHS environment |
| Risk Management | Developing | 2 | Limited experience beyond retail context | Learn formal tools (risk registers) |
| Technical Project Tools | Moderate | 3 | Basis MS project/Gantt chart knowledge | Deepen use of Agile tools, dashboards and NHS digital systems |
| Decision-making | Strong | 4 | Good under pressure in fast paced environments | Apply structured models (SWOT, PESTLE) |
| Time Management | Strong | 4 | Consistently meet deadlines at work/university | Maintain but adapt to long-term projects |

## 5.2 Strengths & Weaknesses

Strengths

- Strong interpersonal communication and customer-facing skills.

- Experience motivating small teams.

- Confidence in making decisions under pressure.

Weaknesses

- Limited exposure to healthcare-specific project management.

- Lack of advanced technical project management tool experience.

- Developing stage in formal risk management approaches.

## 5.3 Personal Development Plan

| Objective | Action | Resources Required | Timescale | Success Measure |
| --- | --- | --- | --- | --- |
| Improve stakeholder management in healthcare projects | Shadow NHS project managers and attend stakeholder engagement workshops | NHS training opportunities, mentor support | 6–12 months | Confidently lead stakeholder meeting with multiple NHS groups |
| Enhance risk management skills | Complete PRINCE2 Risk Management module and practice with risk registers | Online course, case study exercises | 3–6 months | Develop a comprehensive risk register for a simulated NHS project |
| Strengthen technical project tool skills | Gain proficiency in MS Project and Kanban tools | Online tutorials, practice projects | 3–6 months | Create Gantt chart and Kanban board for academic project |
| Develop healthcare project awareness | Attend NHS Digital webinars, review case studies | Online NHS resources | 6 months | Reflective log of learning, improved application in assignments |
| Improve communication with senior stakeholders | Write executive summaries and present updates | University projects, workplace role-play | Ongoing | Receive positive feedback from supervisors on clarity of reporting |

The self-audit notes strong transferable skills in communication and leadership, but identifies gaps in project methodologies, risk management, and NHS stakeholder engagement. The PDP sets SMART actions to address these areas, aiding professional development as a healthcare project manager.

# 6. Conclusion

Within this report project management theories and processes has been applied to the concept of introducing self-service patient check-in kiosks within an NHS outpatient setting. Using recognised methodologies, the report has demonstrated how structured project management can guide a project from concept to completion while address challenges in healthcare environments.

The project addresses objectives of improving patient flow and reducing staff overload, while aligning with NHS efficiencies and digital transformation strategies. Initiation, environmental scanning, and structured planning methods such as Work Breakdown Structure, Gantt charts, and risk registers are used to address complexity in project management. Different methodologies contribute distinct functions: PRINCE2 focuses on governance and Agile tools like Kanban support adaptability. Key risks for the project included technical integration challenges, possible resistance from staff and patients, and concerns around data security. Mitigation strategies such as phased rollouts and adherence to GDPR guidelines are identified as important for successful project implementation.

Key attributes of a project manager were identified and included leadership, communication, stakeholder management. A self-assessment has shown strengths in leadership and communication, however highlighted opportunities for improvements in risk management, use of technical projects tools, and engaging with NHS stakeholders. A structured personal development plan (PDP) will be implemented to address these areas. Introducing self-service kiosks to the NHS is both a technical and cultural shift. Success relies on maintaining efficiency and inclusivity, so all patients benefit. Using effective project management, risk control, and leadership can drive meaningful improvements and set an example for future digital projects.

# References

Alazzawi, A., Yas, Q. M., & Rahmatullah, B. (2023). A comprehensive review of software development life cycle methodologies: Pros, cons, and future directions. Iraqi Journal for Computer Science and Mathematics, 4(4), 173–174. https://doi.org/10.52866/ijcsm.2023.04.04.04

Department of Health & Social Care & Prime Minister's Office. (2025, July 30). Fit for the future: 10 Year Health Plan for England - executive summary (accessible version). GOV.UK. https://www.gov.uk/government/publications/10-year-health-plan-for-england-fit-for-the-future/fit-for-the-future-10-year-health-plan-for-england-executive-summary#from-analogue-to-digital-power-in-your-hands

Digital Health News. (2021, January 26). UK NHS hospital trusts embrace self service check-in technology. https://www.digitalhealthnews.eu/industry/2456-uk-nhs-hospital-trusts-embrace-self-service-check-in-technology

Donato, H. (2025, March 7). What is project management? Definition, types & examples. Project-Management.com. . https://project-management.com/what-is-project-management/

GeeksforGeeks. (2025, July 23). What is Agile Project Management (APM)? https://www.geeksforgeeks.org/software-engineering/agile-project-management/#what-is-agile-project-management-apm

Good, L. (2025, May 9). What is agile project management? An ultimate guide for flexible & smarter teams. Project-Management.com. . https://project-management.com/agile-project-management/

Greenhalgh, T., Shaw, S. E., Alvarez Nishio, A., Booth, A., Byng, R., Clarke, A., Dakin, F., Davies, R., Faulkner, S., Hemmings, N., Husain, L., Kalin, A., Ladds, E., Moore, L., Rosen, R., Rybczynska-Bunt, S., Wherton, J., & Wieringa, S. (2022). Protocol: Remote care as the ‘new normal’? Multi-site case study in UK general practice. NIHR Open Research, 2, 46. https://pmc.ncbi.nlm.nih.gov/articles/PMC10593351

Health and Social Care Committee. (2023). Digital transformation in the NHS: Eighth report of session 2022–23. House of Commons. https://publications.parliament.uk/pa/cm5803/cms

ILX Marketing Team. (2024, May 30). The difference between a project and a programme. PRINCE2 UK. https://www.prince2.com/uk/blog/project-vs-programme

Institute of Project Management. (2022, May 20). What is Waterfall Methodology: Everything you need to know. https://instituteprojectmanagement.com/blog/waterfall-methodology/

Kerzner, H. (2017). Project management metrics, KPIs, and dashboards: A guide to measuring and monitoring project performance. John Wiley & Sons. https://doi.org/10.1002/9781119427599

Landau, P. (2023, May 16). What is a risk register & how to create one. ProjectManager. https://www.projectmanager.com/blog/guide-using-risk-register#:~:text=A%20%EE%80%80risk%EE%80%8

Landau, P. (2024, September 9). 22 project management tools & techniques for project managers. ProjectManager. https://www.projectmanager.com/blog/project-management-techniques-for-every-pm

LaPrad, L. (2025, June 3). Gantt chart 101: What it is & how to build one that works. TeamGantt. https://www.teamgantt.com/what-is-a-gantt-chart

MacNeil, C. (2025, February 7). Project initiation: The first step to successful project management. Asana. https://asana.com/resources/project-initiation

Matthews, B. (2024, April 19). RACI matrix: Responsibility assignment matrix guide. Project-Management.com. https://project-management.com/understanding-responsibility-assignment-matrix-raci-matrix/

Mitchell, G. (2025, August 2). 7 PRINCE2 project stages – All you need to know. The Knowledge Academy. https://www.theknowledgeacademy.com/blog/prince2-project-stages/

NHS England. (2024, December 17). Statistics on Public Health, England 2023. NHS England Digital. https://digital.nhs.uk/data-and-information/publications/statistical/statistics-on-public-health/2023

NHS England. (2024, December 4). Principles for assessing and managing risks across integrated care systems. https://www.england.nhs.uk/long-read/principles-for-assessing-and-managing-risks-across-integrated-care-systems/

NHS England. (2025, April 22). University Hospitals of Leicester NHS Trust - Digital Patient Wayfinding. NHS England Digital. https://digital.nhs.uk/services/networks-and-connectivity-transformation-frontline-capabilities/connectivity-hub/wireless-trials/connectivity-hub-wireless-trialist-case-studies/university-hospitals-of-leicester-nhs-trust

Raeburn, A. (2025, February 7). The work breakdown structure (WBS) for project management: What it is and how to use it. Asana. https://asana.com/resources/work-breakdown-structure

Rehkopf, M. (2025). What is a Kanban board? Atlassian. https://www.atlassian.com/agile/kanban/boards

Savience Ltd. (2023, November 13). Benefits of hospital self-check-in kiosks. https://savience.com/2023/11/13/benefits-of-hospital-self-check-in-kiosks/

Sehgal, H. L. K., Greenfield, G., Neves, A. L., Harmon, M., Majeed, A., & Hayhoe, B. (2024). Efficacy and safety of a digital check-in and triage kiosk in emergency departments: A systematic review protocol. BMJ Open, 14(7), e084506. https://doi.org/10.1136/bmjopen-2024-084506

Storey, F. (2024, July 10). Top 5 reasons healthcare providers should embrace self-service kiosks. imageHOLDERS. https://www.imageholders.com/insights/top-5-reasons-healthcare-providers-should-embrace-self-service-kiosks/

Turner, J. R., & Müller, R. (2005). The project manager’s leadership style as a success factor on projects: A literature review. Project Management Journal, 36(1), 49–61. https://www.researchgate.net/publication/258568476_The_Project_Manager's_Leadership_Style_as_a_Success_Factor_on_Projects_A_Literature_Review

West Suffolk NHS Foundation Trust. (2024, January 23). New check-in kiosks for hospital outpatient appointments. https://www.wsh.nhs.uk/News-room/news-posts/New-check-in-kiosks-for-hospital-outpatient-appointments.aspx

# Appendix A

Gantt Chart

| TASK NAME | START DATE | DAY OF MONTH* | END DATE | DURATION* (WORK DAYS) | DAYS COMPLETE | DAYS REMAINING* | TEAM MEMBER | PERCENT COMPLETE |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Initiation |  |  |  |  |  |  |  |  |  |
| Create project charter | 9/1 | 1 | 9/22 | 22 | 22 | 0 | PM | 100% |  |
| Business case | 9/8 | 8 | 9/15 | 8 | 6.4 | 1.6 | PM | 80% |  |
| Stakeholder Mapping |  |  |  |  |  |  |  |  |  |
| Identify Stakeholders | 9/8 | 8 | 9/22 | 15 | 15 | 0 | PM | 100% |  |
| Governance | 9/15 | 15 | 9/29 | 15 | 12 | 3 | PM | 80% |  |
| Procurement of Kiosk Hardware |  |  |  |  |  |  |  |  |  |
| Risk Register | 9/29 | 29 | 10/20 | 22 | 22 | 0 | PM | 100% |  |
| Communication Plan | 9/29 | 29 | 10/13 | 15 | 12 | 3 | PM | 80% |  |
| GDPR Compliance | 10/6 | 6 | 10/27 | 22 | 17.6 | 4.4 | PM | 80% |  |
| Security Review | 10/13 | 13 | 11/3 | 22 | 17.6 | 4.4 | PM | 80% |  |
| Technical Integration with NHS | 10/13 | 13 | 11/24 | 43 | 34.4 | 8.6 | PM | 80% |  |
| Staff Engagement & Training | 10/27 | 27 | 11/17 | 22 | 13.2 | 9 | PM | 60% |  |
| Pilot Kiosk Installation |  |  |  |  |  |  |  |  |  |
| Pilot Site 1 | 12/1 | 1 | 12/22 | 22 | 22 | 0 | PM | 100% |  |
| Pilot Evaluation & Feedback | 12/22 | 22 | 1/5 | 15 | 12 | 3 | PM | 80% |  |
| Wider Rollout Across Sites | 1/4 | 4 | 2/15 | 43 | 25.8 | 17.2 | PM | 60% |  |
| Project Close Down & Review | 2/15 | 15 | 3/2 | 16 | 0 | 16 | PM | 0% |  |

# Appendix B

RACI Matrix

| Risk | Likelihood (1–5) | Impact (1–5) | Risk Rating | Mitigation Strategy | Risk Owner |
| --- | --- | --- | --- | --- | --- |
| Technical integration failure | 3 (Medium) | 5 (High) | 🔴 Critical | Early system testing, phased rollout and vendor accountability clauses in contract | IT Project Lead |
| Staff resistance | 5 (High) | 3 (Medium) | 🔴 Critical | Staff engagement workshops, clear communication about role security | HR / Department Manager |
| Patient resistance | 3 (Medium) | 3 (Medium) | 🟠 Medium | Maintain staffed desks, provide kiosk helpers and ensure intuitive design | Patient Experience Lead |
| Budget overrun | 3 (Medium) | 3 (Medium) | 🟠 Medium | Include 10–15% contingency, regular budget reviews and strict supplier contract management | Finance Officer |
| Supplier delays | 3 (Medium) | 3 (Medium) | 🟠 Medium | Use reliable suppliers, insert penalty clauses and hold buffer stock | Procurement Manager |
| Cybersecurity breach | 2 (Low) | 5 (High) | 🟠 Medium (monitor closely) | Penetration testing, GDPR compliance checks and NHS Digital audits | Information Governance |
| Minor kiosk faults | 2 (Low) | 1 (Low) | 🟢 Low | Maintenance contracts, regular servicing and spare parts available | Facilities / IT Support |

# Appendix C

Kanban Board

| Backlog (To Be Planned) | To Do (Planned) | In Progress | Review/Testing | Done |
| --- | --- | --- | --- | --- |
| Define project scope | Draft communication plan | Staff engagement workshops | Pilot testing of kiosks in one clinic | Business case approval |
| *Secure funding | Procurement of kiosk hardware | Technical integration with NHS systems | Cybersecurity testing | Supplier selection |
| Identify stakeholders | Staff training plan | Budget monitoring | Patient feedback collection (surveys) | Risk register creation |
| Draft risk register | Data protection compliance review (GDPR) | Installation of first kiosks | Post-installation performance review | Project initiation documents |
| Establish project governance structure | Create contingency budget plan | Change management initiatives | Management sign-off for wider rollout | Stakeholder mapping completed |

# Appendix D

Risk Register

| Risk | Severity | Likelihood | Risk Rating | Mitigation Strategy |
| --- | --- | --- | --- | --- |
| Technical integration failure (kiosks incompatible with NHS patient management systems) | High | Medium | High | Conduct early compatibility testing, involve IT department in supplier selection. |
| Staff resistance (perceived threat to roles) | Medium | High | High | Provide staff training, emphasise kiosks as support not replacement and involve staff in planning. |
| Patient resistance (low digital literacy, preference for face-to-face check-in) | Medium | Medium | Medium | Offer staffed desks alongside kiosks, design user-friendly interface and provide volunteer support. |
| Data security breach (GDPR violation) | High | Low | High | Implement NHS-compliant encryption, restrict access to authorised users and conduct penetration testing. |
| Budget overrun (unexpected costs in procurement/installation) | Medium | Medium | Medium | Include 20% contingency in budget, phased rollout to manage financial risk. |
| Supplier delays (hardware delivery issues) | Medium | Medium | Medium | Establish clear service-level agreements (SLAs) and consider multiple suppliers. |

# Appendix E

Cost Benefit Analysis

Project Costs (Over 3-Year Horizon)

| Category | Detail | Estimated Cost (£) |
| --- | --- | --- |
| Hardware procurement | 10 kiosks @ £4,000 each | £40,000 |
| Software licensing | Integration + maintenance (£1,500 per kiosk/year) | £45,000 |
| Implementation costs | Installation, testing, project management | £20,000 |
| Training & change management | Staff training sessions, user manuals | £10,000 |
| Cybersecurity compliance | GDPR/data protection audits, encryption measures | £15,000 |
| Contingency (10%) | Buffer for unexpected costs | £13,000 |
| Total Project Cost |  | £143,000 |

Project Benefits (Annual, Estimated)

| Category | Detail | Annual Benefit (£) |
| --- | --- | --- |
| Reduced admin staffing costs | Reception/admin time saved (2 FTE @ £25k) | £50,000 |
| Faster patient check-in | Average wait time reduced → higher throughput | £20,000 (productivity) |
| Error reduction | Fewer manual entry mistakes, saving rectification costs | £10,000 |
| Improved patient satisfaction | Better experience → NHS Friends & Family Test improvement (hard to monetise, proxy £15k) | £15,000 |
| Scalability & reuse | System reusable in other clinics/hospitals | £10,000 |
| Total Annual Benefit |  | £105,000 |

# Appendix F

PESTLE Analysis

| Factor | Impact on Project |
| --- | --- |
| Political | NHS’s digital transformation agenda strongly supports automation in healthcare services. However, changes in government or funding priorities could impact long-term adoption. |
| Economic | Budget constraints across NHS Trusts require strong cost–benefit justification. Inflation and supply chain issues could increase kiosk costs. |
| Social | An ageing population increases outpatient demand but also raises concerns about digital literacy and accessibility for older patients. |
| Technological | Advances in touchscreen technology and NHS data integration tools support project feasibility. Cybersecurity threats require robust mitigation strategies. |
| Legal | Strict compliance with GDPR and NHS data protection policies is essential. Failure to meet legal requirements could result in reputational and financial penalties. |
| Environmental | NHS sustainability goals require kiosks to be energy-efficient and have minimal environmental impact. |

SWOT Analysis

| SWOT Analysis |  |
| --- | --- |
| STRENGTHS Aligns with NHS priorities for digital innovation. Proven technology with successful case studies in other trusts. Potential to improve patient satisfaction and reduce delays. | WEAKNESSES Requires initial investment during a period of pressures in budget. Staff may lack confidence in supporting patients with new technology. Risk of technical integration issues with existing NHS systems. |
| OPPORTUNITIES Expansion to additional clinics or services. Potential for integration with mobile apps for remote check-in. Contribution to NHS carbon reduction targets by reducing paper usage. | THREATS Staff or patient resistance to change. Cybersecurity risks, including data breaches. Vendor insolvency or supply chain delays. |

# Appendix G

Work Breakdown Structure Diagram

Project Implementation

Digital Patient Self-Check-In-Kiosk System

Procurement

Installation

Training

Testing

Go-Live

Review

Planning

Develop staff training modules

Conduct in-person training sessions for reception teams

Create patient facing instruction materials and signage

Deploy kiosks to remaining pilot sites

Monitor system performance and patient usage rates

Conduct post-implementation review

Document lessons learned

Prepare scale-up recommendation report

Launch first pilot clinic

Gather feedback from patients and staff

Refine software interface and workflows

Deliver kiosks to pilot sites

Install hardware in out-patient clinics

Integrate kiosk software with NHS patient management systems

Test connectivity and performance

Tender process with suppliers

Evaluate proposals and select vendor

Finalise contracts and service-level agreements

Conduct stakeholder analysis

Finalise requirements specification

Develop procurement plan

Secure budget approval

# Bibliography

Alazzawi, A., Yas, Q. M., & Rahmatullah, B. (2023). A comprehensive review of software development life cycle methodologies: Pros, cons, and future directions. Iraqi Journal for Computer Science and Mathematics, 4(4), 173–174. https://doi.org/10.52866/ijcsm.2023.04.04.04

Department of Health & Social Care & Prime Minister's Office. (2025, July 30). Fit for the future: 10 Year Health Plan for England - executive summary (accessible version). GOV.UK. https://www.gov.uk/government/publications/10-year-health-plan-for-england-fit-for-the-future/fit-for-the-future-10-year-health-plan-for-england-executive-summary#from-analogue-to-digital-power-in-your-hands

Digital Health News. (2011, January 26). UK NHS hospital trusts embrace self service check-in technology. https://www.digitalhealthnews.eu/industry/2456-uk-nhs-hospital-trusts-embrace-self-service-check-in-technology

Digital Health News. (2021, January 26). UK NHS hospital trusts embrace self service check-in technology. https://www.digitalhealthnews.eu/industry/2456-uk-nhs-hospital-trusts-embrace-self-service-check-in-technology

DNV Imatis AS. (2024). Check-in and queue management system: G-Cloud 14 pricing document (Version 1.0). https://assets.applytosupply.digitalmarketplace.service.gov.uk/g-cloud-14/documents/720352/998132191513695-pricing-document-2024-05-07-1108.pdf

Donato, H. (2025, March 7). What is project management? Definition, types & examples. Project-Management.com. . https://project-management.com/what-is-project-management/

GeeksforGeeks. (2025, July 23). What is Agile Project Management (APM)? https://www.geeksforgeeks.org/software-engineering/agile-project-management/#what-is-agile-project-management-apm

Good, L. (2025, May 9). What is agile project management? An ultimate guide for flexible & smarter teams. Project-Management.com. . https://project-management.com/agile-project-management/

Greenhalgh, T., Shaw, S. E., Alvarez Nishio, A., Booth, A., Byng, R., Clarke, A., Dakin, F., Davies, R., Faulkner, S., Hemmings, N., Husain, L., Kalin, A., Ladds, E., Moore, L., Rosen, R., Rybczynska-Bunt, S., Wherton, J., & Wieringa, S. (2022). Protocol: Remote care as the ‘new normal’? Multi-site case study in UK general practice. NIHR Open Research, 2, 46. https://pmc.ncbi.nlm.nih.gov/articles/PMC10593351

Health and Social Care Committee. (2023). Digital transformation in the NHS: Eighth report of session 2022–23. House of Commons. https://publications.parliament.uk/pa/cm5803/cms

ILX Marketing Team. (2024, May 30). The difference between a project and a programme. PRINCE2 UK. https://www.prince2.com/uk/blog/project-vs-programme

Institute of Project Management. (2022, May 20). What is Waterfall Methodology: Everything you need to know. https://instituteprojectmanagement.com/blog/waterfall-methodology/

Kerzner, H. (2017). Project management metrics, KPIs, and dashboards: A guide to measuring and monitoring project performance. John Wiley & Sons. https://doi.org/10.1002/9781119427599

Landau, P. (2023, May 16). What is a risk register & how to create one. ProjectManager. https://www.projectmanager.com/blog/guide-using-risk-register#:~:text=A%20%EE%80%80risk%EE%80%8

Landau, P. (2024, September 9). 22 project management tools & techniques for project managers. ProjectManager. https://www.projectmanager.com/blog/project-management-techniques-for-every-pm

LaPrad, L. (2025, June 3). Gantt chart 101: What it is & how to build one that works. TeamGantt. https://www.teamgantt.com/what-is-a-gantt-chart

Lewis, A., West, J., Lewis, C., & Murfett, D. (2017, May 9). Patient self service check in kiosks reduce waiting times. HSJ Solutions. https://solutions.hsj.co.uk/patient-self-service-check-in-kiosks-reduce-waiting-times/7014811.article

MacNeil, C. (2025, February 7). Project initiation: The first step to successful project management. Asana. https://asana.com/resources/project-initiation

Matthews, B. (2024, April 19). RACI matrix: Responsibility assignment matrix guide. Project-Management.com. https://project-management.com/understanding-responsibility-assignment-matrix-raci-matrix/

Mendip Vale Medical Group. (n.d.). Self-health kiosk. https://mendipvale.nhs.uk/services/self-health-kiosk#:~:text=The%20Health%20Kiosks%20allow%20patients%20to%20answer%20health,patient%20record%2C%20ready%20for%20a%20clinician%20to%20review

Mitchell, G. (2025, August 2). 7 PRINCE2 project stages – All you need to know. The Knowledge Academy. https://www.theknowledgeacademy.com/blog/prince2-project-stages/

Mosher, Z. A., Hudson, P. W., Lee, S. R., Perez, J. L., Arguello, A. M., McGwin, G., Theiss, S. M., & Ponce, B. A. (2020). Check-in kiosks in the outpatient clinical setting: Fad or the future? Southern Medical Journal, 113(3), 134–139. https://doi.org/10.14423/SMJ.0000000000001078

NHS England. (2023, December 5). Urgent care self-service product. NHS England Digital. https://digital.nhs.uk/services/urgent-care-self-service-product

NHS England. (2024, December 17). Statistics on Public Health, England 2023. NHS England Digital. https://digital.nhs.uk/data-and-information/publications/statistical/statistics-on-public-health/2023

NHS England. (2024, December 4). Principles for assessing and managing risks across integrated care systems. https://www.england.nhs.uk/long-read/principles-for-assessing-and-managing-risks-across-integrated-care-systems/

NHS England. (2025, April 22). University Hospitals of Leicester NHS Trust - Digital Patient Wayfinding. NHS England Digital. https://digital.nhs.uk/services/networks-and-connectivity-transformation-frontline-capabilities/connectivity-hub/wireless-trials/connectivity-hub-wireless-trialist-case-studies/university-hospitals-of-leicester-nhs-trust

Raeburn, A. (2025, February 7). The work breakdown structure (WBS) for project management: What it is and how to use it. Asana. https://asana.com/resources/work-breakdown-structure

Rehkopf, M. (2025). What is a Kanban board? Atlassian. https://www.atlassian.com/agile/kanban/boards

Savience Ltd. (2023, November 13). Benefits of hospital self-check-in kiosks. https://savience.com/2023/11/13/benefits-of-hospital-self-check-in-kiosks/

Sehgal, H. L. K., Greenfield, G., Neves, A. L., Harmon, M., Majeed, A., & Hayhoe, B. (2024). Efficacy and safety of a digital check-in and triage kiosk in emergency departments: A systematic review protocol. BMJ Open, 14(7), e084506. https://doi.org/10.1136/bmjopen-2024-084506

Storey, F. (2024, July 10). Top 5 reasons healthcare providers should embrace self-service kiosks. imageHOLDERS. https://www.imageholders.com/insights/top-5-reasons-healthcare-providers-should-embrace-self-service-kiosks/

Turner, J. R., & Müller, R. (2005). The project manager’s leadership style as a success factor on projects: A literature review. Project Management Journal, 36(1), 49–61. https://www.researchgate.net/publication/258568476_The_Project_Manager's_Leadership_Style_as_a_Success_Factor_on_Projects_A_Literature_Review

University Hospitals Birmingham NHS Foundation Trust. (2025, January 9). At the hospital (outpatients). https://www.uhb.nhs.uk/patients/outpatients/at-the-hospital/

West Suffolk NHS Foundation Trust. (2024, January 23). New check-in kiosks for hospital outpatient appointments. https://www.wsh.nhs.uk/News-room/news-posts/New-check-in-kiosks-for-hospital-outpatient-appointments.aspx

West Suffolk NHS Foundation Trust. (2024, January 23). New check-in kiosks for hospital outpatient appointments. https://www.wsh.nhs.uk/News-room/news-posts/New-check-in-kiosks-for-hospital-outpatient-appointments.aspx

MindByte Communications. (2011, January 27). UK NHS hospital trusts embrace self service check-in technology. https://www.mindbyte.eu

Malsam, W. (2025, February 28). What is PRINCE2? Principles, aspects, roles & processes. ProjectManager. https://www.projectmanager.com/blog/prince2-methodology