## Sheet1
Scheme of work Independent Project BMCP6006 24/25
Week commencing | Content | Comments
INDUCTION WEEK | INTRODUCTION TO INDEPENDENT PROJECT - Don't miss the bus
30th September 24 | Group discussion on Proposal and Ethics
7th October 24 | Supervision | NEED TO BOOK TIMESLOT
Friday 11th October | Submit amended proposal and Ethics forms
14th October 24 | Group discussion on Introduction
21st October 24 | Supervision - Feedback on proposal and ethics forms | NEED TO BOOK TIMESLOT
Friday 25th October | Submit Introduction chapter
28th October 24 | Individual feedback on Introduction chapter | NEED TO BOOK TIMESLOT
4th November 24 | Group discussion: Literature review
11th November 24 | PROGRESS WEEK - Schedule meetings with those students who you are concerned may be falling behind
18th November 24 | Supervision | NEED TO BOOK TIMESLOT
25th November 24 | Supervision | NEED TO BOOK TIMESLOT
Friday 29th November | Submit Literature review
2nd December 24 | Feedback on literature reviews | NEED TO BOOK TIMESLOT
9th December | Group discussion: Methodology
CHRISTMAS VACATION
27th January 25 | Supervision | NEED TO BOOK TIMESLOT
Friday 31st January 2025 | Submit methodology chapter
3rd February 25 | Approval of questionnaires/interview questions | NEED TO BOOK TIMESLOT
10th February 25 | Individual feedback on Methods chapter | NEED TO BOOK TIMESLOT
17th February 25 | Supervision | NEED TO BOOK TIMESLOT
24th February 25 | Group discussion: Analysis
3rd March 25 | Supervision | NEED TO BOOK TIMESLOT
10th March 25 | PROGRESS WEEK - Schedule meetings with those students who you are concerned may be falling behind
Friday 14th March | Submit Analysis chapter
17th March 25 | Group discussion Conclusion
24th March 25 | Individual feedback analysis | NEED TO BOOK TIMESLOT
Friday 28th March | Submit Conclusion chapter
31st March 25 | Individual feedback on conclusion | NEED TO BOOK TIMESLOT
EASTER VACATION (7th April-25th April)
28th April 25 | Supervision to check formatting | NEED TO BOOK TIMESLOT
Tuesday 6th May 2025 | FINAL SUBMISSION BY 23:59