## Data Entry
FAILURE MODE AND EFFECTS ANALYSIS
Item: | The General Delivery Process Of A Vibration Trial at ETC |  |  |  | Responsibility: |  | To Identify & Prioritise The Risks During Testing That Have |  |  |  | FMEA number: | 1
Model: | From Issue Of Trial Instruction To Production of Data Plots |  |  |  | Prepared by: Ralph Whittaker |  | The Biggest Impact On The Ability To Provide Test Data Plots & Satisfactory Customer Service. |  |  |  | Page : | 1
Core Team: | Dynamic Trials Delivery Team | [9 empty] | FMEA Date (Orig): | 2018-01-15 | Rev: |  | N/A
Process Function | Potential Failure Mode | Potential Effect(s) of Failure | Sev | Class | Potential Cause(s)/ Mechanism(s) of Failure | Occur | Current Process Controls | Detec | RPN | Recommended Action(s) | Responsibility and Target Completion Date | Action Results
[12 empty] | Actions Taken | Sev | Occ | Det | RPN
Gather Trial Instruction (TI) | TI Not ready. | Delay start of Trial set up | 3 | D | Customer requirements not clear / uncertain. Planning not running to schedule. | 3 | Planning schedule. Liaison with customer. | 9 | 81 | Improve planning department scheduling. Request TI well in advance. Train more of the planning office to write TI's . | Planning Department Manager - Immediately |  |  |  |  | 0
Read & Interpret TI | TI incorrectly worked from, confusion and doubt. | TI has to be re-written with correct info, delays start of trial set up | 7 | D | Human typing error. TI incorrectly written. Missing / incorrect test information (Specification g levels / durations / temperatures) from customer. | 2 | None, training of planning staff. | 8 | 112 | Improve competency and capability of Planning Department to write TI's correctly and on time. Request clarity on specifics of customer requirements in advance. | Planning Department Manager - Training to commence as soon as possible |  |  |  |  | 0
Gather instrumentation | Instrumentation not available | Delays set up of trial and running closed loops, accelerometer check outs | 8 | D | Tech services not calibrated enough, PRT's or accelerometers. Equipment not return from previous trials | 8 | None (No management). Sign in / out log book of equipment. | 2 | 128 | Enrol a manager to oversee the department and ensure equipment is being calibrated on time. Request ALL instrumentation is return to storage on completion of every trial. Ensure everyone uses the log book so equipment can be located on site. | Tech Services Manager - Immediately |  |  |  |  | 0
Raise Trial Daily Log Book | Log book not filled in, slow start to trial and no record of what's going on/ what's being used. | Cant fill out some specifics like calibration / maintenance due dates as awareness of equipment to be used is unknown. Customer info not available. Log book not completed. | 4 | D | Equipment or facilities unknown or unavailable. Requested data to be recorded unknown/ unsure due to customer requirements unknown / unavailable | 3 | As much filled out as possible as knowledge becomes available. | 5 | 60 | Plan much more in advance. Better scheduling and availability of test equipment and facilities. | Technician / Resource Manager - ASAP |  |  |  |  | 0
Write Test Specification on Controller | Test Spec not known / provided incorrectly from customer. Staff not Certified Technically Competent (CTC) | Delay writing control programme on controller. Delay start of Trial. | 7 | D | Customer provided incorrect data. Staff not pushing themselves to gain CTC or not time or opportunity to be trained. | 2 | Secondary software programmes (VibKit) used for double checking spec / controller output is correct. CTC training folded kept up to date and reviewed during Personal Development Plan meetings. | 7 | 98 | Continue to use VibKit to double check acceleration (test) spec levels. Introduce more opportunities / encourage staff to gain CTC's in controller software. | Project Engineer, Trial Technician, Trial Engineer - ASAP |  |  |  |  | 0
Specs peer checked by independent certified competent engineer | No one immediately available to check specs are correctly written | Delay in starting / running trial. | 5 | D | Not enough people CTC'd / absence due to holidays / sickness | 1 | Increasing the number of CTC'd engineers on site. | 3 | 15 | Continue to train / get signed off more engineers that can check over specs. Ensure not too many engineers are off on holiday at once. | Team Leader - ASAP |  |  |  |  | 0
Safety Brief provided to staff working on trial, acknowledge, understood & signed | Project Engineer not available, Safety Brief NOT given, not all staff briefed in time. | Delay in receiving Safety Brief. Can't start work on test items. Repetition of Safety Brief to previously absent staff. Potential trial time wasted. Not all staff can work on the trial, and are not utilised. Working on a trial without Safety Brief catastrophic events can occur, injury or even death. | 5 | A | No one immediately available to give safety brief. PE off work. Not ALL staff available at once. | 1 | Safety Brief can be given by another qualified person on site. Arrange Safety Brief when all potential trial workers are available. | 3 | 15 | Brief everyone on the Dynamics Trail Delivery team on every trial running so that anyone can work on any trail at any time if necessary. | Trials Safety Manager, Project Manager - Immediately |  |  |  |  | 0
Trial set up (staging / rig / shaker) | Trial set up not completed in time or to / correct layout / high enough standard. | Delay in starting trial. Non functional set up. Damage to equipment or injury to workers. Increase project costs due to work time wasted, over spend on project budget. | 8 | B | Competent personnel off work. No previous knowledge / experience of set up. No Photos of previous set up for similar trial. | 2 | One person involved / leads in all set ups / some photographs taken for records of common set ups | 1 | 16 | To train (more) personnel on set up / extend knowledge to others / have a dedicated trials set up team. Keep detailed step by step photographs of ALL set ups for records to refer to for future trials. Plan holidays / back up staff trained to cover potential bouts of sickness | Set Up team, Dynamics Team Leader - ASAP |  |  |  |  | 0
Instrumentation check-out | Instrumentation check out failure | Delay in starting trial. Data not gathered. Controller can't function. Increase project costs due to work time wasted. | 6 | D | Broken accelerometers. Broken / loose leads. Noise on signal channels. Shaker damaged. Rig plate not suitable / broken. | 2 | Instrumentation calibration / check. Routine shaker maintenance. | 9 | 108 | Check instrumentation in advance of trial / after trial in between calibration testing. Perform shaker check-out after EVERY trial. | Trial Technician, Trail Engineer - When required |  |  |  |  | 0
Load inert item onto rig | Item doesn’t fit rig. (Too big / small / heavy / hole pitches out of line) | Up to a week delay in loading inert item for starting precursor testing. Increase project costs due to material / labour time wasted, over spend on project budget. | 8 | D | Rig not correctly designed with test item in mind / full accurate test item dimensions. | 4 | Sometimes customer's own rig is used. Rig is designed & made according to paper plan / provided written dimensions of test item. | 7 | 224 | Use customer designed rig where possible. Physically check test item / measure / photograph before designing on CAD & producing rig in workshops. | Rig Designer, Workshops - ASAP / when required |  |  |  |  | 0
Instrument, Condition & Test inert item (Precursors) | Conditioning failure. Precursor test failure. Control response of controller fails to control test as per spec | Delays start time of live store trials. Precursor data not produced. Increase project costs due to power / energy and a lot time (12-16 hours) wasted | 6 | D | Accelerometer positioning, fixings coming loose. Set up of rig not suitable. Broken rig or item. Mobile Conditioning Unit (MCU) failure / leak in chamber / power cut. | 3 | Good practice / method / experience for fixing instrumentation. Low level testing completed before full level 0dB performed. Routine maintenance of MCU. Ensure test abort / alarm levels are set to trip the controller if control is outside certain tolerances. | 2 | 36 | Double check fixings, ensure correct amount of glue / torque is always used when fixing accelerometers / tightening bolts. Train technicians on how to measure up bolts so only correct bolt lengths used (so bolts don't bottom out etc). Only have MCU turned on when in use to prevent wasting cooling gas / wear and tear of parts. | Trial Technician, Trail Engineer , Maintenance Team used for MCU maintenance - When required |  |  |  |  | 0
Test inert item according to Customer Spec | Item under or over tested | Damage to item, incorrectly certified as passed testing. Huge negative impact on project costs if damage occurs. Very unhappy customer. | 9 | B | Human typed / calculated error. Wrong Spec sent or input into controller | 1 | Sometimes spec levels are double checked using secondary software | 7 | 63 | Check EVERY customer Spec EVERY TIME, as soon as reasonably possible using secondary calculative software (VibKit). Discuss Spec more in depth with customer. Advanced controller training for Technicians / Engineers | Potentially Customer that sent original Spec, Person in planning that wrote the TI, Trial Engineer - Immediately |  |  |  |  | 0
Load, Instrument, Condition & Test Live item | Conditioning failure / air inside not reaching target temperature. Control response of controller fails to control test as per spec | Increases time taken to complete test as per customer requirement. Trial over runs deadline. Over spend on project budget. | 7 | D | MCU failure / leak in chamber / power cut. Live store with explosive content acts differently at temperature due to difference in make up of internal mass material. | 3 | Precursor with representative mass used for pre-run of trial. MCU routinely checked and chambers checked / repaired. Notification Text message service to personnel on call off site of MCU failure during out of hours | 2 | 42 | Try to represent the live run as near as possible during the precursor runs before moving on to the live testing. Allocate people for on-call service during out of hours. | Trial Technician, Trail Engineer , Maintenance Team used for MCU maintenance - When required |  |  |  |  | 0
Plot Test data results ready for presentation to customer | Data not plotted / incorrect data plotted for customer. | Delay in providing plots. Final Report Delayed. Unsatisfied customer. Poor company reputation. Project cost increase due to re-testing required. Frustrated customer. | 10 | D | Test not achievable / not fully completed / equipment failure / accelerometers fixed in the wrong direction o test item. Data not gathered / insufficient / inaccurate / incorrect data recorded. | 1 | Peer checking of set up of instrumentation / Test Specs. Staff training. Repeat Testing. | 1 | 10 | Increase level and detail of staff training. Quickly repeat testing as soon as possible to collect correct / accurate data. | Trial Technician, Trial Engineer, Maintenance team - ASAP |  |  |  |  | 0

## About This Template
This template was written for the American Society for Quality by
Stat Aids
Your feedback is welcome and encouraged. Please e-mail to:
Stat_Aids@yahoo.com