## Slide 1: Title: Year of Legends – International Cultural Tourism Summit 2025
Subtitle: Feasibility Plan and Strategic Event Overview Presenter: Sabbir Hussain, Event Planner
Module code: BMIH6007
Student name: Sabbir Ansar Hussain
Student ID number: 2233891
AI Acknowledgement
I confirm that I have not used any AI tools in the research and creation of this assignment. I confirm that I have not presented any AI generated materials as my own work. I confirm I have copies of my drafts, notes, and other resources I used, which I may be asked to provide in evidence.

## Slide 2: Agenda
Introduction & Event Overview
Venue Selection & Destination
Stakeholder Analysis
Event Program & Experience
Sustainability Measures
Risk & Crisis Management
Operational Plan & Budget
Event Evaluation
Conclusion & Questions
Notes: This slide covers the structure of presentation. We will address the objectives of the event, the choice of the place, the role of the stakeholders, and the highlights of the event. There will also be sustainability endeavors, risk mitigation endeavors, as well as the operations logistics of the event. We will conclude by examining the way in which the success will be measured and then conclude by summarizing the feasibility of the event.

## Slide 3: Introduction & Event Overview
Event Name: Year of Legends
Theme & Purpose: Showcase Welsh culture & heritage to boost tourism
Event Type: International Conference & Expo (Keynotes, workshops, cultural showcases, B2B networking)
Location & Dates: ICC Wales, Newport – Summer 2025 (3 days)
Scale: ~300 international delegates
Notes: The Year of Legends will present Wales Tourism Week is an industry led opportunity to raise awareness of the issues impacting the tourism industry in Wales, but it is also a time to showcase the quality of Welsh tourism (Business Wales, 2025). This is a hybrid international cultural tourism conference and expo. The event is to be held at ICC Wales, Newport, which provides one of the best places with good facilities that can accommodate the anticipated 300 delegates (ICC Wales, 2025). The summit will give the tourism professionals and media an opportunity to experience Wales first hand, which will increase global tourism to Wales.

## Slide 4: Event Objectives (SMART)
Objective 1: Attract 300 international delegates from 15+ countries
Objective 2: Generate £500,000+ in tourism spending and at least 50 new B2B partnerships
Objective 3: Achieve an 80%+ satisfaction rate among attendees
Notes: We have identified specific, measures, achievable, relevant as well as time-based (SMART) goals of the summit. The initial target is to hire 300 international delegates and this will guarantee the international coverage of the event. The second is aimed at economic influence by the spending of delegates and B2B opportunities. Finally, we will target a satisfaction of 80%+ of the delegates through post-event surveys, so that the summit achieves the purposes of education and networking.

## Slide 5: Venue Selection & Destination
Destination: Wales, UK – rich cultural heritage & government support via Visit Wales
Venue: ICC Wales, Newport – modern venue with 4,000+ capacity
Accessibility: 30 min from Cardiff Airport, easy transport links
Venue Suitability: Modern A/V, flexible space, sustainability certified
Notes: Wales is a great place to visit and it is a historic place with a combination of natural beauty and a friendly tourism structure (Galagar et al., 2025). The ideal place to host this summit is ICC Wales at Newport that has state-of-the-art facilities, versatile spaces, and good accessibility via the Cardiff Airport. It is also sustainable, as it is an ISO 20121 certified event management company. Moreover, modern facilities of the venue, such as outstanding A/V facilities and versatile facilities, will make sure that all sessions and activities will go on smoothly (Borrego-Baslalobre et al., 2025). Its close location to Cardiff and major transport links also make it further convenient to international delegates who would have attended the summit

## Slide 6: Stakeholder Analysis
Primary Stakeholders
Delegates: Tour operators, travel agents, media
Secondary Stakeholders
Exhibitors/Speakers: Welsh tourism businesses, cultural performers
Venue & Suppliers: ICC Wales, catering, AV providers
Sponsors/Partners: Airlines, hotel chains, tourism boards
Local Community: Residents, local businesses
Government: Local council, police, health authorities
Volunteers: Student ambassadors for event support
Notes: Management of the stakeholders is paramount towards the success of the event. The main stakeholders are the delegates, exhibitors, staff of the venue and sponsors (Chullen et al., 2025). These teams directly participate in the provision of the experience of the event and its success. The local community and the government of the area are secondary stakeholders, as they would assist in logistics and compliance. The use of volunteers in the local universities will make the work easy and create a feeling that the community is a part and parcel of it.

## Slide 7: Event Program & Experience
Day 1: Opening ceremony, keynote speeches, Welsh legends-themed welcome reception
Day 2: Workshops, exhibitions, site visits to Cardiff Castle and St Fagans
Day 3: Strategic forums, networking sessions, closing gala at Cardiff Castle
Notes: The event program will be over a period of three days providing an active balance of professional and cultural activities. The first day will consist of keynotes and a cultural reception. Day 2 will consist of interactive workshops, exhibition and visit to some of the classic Welsh landmarks. The 3rd day will be based on strategy and networking, and it will be finished with the gala dinner with Welsh food and performances. This combination will make delegates involved and interested in Welsh culture

## Slide 8: Sustainability & CSR
Environmental Initiatives: Plastic-free, waste reduction, renewable energy use
Social Responsibility: Inclusivity (accessibility for all), local community engagement
Economic Sustainability: Local procurement, fair wages, budget monitoring
Notes: We will make our summit sustainable, in the Triple Bottom Line manner (Nica, Chiriță and Georgescu, 2025). On the environmental front, we will be rid of single-use plastics and will apply recyclable material. At the social level, we strive to be inclusive and would have easy access to services and interactions with the local cultural groups. Economically, the event will benefit the local economy by ensuring the ethical buying approach and fair wages to all

## Slide 9: Risk Management & Crisis Plan
Risk Management & Crisis Plan
Risk Assessment
Mitigation Strategies
Crisis Management Protocol
Notes: Risk management is a must in any big event (Gallardo‐Vázquez, 2025). Our risk assessment has been done with main risks being identified such as health emergency, weather disturbances and security risks. On site medical personnel, alternative locations in case of weather complications and security provisions are some of the mitigation measures. Our crisis management plan will be such that there is a fast and clear communication in the event that something goes wrong.

## Slide 10: Operational Plan & Logistics
Project Management: Event cycle approach with a Gantt chart and milestone checkpoints
Staffing: Core team of 5, 30 on-site staff/volunteers
Delegate Services: Online registration, pre-arrival info packs, on-site signage, multilingual support
Technology: Event management software, mobile app, high-speed Wi-Fi
Notes: Our operation strategy will have a systematized project management process, having clear time lines, responsibilities, and check points. The number of staff involved will comprise a core team of 5 people who will undertake all the event management processes with a total of 30 people going on-site as volunteers. A delegate experience will be smooth and simple through easy online registration, ultimate pre-arrival information and our multilingual support. We will also capitalize on technology where we use a mobile application to network and engage in real-time to keep operations running smoothly

## Slide 11: Event Evaluation & Success Metrics
KPIs: Attendance, financial outcomes, attendee satisfaction (80%+ positive feedback)
Data Collection: Surveys, app analytics, social media metrics, ROI analysis
Reporting: Event evaluation report with findings and improvement areas
Notes: The key performance indicators (KPIs) will be used to measure the event success, i.e., attendance of delegates, financial performance, and satisfaction of the attendants. The collection of data will be conducted through post-event surveys, application analytics, and use of social media. The analysis of ROI will assist us to evaluate financial results, and an event evaluation report will give us the information about achievements and the aspects that will be improved in the future.

## Slide 12: Conclusion
Feasibility Confirmed: Event is viable with a strong market demand, operational support, and financial sustainability.
Strategic Alignment: Aligns with industry trends, leveraging MICE tourism and promoting Wales as a top cultural destination.
Value Proposition: Benefits for all stakeholders: delegates, sponsors, exhibitors, the host destination, and the local community
Notes: In summary, Year of Legends is a well-coordinated and viable event that has a high prospect of enhancing the image of the tourism in Wales. The event also helps in the economic development by networking and partnering with international countries and also through the provision of cultural experiences, which are beneficial to the delegates and the local people. The success of the event will not only achieve short-term objectives but also provide the foundation to the cultural tourism sector in Wales grow in the future

## Slide 13: References
Business Wales, 2025. Wales Tourism Week 2025. Online: https://businesswales.gov.wales/news-and-blog/wales-tourism-week-2025
ICC Wales, 2025. Wales Tech Week 2025. Online: https://www.iccwales.com/whats-on/wales-tech-week-2025
Galagar, M.S., Libo-on, R.M. and Miñoza, J.T., 2025. An exploratory case study of sustainable tourism environment for a nature-oriented market: inputs to the development of a travel brochure. Journal of Ecotourism, pp.1-17.
Borrego-Baslalobre, F.J., Angosto, S., Zurita-Ortega, F. and Morales-Baños, V., 2025. Quality of Web Offering for Canoeing as a Sustainable Tourism and Recreational Tool. Journal of Tourism and Services, 16(30), pp.190-214.
Chullen, C., Hall, T., Oliva, V., Nuhfer, Z., Rodgers, D.L., Krenzel, J., Ibanez, R. and Andrews, G.M., 2025, July. Cultivating and Communicating Robust Knowledge Through Collaboration. In 54th International Conference on Environmental Systems (ICES) (No. ICES-2025-32).
Nica, I., Chiriță, N. and Georgescu, I., 2025. Triple Bottom Line in Sustainable Development: A Comprehensive Bibliometric Analysis. Sustainability, 17(5), p.1932.
Gallardo‐Vázquez, D., 2025. Defining the Path to Sustainability Based on Triple Bottom Line Dimensions. Corporate Social Responsibility and Environmental Management.