## Feasability Costs
Feasability Cost Plan for Joseph Parry Theatre
Ref |  |  | Original Rate | Measure | Unit of Measure | Adjusted Rate | Total
Theatre
T1 | Option 1 (Mount View Academny, London) |  | 1643.1409 | 3000 | m2 | 2327.783 | 6983348.9082
T2 | Option 2 (Similar Project) |  | 2857.1429 | 3000 | m2 | 5298.7013 | 15896103.8961
T3 | Spons m2 rate |  | 7781.48 | 3000 | m2 | 7982.1109 | 23946332.7904
Landscaping
L1 | Break out Existing Hardstanding |  | 85 | 2250 | m3 | 87.1916 | 196181.0241 | Breakout and dispose
L2 | Site Clearance |  | 200 | 5400 | m3 | 206.4 | 1114560 | based on hazardous material. 9000m2 x 600mm depth
L3 | Provisional Sum: Japenese Knott Weed |  | 200 | 3150 | m3 | 206.4 | 650160 | 7m rule @ 5% of site area
L4 | Additional Foundations |  | 87.01 | 3150 | m2 | 89.7943 | 282852.108 | 2,3 & 4. Pile Foundaions with Beam support
L6 | Block paving on a permiable base |  | 85 | 1600 | m2 | 87.72 | 140352
| Surveys | [5 empty] | 50000
S1 | UXO
S2 | Transport Assessment
S3 | Architectual Watching Brief
S4 | Ground Investigation
S5 | Environmental Report
S6 | Drainage Report
S7 | Bird Survey
S8 | Bat Survey
S9 | Flood Risk Assessment
[6 empty] | Total | 26380437.9225
Optional
O1 | Bridge |  | 5300 | 475 | m2 | 8453.0182 | 4015183.6364 | 95M Bridge x 5m width based on approximate sizes
O2 | Car Park |  | 110 | 783 | m2 | 113.52 | 88886.16 | 12.5m2 per space, 18m2 per disabled. 1 space per 5 seats allowed for 10% disabled
Total
P1 | Prelims | [5 empty] | 3048450.7719
P2 | Risk | [5 empty] | 2133915.5403
P3 | Misc | [5 empty] | 914535.2316
6096901.5438
|  |  |  | Total Funding Required |  |  | 36581409.2626

## Summary Sheet
Element Ref | Element | Cost Summary (Prior to Adjustment) | Cost Summary (Updated for Location Only) | Cost Sumary (Updated for both Location and Construction Date)
0 | Facilitating Works | 780000 | 663000 | 805580.6452
1 | Sub-Structure | 651052.5 | 553394.625 | 672404.2218
2 | Superstructre | 6103278 | 5187786.3 | 6303439.2677
3 | Internal Finishes | 787430 | 669315.5 | 813254.3172
4 | FFE | 389250 | 330862.5 | 402015.7258
5 | Services | 1541200 | 1310020 | 1591744.7312
6 | Prefab Build & Units | 0 | 0 | 0
7 | Work to Existing Buildings | 0 | 0 | 0
8 | External Works | 472880.2 | 401948.17 | 488388.6367
9 | Main Contractor Prelims | 1072509.07 | 911632.7095 | 1107682.7546
10 | Main Contractor OH&P | 1179759.977 | 1002795.9804 | 1218451.03
11 | Project Design Fees | 589879.9885 | 501397.9902 | 609225.515
12 | Other Development Project Costs | 1002795.9805 | 852376.5834 | 1035683.3755
13 | Risk | 2185505.3574 | 1857679.5538 | 2257180.5331
Total |  |  |  | 17305050.7537
Assumptions
Further information will become available in terms of accurate measurements

## 0 Facilitating Works
Facilitating Works
Ref | Description | Quantity | Measure | Rate | Total | Notes
2.1.0.1 | Toxic/Hazardous/Contaminated Material Treatment | 3150 | m3 | 200 | 630000 | Alllow to remove japenese knott weed. Provisional Sum 5% of site area 7m rule
2.1.0.3 | Radon Barrier |  | m2 | 10.5 | 0 | Cost not available at this time
| Surveys - Provisional Sum | 1 | Item | 150000 | 150000
|  | Total |  |  | 780000

## 1 Substructure
Sub-Structure
Ref | Description | Quantity | Measure | Rate | Total | Notes
2.1.1.1 | Excavate to form piling mat; supply and lay imported hardcore - recycled brick and similar to form mat. | 25 | m3 | 11.3 | 282.5
2.1.1.2 | Privision of Plant (1nr Rig); including bringing to and removing from site; maintenance, erection and dismantling at each pile position. | 1 | Item | 19000 | 19000
2.1.1.3a | Supply and install concrete Continuous Flight Auger (CFA) piles; cart away inactive spoil. 15m long pile; 900mm diamaeter. Reinforced concrete CFA Piles. | 35 | nr | 3450 | 120750 | Theatre Building
2.1.1.3b | Supply and install concrete Continuous Flight Auger (CFA) piles; cart away inactive spoil. 15m long pile; 900mm diamaeter. Reinforced concrete CFA Piles. | 25 | nr | 3450 | 86250 | Building B
2.1.1.3c | Supply and install concrete Continuous Flight Auger (CFA) piles; cart away inactive spoil. 15m long pile; 900mm diamaeter. Reinforced concrete CFA Piles. | 30 | nr | 3450 | 103500 | Building C
2.1.1.4a | Excavate pit in firm ground by machine, partial back fill, partial disposal, support, compaction, cut off pile and reinforcement, formwork; reinforced in situ concrete cap 25 N/mm2; reinforcement at 50 kg/m3; rates per cap for cap size. 900mm x 900mm x 1000mm; 1-2 piles. All piles to installed through soil extraction due to surrounding conservation area. | 35 | nr | 1278 | 44730 | Theatre Building
2.1.1.4b | Excavate pit in firm ground by machine, partial back fill, partial disposal, support, compaction, cut off pile and reinforcement, formwork; reinforced in situ concrete cap 25 N/mm2; reinforcement at 50 kg/m3; rates per cap for cap size. 900mm x 900mm x 1000mm; 1-2 piles. All piles to installed through soil extraction due to surrounding conservation area. | 25 | nr | 1278 | 31950 | Building B
2.1.1.4c | Excavate pit in firm ground by machine, partial back fill, partial disposal, support, compaction, cut off pile and reinforcement, formwork; reinforced in situ concrete cap 25 N/mm2; reinforcement at 50 kg/m3; rates per cap for cap size. 900mm x 900mm x 1000mm; 1-2 piles. All piles to installed through soil extraction due to surrounding conservation area. | 30 | nr | 1278 | 38340 | Building C
2.1.1.5a | Reinforced in situ concrete ground beams; bar reinforcement; formwork. 450mm x 600mm, reinforcement at 270 kg/m3. | 220 | m | 275 | 60500 | Theatre Building
2.1.1.5b | Reinforced in situ concrete ground beams; bar reinforcement; formwork. 450mm x 600mm, reinforcement at 270 kg/m3. | 180 | m | 275 | 49500 | Building B
2.1.1.5c | Reinforced in situ concrete ground beams; bar reinforcement; formwork. 450mm x 600mm, reinforcement at 270 kg/m3. | 350 | m | 275 | 96250 | Building C
| Total |  |  |  | 651052.5

## 2 Superstructure
Superstructure
Ref | Description | Quantity | Measure | Rate | Total | Notes
2.1.1.1 | Structural steel frame, including fittings and fixings: details, including size of measurement for ascertaining the gross internal floor area (GIFA). | 3750 | m2 | 425 | 1593750 | Suspended slab; permanent steel shuttering with 130mm thick concrete; no coverings or finishes up to 6 storeys. Additional GIFA used to allow for the vaulted areas.
2.2.1.1 | Precast concrete suspended floors; 1200mm wide suspended slab; 75mm thick screed; no coverings or finishes | 3750 | m2 | 175 | 656250 | Additional GIFA used to allow for the vaulted areas.
2.3.2.1 | Roof structure – flat roofs. The area measured is the area of the roof on plan measured to the inside face of the external walls. | 1900 | m2 | 99 | 188100 | 75mm thick lightweight bituminous screed and vapour barrier.
2.3.4.1 | Gutters | 35 | m | 94 | 3290 | Allowed for edges to flat roofs; code 4 lead drip dresses into gutter; 230mm x 25mm painted softwood fascia; buildup. 100mm uPVC gutter.
2.3.4.2 | Rainwater Pipes | 25 | m | 57 | 1425 | 110mm diamater uPVC downpipes fixing to backgrounds; including offsets and shoes.
2.4.1.1 | Stair Structures | 3 | nr | 18000 | 54000
2.5.1.1 | Metal rainscreen cladding system, two finishes, including Metsec, concealed fixings, flashings | 2950 | m2 | 1025 | 3023750 | Extra allowance made to allow for Cor-Ten Steel Finish.
2.6.1.1a | Aluminium windows (U-value = 1.6W/m2 K) Standard windows double glazed; powder coated | 200 | m2 | 590 | 118000 | Measured 175m2. Allowed extra due to drawing innacruacies. Steel windows (U-value = 1.6W/m2 K) Standard windows double glazed; powder coated
2.6.1.1b | Curtain Wallings System; Walling systems; stick curtain walling with double glazed units, aluminium structural framing and spandrel rails. Standard colour powder coated capped. | 250 | m2 | 650 | 162500 | Walling systems; stick curtain walling with double glazed units, aluminium structural framing and spandrel rails. Standard colour powder coated capped. Measured 185.15m2 allowed for 250m2 due to drawing inaccruancies.
2.6.1.1c | Rooflights, skylights, roof windows and frames; pre-glazed; treated Nordic Red Pine and aluminium trimmed Velux windows GGU 3070 or other equal; type U flashings and soakers (for tiles and pantiles up to 45mm deep), and sealed double glazing unit (trimming opening not included) Roof windows | 4 | nr | 2163.5 | 8654 | Based on 5m2 windows to Fire escpae
2.6.2.1a | Aluminium external doorsets, incl. all ironmongery, double | 7 | nr | 2650 | 18550
2.6.2.1b | Automatic high capacity revolving doors; 2-wing ASSA ABLOY UniTurn providing safe hands free operation with capacity for multiple occupants and trolleys per compartment. Modern modular design with two centre passage manually pivoting break out door leaves arranged between two rotating showcases. Curved glazed outer walls and canopy enclose a whole rotating radially segmented ceiling, fixed semi-circular dustcovers and load-bearing peripheral drive with imbedded Configurable Digital Control. System including normal installation to comply with BS7036–0-2014 / BS-EN16005, complete with the installer’s Declaration of Conformity in accordance with UniTurn High Capacity Automatic Revolving Door; 2 wing 5400mm dia., 2200mm internal height | 2 | nr | 60667 | 121334
2.7.1.1a | Internal Walls; Plater bord with a plaster finish | 875 | m2 | 100 | 87500 | 350Lm x 2.5 high = 875m2
2.8.1.1a | Hardwood panelled; hardwood lining; hardwood architrave; aluminium ironmongery (latch only); brass or stainless ironmongery (latch only); painting and polishing single leaf; four panelled doors; mouldings | 29 | nr | 1175 | 34075
2.8.1.1b | Hardwood panelled; hardwood lining; hardwood architrave; aluminium ironmongery (latch only); brass or stainless ironmongery (latch only); painting and polishing double leaf; four panelled doors; mouldings | 11 | nr | 2250 | 24750
2.8.1.1c | Toilet Doors | 21 | nr | 350 | 7350 | Standard Internal Days
|  |  |  | Total | 6103278

## 3 Internal Finishes
Internal Finishes
Ref | Description | Quantity | Measure | Rate | Total | Notes
2.1.3.1 | Concrete Wall Finishes | 2950 | m2 | 45 | 132750 | two coat sand cement render and emulsion finish
2.1.3.1a | Timber acoustic wall finsihes to theatre | 1600 | m2 | 275 | 440000
2.1.3.2a | Floor Finishes - Main Building | 1944 | m2 | 35 | 68040 | Screeds to cores and common areas; 150mm thick to make up levels
2.1.3.2b | Floor Finishes - Carpet, heavy duty carpet tiles, including timber skirting | 1056 | m2 | 75 | 79200
2.1.3.3 | Ceiling Finishes | 3000 | m2 | 22.48 | 67440 | Plaster to soffits plaster skim coat to plasterboard ceilings Emulsion paint to plaster; one mist and two coats
|  |  |  | Total | 787430

## 4 FFE
Fittings, Furnishings and Equipment
Ref | Description | Quantity | Measure | Rate | Total | Notes
2.1.4.1a | No allowance to be made for soft furnishings. | 1 | Item | 150000 | 150000 | Provisional Sum
2.1.4.1b | Theatre Seating | 435 | nr | 550 | 239250 | 396 shown on drawings. Allowed for an additional 10% due to limited information.
|  |  |  | Total | 389250

## 5 Services
Services
Ref | Description | Quantity | Measure | Rate | Total | Notes
2.1.5.1 | Sanitary Installations | 3000 | m2 | 57 | 171000 | Based on Gifa
2.1.5.4 | Water Installations | 3000 | m2 | 67 | 201000 | Based on Gifa
2.1.5.7 | Ventilation | 3000 | m2 | 63 | 189000 | Based on Gifa
2.1.5.8 | Electrical Installations | 3000 | m2 | 28 | 84000 | Based on Gifa
2.1.5.9 | Fuel Installations | 3000 | m2 | 4.4 | 13200 | Gas mains service to plantroom. Gross internal floor area
2.1.5.10 | Lift and Conveyor Installation | 2 | nr | 140000 | 280000 | Passenger lifts (standard brushed stainless steel finish; 2 panel centre opening doors). 13 person; 6 stops
2.1.5.11 | Fire and Lighting Protection | 3000 | m2 | 56 | 168000 | Gross internal floor area (unless described otherwise); Including fire alarm, public address system, security installation unless stated otherwise
2.1.5.12 | Communication, Security and Control Systems | 3000 | m2 | 145 | 435000 | Gross internal floor area (unless described otherwise); Including fire alarm, public address system, security installation unless stated otherwise
|  |  |  | Total | 1541200

## 6 Prefab Build & Units
Prefabricated buildings and building units
Ref | Description | Quantity | Measure | Rate | Total | Notes
2.1.6.1 | Prefabrication buildings and building units |  | m2 | 0 | 0 | N/A
|  |  |  | Total | 0

## 7 Work to Exist Buildings
Work to existing buildings
Ref | Description | Quantity | Measure | Rate | Total | Notes
2.1.7.1 | Minor Demolition and Alteration Works |  | m2 | 0 | 0 | N/A
|  |  |  | Total | 0

## 8 External Works
External Works
Ref | Description | Quantity | Measure | Rate | Total | Notes
2.1.8.2 | Permeable concrete block paving; 80mm thick Formpave Aquaflow or equal; maximum gradient 5%; laid on 50mm sand/gravel; subbase 365mm thick clean crushed angular non plastic aggregate, geotextiles filter layer to top and bottom of subbases | 1600 | m2 | 73 | 116800
2.1.8.4 | security fencing; 2400mm high painted plywood hoarding | 475 | m | 157.5 | 74812.5
2.1.8.6 | External Drainage | 1600 | m2 | 108 | 172800 | Drainage
2.1.8.7 | External Services | 1 | nr | 100000 | 100000 | Provisional Sum; allowing for laying electric, water and gas as well as connection
2.1.8.8 | Tree planting semi-mature or mature tree, 40–45cm girth | 10 | nr | 846.77 | 8467.7 | Provisional Sum
2.1.8.9 | Car Park | 783 | m2 | 125 | 97875
|  |  |  | Total | 472880.2

## 9 Main Contractor Prelims
Main Contracor Prelims
Ref | Description | Quantity | Measure | Total | Notes
2.1.9 | Main Contractors Prelims | 10 | % | 1072509.07

## 10 Main Contractor OH&P
Main Contracrors OH&P
Ref | Description | Quantity | Measure | Total | Notes
2.1.10 | Main Contractors OH&P | 10 | % | 1179759.977

## 11 Project_design fees
Project Design Fees
Ref | Description | Quantity | Measure | Total | Notes
2.1.11 | Design Fees | 5 | % | 589879.9885

## 12 Other Dev_Proj Costs
Ref | Description | Quantity | Measure | Total | Notes
2.1.12 | Misc | 8.5 | % | 1002795.9805 | N/A

## 13 Risks
Ref | Description | Quantity | Measure | Total | Notes
2.1.13 | Risk built into the project due to the incomplete design and modelling issues, and increased risk allowance has been made to ensure covereage of desgin changes as the work progresses. | 15 | % | 2185505.3574