## Slide 1: Final account procedures

## Slide 2: The contract sum may need to be adjusted for a number of reasons, including:
Variations.
Fluctuations.
Prime cost sums.
Provisional sums.
Payments to nominated sub-contractors or nominated suppliers.
Statutory fees.
Payments relating to the opening-up and testing of the works.
Loss and expense.
Liquidated and ascertained damages.
Contra claims imposed as a result of the contractor's operations (such as a third-party claim resulting from contractor negligence or contractual breach, for example, flooding a neighbour's property).
The release of any remaining retention.

## Slide 3
This presentation summarises what a final account is and how they are used to establish a final adjustment to the contract price. The practical issues of how to prepare a final account in accordance with the contract and the process of cooperation between the parties and negotiation will also be discussed.
Practical consideration such as advising on the structure of a final account and how to prepare a statement for final account (including examples) will also be considered.

## Slide 4: What is a final account
We will investigate what a final account is. What are the common definitions within the major contracts and how the contractual procedures may differ.

## Slide 5
The final account is the conclusion of the contract sum (including all necessary adjustments) and signifies the agreed amount that the employer will pay the contractor. It includes any works that are paid to the contractor through the main contract.

## Slide 6
Typically, the final account includes any loss and expense associated with any extensions of time and any other claims the contractor feels he or she is due under the contract. It also indicates the finalisation of any disputes that may have arisen and in that sense draws a line under the financial obligations of both parties, save in respect of defects. The final account will not typically include items such as liquidated damages, VAT or interest on overdue payments.

## Slide 7: Contractual definitions of final account
The procedures, as set out in the various forms of contract, contain slight differences in terminology and procedure (i.e. between the JCT and the NEC contracts), but essentially they produce the same result. Most contracts require the contractor to substantiate their accounts to the employer so it can be properly assessed.

## Slide 8
The NEC forms of contract do not refer to final accounts as it is assumed that the final account is adjusted as the project proceeds on the basis that the compensation event procedure is followed.

## Slide 9
The JCT defines the process for final accounts and final payments under clause 4.12 of the Design and Build Contract or Clause 4.5 of the JCT Standard Form.
Note that the timelines are different between the Standard Building Contract and the Design and Build Contract.

## Slide 10
The FIDIC suite of contracts, which are mainly used for the international market all have their own timescales. Clause 14 refers to payment and subclause 14.11 spells out the final account process and timescales.

## Slide 11: Rolling final accounts

## Slide 12
The term ‘rolling final accounts’ is often used, but it is not always properly adhered to. Rolling final accounts will ensure that all instructions and cost effects to a project are agreed and up-to-date at the point of the latest financial report. This relies on an organised quantity surveyor and contractor and willingness of the parties to make agreements on a regular on-going basis.

## Slide 13
The NEC contracts put more emphasis on the timescales related to agreeing individual variations (known as compensation events).
Time bar penalties are also included for not agreeing compensation events within the contractual timescales. In theory this forces a rolling final account to be maintained but unfortunately, this does not necessarily mean that all NEC contracts are used as they should be. The NEC is designed to agree cost and time simultaneously.
.

## Slide 14
Conversely it doesn’t necessarily mean that other contracts don’t have a long final account process. The reality is that the contract can only provide the framework for final accounts to be agreed throughout the contract period.
It still relies on the hard work, organisation and willingness by both parties to make agreements as they go along.
Remember that it is not the role of the QS to agree variations or final accounts. The QS’s role is to value variations in accordance with the contract and adjust the final account as necessary

## Slide 15: Preparing for final account

## Slide 16: Preparing for final account
The preparation of the final account occurs throughout the contract period.
Financial statements prepared by the quantity surveyor will generally serve as the starting point for final account discussions.
As a matter of preparation, the professional quantity surveyor (PQS) should ensure that all contracts instructions have been accounted for and that all other potential cost-related items are scheduled out

## Slide 17: This may include, but not be limited to:
provisional sums (which can only be expended by issue of a contact instruction)
agreeing prime cost sums (where applicable)
any loss and expense associated with extensions of time
adjustment of provisional/approximate quantities
fluctuations
any set-off/contra charges (typically a subcontractor issue) or
any other items affecting total cost.

## Slide 18: Preparing a Final account (contd)
Note that standard building contracts do not contain any express provision for dealing with contra charges, therefore, if agreed between the contractor and employer they should be instructed as a variation to the contract.
If the contractor does not agree then any off-sets/contra charges must go through the ‘pay less notice’ process outlined in the Local Democracy, Economic Development and Construction Act 2009 (which will be referenced as ‘The Construction Act’ in this guidance note).

## Slide 19
From the contractor’s perspective, they will also go through a similar exercise in preparation for the final account, but also ensuring that all possible variations from subcontractors and suppliers are picked up and reported to the employer.
The contractor will not want to enter final account negotiations without having accurate costs from their supply chain, although there may be no direct contractual link between the contractor’s entitlement to be paid by the employer when compared with an obligation to pay their subcontractors.

## Slide 20: Linking the last formal cost report to final account
The last formal cost report presented by the PQS should provide a very good indication of where the final account is likely to be settled. If costs have been tracked properly throughout the duration of the project then the only difference between the last formal costs report in the final account should be any changes or variations in the period between the last forecast reports in the final account.

## Slide 21
Suitable project documentation and well-followed contract administration procedures should make the task of preparing a final account more straightforward in the long run.
Good documentation is easily auditable and the importance of this is highlighted when proper records are not available.
Disputes can occur where key members of either the employer’s or contractor’s team changes throughout the project duration.

## Slide 22
At the commencement of the project, the project manager should produce a project execution plan (PEP), and within this plan, there should be a procedure set out for contract administration of the project.
This should include the change control mechanism and the procedure for contract instructions.
This helps to provide a framework for auditability to keep good contract documentation, which can be referred to during the final account negotiations

## Slide 23: Importance of change control
Change control is the administrative process that implements the contract mechanisms for instructing change.
The process must adhere to the contract requirements for notification and approval of change by the identified parties.
Change control is also a critical part of a well-run and audited project.
Any potential changes should go through this process before an instruction is given so that the employer feels they are able to make informed decisions.
It also ensures that the contractor is not going ahead and acting on changes that they believe they’ve been instructed to do, only to find out that they were not actually communicated to the employer.

## Slide 24
The change control system should not be too cumbersome so that it deters the project team from using it.
All parties should want to use it, as it will provide security, auditability and clarifications of any changes or rejections of any changes.
Without a well-managed change control process, the final account negotiations may be more difficult.
There may be a difference of opinion between what the contractor believes they were instructed compared to what they were actually instructed.

## Slide 25: Final account meetings - preparation and procedure
The final account meetings are generally held between the contractor and the quantity surveyor, although it is not unusual for the project manager, the designer, or a representative from the employer to also attend.
It is an opportunity to exchange information and present methodologies for valuation of each variation in accordance with the contract. It is not a forum to make agreements on the valuation of variations beyond the contract conditions.

## Slide 26
Most of the preparatory work should have been carried out ahead of time so that the final account meeting can focus on agreeing the few outstanding items that may be still in abeyance.
If there is a difference of opinion between the contractor and the employer’s quantity surveyor then it is suggested that further work is done to close the gap using telephone calls and more informal meetings between the employer and contractor.
The final account meeting should certainly not be the first time that parties have seen each other’s positions; this would indicate that the change control process has not been working properly.

## Slide 27
Agreement of the final account will allow the contract administrator to issue the final certificate. The final certificate is conclusive that all paten defects have been remedied, all adjustments to the contract sum have been agreed and all claims settled.
Latent defects may still become apparent after completion of the contract and these may give rise to action for damages, for breach ofcontract or negligence.
Where proceedings have begun in relation to a dispute, the conclusiveness of the final certificate is subject to the findings of those proceedings.
In addition, the final certificate itself can be disputed (usually within 28 days).
Adjudication, arbitration or other dispute resolution procedures may then be necessary to resolve the dispute. The final certificate is then only conclusive in relation to matters that are not disputed.