## Feasability Costs
Feasability Plan for Multi Use Project
2008/2232 ¦ Construction of 6 storey mixed use development comprising of 1 no. ground floor retail unit (Class A1) and 1 no. ground floor food and drink unit (Class A3) and 132 no. bedroom hotel (Class C1) with 10 no. car parking spaces and delivery/service yard (application for reserved matters approval pursuant to outline planning permission 2002/1000 granted on the 19th August 2003) ¦ Site A14A Swansea SA1
|  | Rate | Total | Notes
Hotel Cost Per Bed
18 | nr | 115000 | 2070000 | Double
117 | nr | 115000 | 13455000 | Twin
Lifts
2 | nr | 145000 | 290000 | Passenger
Parking Spaces
300 | m2 | 110 | 33000
Delivery and Service Area
150 | m2 | 110 | 16500
150
Ground Floor Retail
600 | m2 | 1575 | 945000
Ground Floor Food and Drink
750 | m2 | 2125 | 1593750
|  | Total | 18403250

## Information_Used
Design Drawings
SITE_A14_A_ELEVATION_TO_DOCKSIDE-74211
SITE_A14_A_ELEVATION_TO_LANGDON_ROAD_59493
SITE_A14_A_ELEVATION_TO-PLOT-A11C-59694
SITE_A14_A_ELEVATION-TO-PLAZA-59695
SITE_LOCATION_PLAN-32644
SITE_PLAN-59695
SP136_P01_PROPOSED_GROUND_FLOOR_PLAN-70364
SP136_P02_FIRST_FLOOR_PLAN-70362
SP136_P03_SECOND_FLOOR_PLAN-59698
SP136_P04_THIRD_FLOOR_PLAN-59698
SP136_P05_FOURTH_FLOOR_PLAN-70363
SP136_P06_FIFTH_FLOOR_PLAN-59699
SP136_P07_ROOF_Plan-59700
General Information
All cost are based on higher end rates due to the inaccuracies of the drawings.
No allowance has been made for the fit out of a restaurant or Supermarket. Assumed this will be fitted out by the adopted occupier.
At this time a figure has not been generated for the Radon barrier however will be required.
Figures are based on rates for June 2024, should an accruate timeline become available the indcies can be adjusted to reflect this.
Query Sheet
Application Number: |  | 2008/2232
Project Site: |  | Mixed-Use Development Site A14A, SA1, Swansea
Student Name: |  | Thomas Dilley | Lecturer: | Debroah Hughes
Return E-mail: |  | 1550329@student.uwtsd.ac.uk | Contact E-mail: | d.hughes@uwtsd.ac.uk
Query Number | Query Date | Query |  | Response Date | Response
1 | 10.11.2023 | Can you please confirm the general finish of the scheme. |  | 2023-11-10 | Mid range to suit the image of the area.
2 | 10.11.2023 | Can you confirm the date that works are anticipated to be undertaken. |  | 2023-11-10 | Works to start ideally July 2024
3 | 10.11.2023 | There are 132nr Rooms stated in the information however there are 135nr Rooms shown in the drawings. Can you confirm you are happy to base the costs on the 135nr shown. |  | 2023-11-10 | Yes
4 | 10.11.2023 | Can you confirm if you there needs to be any allowances for the purchases of land, or has a separate budget been raised for this. |  | 2023-11-10 | I own the land and so doesn't need to be accounted for.
5 | 10.11.2023 | Are you able to provide me with the sizes of the build as the documents provided have been scanned in therefore are not to scale. There are no sizes shown on the drawings. Dimensions needed for the shops, as well as overall hotel size. |  | 2023-11-10 | No please use known measurements to scale from.
6 | 10.11.2023 | If a ground survey has been undertaken, can you provide the report? |  | 2023-11-10 | No but no contamination found only UXB testing required.
7 | 10.11.2023 | Is there any budget restrictions that I should be aware of? |  | 2023-11-10 | No unless price goes over the anticipaed budget figure
8 | 10.11.2023 | Is there any additional costs such as proffesional fees that need to be applied to budget? |  | 2023-11-10 | Professional fees need to be included as I don't know what they should be.

## Summary Sheet
Element Ref | Element | Cost Summary (Prior to Adjustment) | Cost Summary (Updated for Location Only) | Cost Sumary (Updated for both Location and Construction Date)
0 | Facilitating Works | 147 | 124.95 | 147.155
1 | Sub-Structure | 238845 | 203018.25 | 239096.7944
2 | Superstructre | 3628860 | 3084531 | 3632685.6054
3 | Internal Finishes | 710812.5 | 604190.625 | 711561.8505
4 | FFE | 1282500 | 1090125 | 1283852.0331
5 | Services | 3687650 | 3134502.5 | 3691537.5828
6 | Prefab Build & Units | 0 | 0 | N/A
7 | Work to Existing Buildings | 0 | 0 | N/A
8 | External Works | 104015 | 88412.75 | 104124.6544
9 | Main Contractor Prelims | 965282.95 | 820490.5075 | 966300.5676
10 | Main Contractor OH&P | 1592716.8675 | 1353809.3374 | 1594395.9365
11 | Project Design Fees | 1592716.8675 | 1353809.3374 | 1594395.9365
12 | Other Development Project Costs | 0 | 0 | N/A
13 | Risk | 1380354.6185 | 1173301.4257 | 1381809.8116
Total |  |  |  | 15199907.9278

## 0 Facilitating Works
Facilitating Works
Ref | Description | Quantity | Measure | Rate | Total | Notes
2.1.0.1 | Toxic/Hazardous/Contaminated Material Treatment | 1650 | m2 | 0 | 0 | No Price available at this time. This will be required.
2.1.0.3 | Temporary Support to adjacent Structures | 14 | m | 10.5 | 147 | Yes, neighbouring lot requires support to paved area. 14m x allow for 500mm high. Allow for temporary earth support.
|  | Total |  |  | 147

## 1 Substructure
Sub-Structure
Ref | Description | Quantity | Measure | Rate | Total | Notes
2.1.1.1 | Excavate to form piling mat; supply and lay imported hardcore - recycled brick and similar to form mat | 100 | m3 | 11.3 | 1130 | Allow for site movement into serveral locations.
2.1.1.2 | Privision of Plant (1nr Rig); including brignging to and removing from site; maintenance, erection and dismantling at each pile position. | 1 | Item | 19000 | 19000
2.1.1.3 | Supply and install concrete Continuous Flight Auger (CFA) piles; cart away inactive spoil. 15m long pile; 900mm diamaeter. Reinforced concrete CFA Piles | 39 | nr | 2775 | 108225 | 15m reinforced pile allowed for per pile.
2.1.1.4 | Excavate pit in firm ground by machine, partial back fill, partial disposal, support, compaction, cut off pile and reinforcement, formwork; reinforced in situ concrete cap 25 N/mm2; reinforcement at 50 kg/m3; rates per cap for cap size. 900mm x 900mm x 1000mm; 1-2 piles | 39 | nr | 910 | 35490
2.1.1.5 | Reinforced in situ concrete ground beams; bar reinforcement; formwork. 450mm x 600mm, reinforcement at 270 kg/m3. | 500 | m | 150 | 75000
| Total |  |  |  | 238845

## 2 Superstructure
Superstructure
Ref | Description | Quantity | Measure | Rate | Total | Notes
2.1.1.1 | Structural steel frame, including fittings and fixings: details, including size of measurement for ascertaining the gross internal floor area (GIFA). | 5750 | m2 | 180 | 1035000 | Suspended slab; permanent steel shuttering with 130mm thick concrete; no coverings or finishes up to 6 storeys. Gifa (3750, not in
2.2.1.1 | Precast concrete suspended floors; 1200mm wide suspended slab; 75mm thick screed; no coverings or finishes | 4750 | m2 | 100 | 475000
2.3.2.1 | Roof structure – flat roofs. The area measured is the area of the roof on plan measured to the inside face of the external walls. | 1000 | m2 | 77 | 77000 | 75mm thick lightweight bituminous screed and vapour barrier.
2.3.4.1 | Gutters | 170 | m | 94 | 15980 | 51m x 2 32m x 2 Rounded up for error. Allowedf or edges to flat roofs; code 4 lead drip dresses into gutter; 230mm x 25mm painted softwood fascia; buildup. 100mm uPVC gutter.
2.3.4.2 | Rainwater Pipes | 120 | m | 57 | 6840 | Allow for 6nr downpipes @ 20m each. 110mm diamater uPVC downpipes fixing to backgrounds; including offsets and shoes.
2.4.1.1 | Stair Structures | 8 | nr | 18000 | 144000 | 2nr 5 flights. 1nr 6 flights.
2.5.1.1 | External Walls | 2600 | m2 | 205 | 533000 | 50 x 20m = 1000m2 x 2 = 2000m2 32m x 20m = 640 x 2 = 1280m2 Total 3280m2 (error margin built in). (Less window m2). Allow for reinforeced concrete 25 N/mm2; 15kg/m2 reinofrcement; forwork both sides. 300mm thick.
2.6.1.1a | Windows | 146 | m2 | 590 | 86140 | 73nr @ 2m2 Steel windows (U-value = 1.6W/m2 K) Standard windows double glazed; powder coated
2.6.1.1b | Windows | 550 | m2 | 650 | 357500 | Walling systems; stick curtain walling with double glazed units, aluminium structural framing and spandrel rails. Standard colour powder coated capped
2.6.2.1a | External Doors | 8 | nr | 1225 | 9800 | Double external steel security door, including frame, ironmongery, powder coated finish
2.6.2.1b | External Doors | 4 | nr | 3800 | 15200 | Single external steel security door, including frame, ironmongery, powder coated finish
2.6.2.3 | Shop Front Doors | 1 | nr | 11500 | 11500 | Automatic glazed sliding doors in aluminium; polyester powder coated; linear sliding doors; inner pivoted pocket screens; glazed with safety units in accordance with BS. ASSA ABLOY SL510 P RC2 Anti-Burglar Sliding Door System complete with 100mm operator providing automated operation of the sliding door leaves Double bi-parting; opening 2.00m× 2.30m
2.7.1.1 | Internal Walls | 6000 | m2 | 93 | 558000 | Metal stud and board partitions; height range from 2.40m to 3.30m; 130mm thick partition; 70mm steel studs at 600mm centres generally; 2 layers 15mm Soundbloc board each side; joints filled with joint filler and joint tape; emulsion paint finish; softwood skirtings with gloss finish
2.8.1.1a | Internal Doors; Single | 307 | nr | 950 | 291650 | Standard fire doors; cellular core; softwood lining; softwood architrave; aluminuim ironmongery (lockable, self-closure); painting or polishing; single leaf; Oak veneered; 60 min fire resistance; polished
2.8.1.1b | Internal Doors; Double | 7 | nr | 1750 | 12250 | Standard fire doors; cellular core; softwood lining; softwood architrave; aluminuim ironmongery (lockable, self-closure); painting or polishing; double leaf; Oak veneered; 60 min fire resistance; polished
|  |  |  | Total | 3628860

## 3 Internal Finishes
Internal Finishes
Ref | Description | Quantity | Measure | Rate | Total | Notes
2.1.3.1a | Wall Finishes - Hotel | 4750 | m2 | 23 | 109250 | two coats of lightweight plaster with emulsion finish
2.1.3.1b | Wall Finishes - Commercial Space | 1500 | m2 | 32 | 48000 | two coat sand cement render and emulsion finish
2.1.3.2a | Floor Finishes - Hotel | 4750 | m2 | 75 | 356250 | Carpet tiles; including underlay, edge grippers heavy domestic duty; to floors;
2.1.3.2b | Floor Finishes - Commercial Space | 1500 | m2 | 68 | 102000 | Flexible tiling; welded sheet or butt joint tiles; adhesive fixing Vinyl safety flooring; 3.5mm thick heavy duty
2.1.3.3a | Ceiling Finishes - Hotel | 4750 | m2 | 15.25 | 72437.5 | Plaster to soffits plaster skim coat to plasterboard ceilings Emulsion paint to plaster; one mist and two coats
2.1.3.3b | Ceiling Finishes - Commercial Space | 1500 | m2 | 15.25 | 22875 | Plaster to soffits plaster skim coat to plasterboard ceilings Emulsion paint to plaster; one mist and two coats
|  |  |  | Total | 710812.5

## 4 FFE
Fittings, Furnishings and Equipment
Ref | Description | Quantity | Measure | Rate | Total | Notes
2.1.4.1 | Fully fitted out, finished and furnished bathroom pods; installed; suitable for business class hotels | 135 | nr | 9500 | 1282500 | All Bathroom pods based on accesible requirements
|  |  |  | Total | 1282500

## 5 Services
Services
Ref | Description | Quantity | Measure | Rate | Total | Notes
2.1.5.1 | Sanitary Installations | 4750 | m2 | 57 | 270750 | Based on Hotel Gifa
2.1.5.4 | Water Installations | 4750 | m2 | 67 | 318250 | Based on Hotel Gifa
2.1.5.7a | Ventilation; Hotel | 4750 | m2 | 63 | 299250 | Based on Gifa
2.1.5.7b | Ventilation; Supermearket | 1500 | m2 | 7.85 | 11775 | Based on Gifa
2.1.5.8a | Electrical Installations; Hotel | 4750 | m2 | 280 | 1330000 | Based on Gifa
2.1.5.8b | Electrical Installations; Supermarket | 1500 | m2 | 105 | 157500 | Based on Gifa
2.1.5.9 | Fuel Installations; Hotel | 4750 | m2 | 4.4 | 20900 | Gas mains service to plantroom. Gross internal floor area
2.1.5.9 | Fuel Installations; Supermarket | 1500 | m2 | 2.05 | 3075 | Gas mains service to plantroom. Gross internal floor area
2.1.5.10 | Lift and Conveyor Installation | 2 | nr | 140000 | 280000 | Passenger lifts (standard brushed stainless steel finish; 2 panel centre opening doors). 13 person; 6 stops
2.1.5.11a | Fire and Lighting Protection; Hotel | 4750 | m2 | 56 | 266000 | Gross internal floor area (unless described otherwise); Including lightning protection, sprinklers unless stated otherwise
2.1.5.11b | Fire and Lighting Protection; Supermarket | 1500 | m2 | 1.6 | 2400 | Gross internal floor area (unless described otherwise); Including lightning protection, sprinklers unless stated otherwise
2.1.5.12 | Communication, Security and Control Systems; Hotel | 4750 | m2 | 145 | 688750 | Gross internal floor area (unless described otherwise); Including fire alarm, public address system, security installation unless stated otherwise
2.1.5.12 | Communication, Security and Control Systems; Supermarket | 1500 | m2 | 26 | 39000 | Gross internal floor area (unless described otherwise); Including fire alarm, public address system, security installation unless stated otherwise
|  |  |  | Total | 3687650

## 6 Prefab Build & Units
Prefabricated buildings and building units
Ref | Description | Quantity | Measure | Rate | Total | Notes
2.1.6.1 | Prefabrication buildings and building units |  | m2 | 0 | 0 | N/A
|  |  |  | Total | 0

## 7 Work to Exist Buildings
Work to existing buildings
Ref | Description | Quantity | Measure | Rate | Total | Notes
2.1.7.1 | Minor Demolition and Alteration Works |  | m2 | 0 | 0 | N/A
|  |  |  | Total | 0

## 8 External Works
External Works
Ref | Description | Quantity | Measure | Rate | Total | Notes
2.1.8.2 | Roads, Paths, Pavings and surfacing | 550 | m2 | 110 | 60500 | based on tarmac
2.1.8.4 | Fencing, railings and walls | 7.25 | m2 | 240 | 1740 | Retianing walls 14.5m x 0.5m
2.1.8.6 | External Drainage | 550 | m2 | 30.5 | 16775 | Drainage
2.1.8.7 | External Services | 1 | nr | 25000 | 25000 | Provisional Sum; allowing for laying electric, water and gas as well as connection
|  |  |  | Total | 104015

## 9 Main Contractor Prelims
Main Contracor Prelims
Ref | Description | Quantity | Measure | Total | Notes
2.1.9 | Main Contractors Prelims | 10 | % | 965282.95

## 10 Main Contractor OH&P
Main Contracrors OH&P
Ref | Description | Quantity | Measure | Total | Notes
2.1.10 | Main Contractors OH&P | 15 | % | 1592716.8675

## 11 Project_design fees
Project Design Fees
Ref | Description | Quantity | Measure | Total | Notes
2.1.11 | Design Fees | 15 | % | 1592716.8675

## 12 Other Dev_Proj Costs
Ref | Description | Quantity | Measure | Total | Notes
2.1.12 |  |  | % | 0 | N/A

## 13 Risks
Ref | Description | Quantity | Measure | Total | Notes
2.1.13 | Risk built into the project. | 10 | % | 1380354.6185