## Sheet1
week start | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Jan 25th |  |  |  |  | 2d and 3d sketches - also look at prop possibilities
feb 1st | gather reference images for both projects
feb 8th |  |  | more 3d sketches - design sketches for prop | gather more reference images for both projects | technical drawings - more prop design sketches | narrow down prop design - (Tech Drawings) | finalise prop design - (Tech Drawings)
feb 15th | look at materials needed then see where to get them from - (Tech Drawings) | order materials - Tech and perspective drawings | (Drawings) | sketch out tapestry designs - (Drawings) | finalise tapestry designs - (Drawings) | start the first tapestry in photoshop - (Drawings) | (tapestry) - (Drawings)
feb 22nd | start making miniature basic skeleton - (tapestry) | (Miniature skeleton) - (tapestry) | cobweb experiments - (miniature skeleton) | finish technical and perspective drawings | (miniature skeleton) - (Tapestry) | (tapestry) - (miniature skeleton) | finish tapestry - (miniature skeleton)
mar 1st | basic prop prototype start - (miniature skeleton) | finish skeleton - (prop) | rock surface expeiments - (prop) | start second tapestry - (prop) | finish basic prototype - (tapestry) | make redesign requirements for prop, draw new tech drawings | draw in where wires for lights will go, put them in place where needed on miniature
mar 8th | start bulking out miniature and add surface details as go where necessary - (tapestry) | (tapestry) - (miniature) | practice arduino coding - (tapestry) | (tapestry) - (Miniature) | (tapestry) - (Miniature) | finish 2nd Tapestry - (Miniature) | Start 3rd Tapestry - (miniature)
mar 15th | finish bulking out (wet) - (tapestry) | start making prop mechanism - (taperstry) | base layer paint - (prop) | (paint) - (prop) | contrast colour? 2nd layer paint - (prop) | (tapestry) - (prop) | wash of shadow - (Prop)
mar 22nd | (tapestry) - (prop) | drybrush slight highlights - (prop) | finish the prop mechanism, start altering to make it as slim as possible | any touch up paints - (tapestry) | finish mechanism - (tapestry) | put on gloss where the rock would be glossy and wet | finish 3rd tapestry
mar 29th | start 4th Tapestry | add surface details such as rock debris on the floor, anything that has broken off the walls and things like that | (details) - (Tapestry) | add on the cobwebs - (Tapestry) | (Cobwebs) - (Tapestry) | make the brasiers (6 -8) - (tapestry) | make the columns (6-8) - (Tapestry)
apr 5th | finish 4th Tapestry - (brasiers and columns) | Paint the brasiers and columns | start 5th Tapestry - (paint) | start the athena statue | (tapestry) - (statue) | (tapestry) - (statue) | (tapestry) - (statue)
apr 12th | (tapestry) - (statue) | finish 5th Tapersty - (statue) | start any additional elements to tapestries - (statue) | (tapestry) - (statue) | finish additional elements - (statue) | print tapestry designs onto woven fabric - (statue) | start preparing prop materials - (statue)
apr 19th | (materials) - (statue) | (materials) - (statue) | paint statue | finish the athena statue | final touches and uniform the miniature as a whole | To be filled in once I know what my prop is
apr 26th
may 3rd
KEY: | graduation project all day | morning | afternoon
| indepndent project all day | morning | afternoon
| same for both projects all day | graduation project morning | graduation project afternoon
|  | independent project morning | independent project afternoon