## Monthly forecast
2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01
Site set up and sub structure phase 1 |  | Superstructure framing, all floors, and roofing works |  |  |  |  | External walls & curtain walling & scaffolding |  |  | Internal fit out of Phase 1 | [13 empty] | Internal fit out of phase 2 | [9 empty] | Handover of all buildings
1931606.79 |  | 5284775.97 |  |  |  |  | 1942317.23 |  |  |  |  | Changing site set up and substructure |  |  | Superstructure framing, all floors, and roofing works | [7 empty] | External wall & curtain walling |  |  |  | Landscaping of phase 2
[10 empty] | 6684260.55 | [14 empty] | Landscaping of phase 1 |  | 793914.6
[12 empty] | 1931606.79 |  |  | 5284775.97 | [7 empty] | 1942317.23
793914.6
6684260.55
Divided by percentage of ground floor cover on each phase block
[15 empty] | 3532872.7359 | [7 empty] | 1298439.0683 |  |  |  | 530731.9101
640327.6509 |  | 1751903.2341 |  |  |  |  | 643878.1617 |  |  | 2215832.3723 | [14 empty] | 263182.6899
[12 empty] | 1291279.1391 | [11 empty] | 4468428.1777
Site Set-up, professional fees, contingency
7356604.2
216370.71 | monthly/ 34mths
Month | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | Totals
Set-up/ prof fees/ contingency | 216370.71 | 216370.71 | 216370.71 | 216370.71 | 216370.71 | 216370.71 | 216370.71 | 216370.71 | 216370.71 | 216370.71 | 216370.71 | 216370.71 | 216370.71 | 216370.71 | 216370.71 | 216370.71 | 216370.71 | 216370.71 | 216370.71 | 216370.71 | 216370.71 | 216370.71 | 216370.71 | 216370.71 | 216370.71 | 216370.71 | 216370.71 | 216370.71 | 216370.71 | 216370.71 | 216370.71 | 216370.71 | 216370.71 | 216370.71 |  | 7356604.14
Building works | 320163.82 | 320163.82 | 350380.64 | 350380.64 | 350380.64 | 350380.64 | 350380.64 | 214626.05 | 214626.05 | 214626.05 | 316547.48 | 316547.48 | 746973.86 | 746973.86 | 746973.86 | 758156.57 | 758156.57 | 441609.09 | 441609.09 | 441609.09 | 441609.09 | 441609.09 | 441609.09 | 432813.02 | 879655.83 | 1011247.17 | 578434.15 | 623753.44 | 623753.44 | 623753.44 | 374626.43 | 374626.43 | 374626.43 | 374626.43 |  | 16348009.42
Total | 536534.53 | 536534.53 | 566751.35 | 566751.35 | 566751.35 | 566751.35 | 566751.35 | 430996.76 | 430996.76 | 430996.76 | 532918.19 | 532918.19 | 963344.57 | 963344.57 | 963344.57 | 974527.28 | 974527.28 | 657979.8 | 657979.8 | 657979.8 | 657979.8 | 657979.8 | 657979.8 | 649183.73 | 1096026.54 | 1227617.88 | 794804.86 | 840124.15 | 840124.15 | 840124.15 | 590997.14 | 590997.14 | 590997.14 | 590997.14 |  | 23704613.56
Phase 1 - square smaller block - 33.15%
Phase 2 - L Shape block - 66.85%

## Cashflow
Cashflow
SA1 Development
IP Construction
Jack Rees
Phasing
Phase | Total | Start | End | Difference in days | Difference in weeks | Difference in months
1 | 8111572.65 | 2023-04-01 | 2024-08-01 | 488 | 69.7143 | 17.4286
2 | 15593040.97 | 2024-04-01 | 2026-01-01 | 640 | 91.4286 | 22.8571
Month | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01
Phase 1 | 536534.53 | 536534.53 | 566751.35 | 566751.35 | 566751.35 | 566751.35 | 566751.35 | 430996.76 | 430996.76 | 430996.76 | 532918.19 | 532918.19 | 316547.48 | 316547.48 | 316547.48 | 448138.87 | 448138.87
Phase 2 | [12 empty] | 646797.09 | 646797.09 | 646797.09 | 526388.41 | 526388.41 | 657979.8 | 657979.8 | 657979.8 | 657979.8 | 657979.8 | 657979.8 | 649183.73 | 1096026.54 | 1227617.88 | 794804.86 | 840124.15 | 840124.15 | 840124.15 | 590997.14 | 590997.14 | 590997.14 | 590997.14 | Handover
| 536534.53 | 536534.53 | 566751.35 | 566751.35 | 566751.35 | 566751.35 | 566751.35 | 430996.76 | 430996.76 | 430996.76 | 532918.19 | 532918.19 | 963344.57 | 963344.57 | 963344.57 | 974527.28 | 974527.28 | 657979.8 | 657979.8 | 657979.8 | 657979.8 | 657979.8 | 657979.8 | 649183.73 | 1096026.54 | 1227617.88 | 794804.86 | 840124.15 | 840124.15 | 840124.15 | 590997.14 | 590997.14 | 590997.14 | 590997.14
| 536534.53 | 1073069.06 | 1639820.41 | 2206571.76 | 2773323.11 | 3340074.46 | 3906825.81 | 4337822.57 | 4768819.33 | 5199816.09 | 5732734.28 | 6265652.47 | 7228997.04 | 8192341.61 | 9155686.18 | 10130213.46 | 11104740.74 | 11762720.54 | 12420700.34 | 13078680.14 | 13736659.94 | 14394639.74 | 15052619.54 | 15701803.27 | 16797829.81 | 18025447.69 | 18820252.55 | 19660376.7 | 20500500.85 | 21340625 | 21931622.14 | 22522619.28 | 23113616.42 | 23704613.56
| 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01
| 536534.53 | 1073069.06 | 1639820.41 | 2206571.76 | 2773323.11 | 3340074.46 | 3906825.81 | 4337822.57 | 4768819.33 | 5199816.09 | 5732734.28 | 6265652.47 | 7228997.04 | 8192341.61 | 9155686.18 | 10130213.46 | 11104740.74 | 11762720.54 | 12420700.34 | 13078680.14 | 13736659.94 | 14394639.74 | 15052619.54 | 15701803.27 | 16797829.81 | 18025447.69 | 18820252.55 | 19660376.7 | 20500500.85 | 21340625 | 21931622.14 | 22522619.28 | 23113616.42 | 23704613.56 | Handover

## Cashflow - Phase 1
Cashflow
SA1 Development
IP Construction
Jack Rees
Phasing
Phase | Total | Start | End | Difference in days | Difference in weeks | Difference in months
1 | 8111572.65 | 2023-04-01 | 2024-08-01 | 488 | 69.7143 | 17.4286
Month | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01
Phase 1 | 536534.53 | 536534.53 | 566751.35 | 566751.35 | 566751.35 | 566751.35 | 566751.35 | 430996.76 | 430996.76 | 430996.76 | 532918.19 | 532918.19 | 316547.48 | 316547.48 | 316547.48 | 448138.87 | 448138.87
| 536534.53 | 536534.53 | 566751.35 | 566751.35 | 566751.35 | 566751.35 | 566751.35 | 430996.76 | 430996.76 | 430996.76 | 532918.19 | 532918.19 | 316547.48 | 316547.48 | 316547.48 | 448138.87 | 448138.87
| 536534.53 | 1073069.06 | 1639820.41 | 2206571.76 | 2773323.11 | 3340074.46 | 3906825.81 | 4337822.57 | 4768819.33 | 5199816.09 | 5732734.28 | 6265652.47 | 6582199.95 | 6898747.43 | 7215294.91 | 7663433.78 | 8111572.65
| 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01
| 536534.53 | 1073069.06 | 1639820.41 | 2206571.76 | 2773323.11 | 3340074.46 | 3906825.81 | 4337822.57 | 4768819.33 | 5199816.09 | 5732734.28 | 6265652.47 | 6582199.95 | 6898747.43 | 7215294.91 | 7663433.78 | 8111572.65

## Cashflow - Phase 2
Cashflow
SA1 Development
IP Construction
Jack Rees
Phasing
Phase | Total | Start | End | Difference in days | Difference in weeks | Difference in months
2 | 15593040.97 | 2024-04-01 | 2026-01-01 | 640 | 91.4286 | 22.8571
Month | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01
Phase 2 | 646797.09 | 646797.09 | 646797.09 | 526388.41 | 526388.41 | 657979.8 | 657979.8 | 657979.8 | 657979.8 | 657979.8 | 657979.8 | 649183.73 | 1096026.54 | 1227617.88 | 794804.86 | 840124.15 | 840124.15 | 840124.15 | 590997.14 | 590997.14 | 590997.14 | 590997.14 | Handover
| 646797.09 | 646797.09 | 646797.09 | 526388.41 | 526388.41 | 657979.8 | 657979.8 | 657979.8 | 657979.8 | 657979.8 | 657979.8 | 649183.73 | 1096026.54 | 1227617.88 | 794804.86 | 840124.15 | 840124.15 | 840124.15 | 590997.14 | 590997.14 | 590997.14 | 590997.14
| 646797.09 | 1293594.18 | 1940391.27 | 2466779.68 | 2993168.09 | 3651147.89 | 4309127.69 | 4967107.49 | 5625087.29 | 6283067.09 | 6941046.89 | 7590230.62 | 8686257.16 | 9913875.04 | 10708679.9 | 11548804.05 | 12388928.2 | 13229052.35 | 13820049.49 | 14411046.63 | 15002043.77 | 15593040.91
| 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01
| 646797.09 | 1293594.18 | 1940391.27 | 2466779.68 | 2993168.09 | 3651147.89 | 4309127.69 | 4967107.49 | 5625087.29 | 6283067.09 | 6941046.89 | 7590230.62 | 8686257.16 | 9913875.04 | 10708679.9 | 11548804.05 | 12388928.2 | 13229052.35 | 13820049.49 | 14411046.63 | 15002043.77 | 15593040.91 | Handover

## Client returns
Client Returns
Jack Rees
Cash Flow (long-term) - Client Returns
Completion |  | Year | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 2055 | 2056 | 2057 | 2058 | 2059 | 2060 | 2061 | 2062
Outgoings | Cost £/ anually | Outgoings | 4768819.33 | 9086855.98 | 9734002.61 | 948043.27 | 357046.13 | 357046.13 | 357046.13 | 357046.13 | 357046.13 | 357046.13 | 357046.13 | 357046.13 | 357046.13 | 357046.13 | 357046.13 | 357046.13 | 357046.13 | 357046.13 | 357046.13 | 357046.13 | 357046.13 | 357046.13 | 357046.13 | 357046.13 | 357046.13 | 357046.13 | 357046.13 | 357046.13 | 357046.13 | 357046.13 | 357046.13 | 357046.13 | 357046.13 | 357046.13 | 357046.13 | 357046.13 | 357046.13 | 357046.13 | 357046.13 | 357046.13
Energy | 70000 | Incomings |  | 144400 | 433200 | 1010662 | 1010662 | 1010662 | 1010662 | 1010662 | 1010662 | 1010662 | 1010662 | 1010662 | 1010662 | 1010662 | 1010662 | 1010662 | 1010662 | 1010662 | 1010662 | 1010662 | 1010662 | 1010662 | 1010662 | 1010662 | 1010662 | 1010662 | 1010662 | 1010662 | 1010662 | 1010662 | 1010662 | 1010662 | 1010662 | 1010662 | 1010662 | 1010662 | 1010662 | 1010662 | 1010662 | 1010662
Maintenance | 237046.13 | Annual Total incoming/ outgoings | -4768819.33 | -8942455.98 | -9300802.61 | 62618.73 | 653615.87 | 653615.87 | 653615.87 | 653615.87 | 653615.87 | 653615.87 | 653615.87 | 653615.87 | 653615.87 | 653615.87 | 653615.87 | 653615.87 | 653615.87 | 653615.87 | 653615.87 | 653615.87 | 653615.87 | 653615.87 | 653615.87 | 653615.87 | 653615.87 | 653615.87 | 653615.87 | 653615.87 | 653615.87 | 653615.87 | 653615.87 | 653615.87 | 653615.87 | 653615.87 | 653615.87 | 653615.87 | 653615.87 | 653615.87 | 653615.87 | 653615.87
Staff | 30000 | Client money back | -4768819.33 | -13711275.31 | -23012077.92 | -22949459.19 | -22295843.32 | -21642227.45 | -20988611.58 | -20334995.71 | -19681379.84 | -19027763.97 | -18374148.1 | -17720532.23 | -17066916.36 | -16413300.49 | -15759684.62 | -15106068.75 | -14452452.88 | -13798837.01 | -13145221.14 | -12491605.27 | -11837989.4 | -11184373.53 | -10530757.66 | -9877141.79 | -9223525.92 | -8569910.05 | -7916294.18 | -7262678.31 | -6609062.44 | -5955446.57 | -5301830.7 | -4648214.83 | -3994598.96 | -3340983.09 | -2687367.22 | -2033751.35 | -1380135.48 | -726519.61 | -72903.74 | 580712.13
Security | 20000
Total | 357046.13
Completion
Incomings | Cost £/ anually
Solar panel savings | 21262
Retail rent | 186000
Resindetial rent | 803400
Total | 1010662
Phase one
Outgoings | Cost £/ anually
Energy | 70000
Maintenance | 237046.13
Staff | 30000
Security | 20000
Total | 357046.13
Phase one
Incomings | Cost £/ anually
Café Rent | 30000
Resindential Rent | 403200
Total | 433200