Leonard Betton

1910735

Implementation Plan

BMSP 5022

Contents

Contents 											1

Executive Summary 									2

Introduction 										3

Objective 											3

Implementation Strategy 								3

Risk Analysis 										4

Resource and Tools 									4

Monitor and Evaluate 									5

Conclusion 										5

Appendix 1.										 6

Appendix 2.										 9

Appendix 3 										12

References	 										13

Executive Summary

This report demonstrates the need for an Implementation plan when conducting a new placement.

It explored the goals and objectives of the plan and included the use of the Ghant chart to monitor the plans activities.

It examined the need for a risk analysis and discussed the resources needed to complete the task.

The placement success was then measured and the evaluation process discussed.

Introduction

Canolfan Carwyn is a gym based in Drefach in the Gwendraeth Valley. Research states that this area houses a population of approximately one hundred and ninety thousand people. The figure of residents over the age of fifty is approximately forty-six thousand five hundred.

These statistics also suggest that the age group of 45-64 years show a low figure in exercise participation. The figures also show that this age group show a larger score of people with a body mass index (BMI) of 25+ as compared with the 16-44 group and the over 65 group. (StatsWales, 2019).

These alarming facts have supported the need for a way to encourage fitness in the over 50 group whilst acknowledging their fitness levels at the present time and discovering a way to keep their interest in continuing to exercise (Staying Motivated to Exercise: Tips for Older Adults, 2020).

Objectives

The main aim of this project is to produce an implementation plan which will be used for an exercise programme for individuals who wish to attend a course at Canolfan Carwyn. My role will be as instructor and project manager.

The plan will assess the need for a new fitness class at the Centre, it will look at the reasons for introducing such a class and examine what it hopes to achieve by its implementation.

An implementation plan is essential for a business as it gives a roadmap of the procedures that will be followed. It also allows stakeholders to see the procedure and allows everyone to see what position the plan is at any given time (Kumar, 2023).

I hope to gain further experience in constructing and adapting a fitness plan for a specific age group with varied disabilities. This will help me achieve my future goal to work with individuals who have barriers to exercise and helping them overcome them so that they can lead a normal healthy lifestyle going forward.

Implementation Strategy

This implementation plan aims to deliver a fitness class to individuals over the age of fifty years old. Research suggests that the most important factor for exercise for the over 50’s is that it should be focussing on muscle building whilst being kinder to joints, and the emphasis should be the cardiovascular system, promoting a strong heart and lungs.

(updated, 2022).

I plan to devise a programme over five weeks which will take these individuals, of varying abilities to a position where they can perform daily exercise to enhance their lives, this I plan to do whilst retaining their motivation by keeping it challenging and enjoyable.

I will draw on my experience of being a Martial Arts Instructor for forty three years and deliver a programme which considers both their fitness levels and disabilities should they have them.

I will begin by completing a pre assessment evaluation of my current skills, which will enable me to have a benchmark on my skills when starting this programme of study. (Appendix.1)

Risk Analysis

Risk management can be defined as the process in which potential risks can be identified, so that actions to reduce them can be sought in anticipation of an attack (U.S. Sports Academy, 2008).

It is essential to complete a risk analysis before commencing any new programme to ensure the safety of each individual student and staff . This analysis must be completed by the venue host and the course tutor. (Appendix 2).

Resources and Tools

The resources needed for this programme include the use of the gym at Canolfan Carwyn.

Research states that a Ghant Chart is a useful management tool, it can be used to plan schedule and monitor the project, which improves the overall running of the task. The ghant chart allows project managers and supervisors to view the tasks and progress easily. This research suggests is more likely to allow completion of the project on time (Shweta & Bottorff, 2022).

The tasks needing to be completed were listed and the ghant chart drawn up (Appendix 3).

Research suggests that music helps motivate an individual to exercise before and during a session (Ballmann, 2021). It is essential to include uplifting music to accomplish this.

Variety of exercise is important because it adds interest to the routine and prevents boredom. It also ensures that all muscle groups are being exercised on alternate sessions to allow the worked muscle to recover.(Magat, 2020).

The plan will include different exercise methods including using stretch bands for light muscle building and using body weight as a natural resistance. The static weight machines will be used for toning, and running machines to build up cardiovascular fitness. This programme will also build in stretching exercises as research states that it can be beneficial to individuals as the begin to age, it increases the motion range and encourages flexibility (Felman, 2023).

Monitor and Evaluate

It is essential to monitor and evaluate a new programme as it demonstrates whether the routine is effective or if it needs to be altered to increase the benefits (Verma, 2017).

In career development it helps to measure personal strengths and weaknesses. It allows skill management by monitoring the skills that is required for each task.

Checking the attendance of students is a method of monitoring participation, encouraging feedback is an excellent way to discover individual opinion on the overall enjoyment of the programme.

Research suggests that a beginner would need to exercise at least two to three times a week to gain the maximum benefits (Better Health Channel, 2022).

Conclusion

This report aimed to complete an implementation plan for a placement at Canolfan Carwyn.

It examined the need for a risk assessment prior to beginning the programme, and highlighted the reason for the chosen age group. It explored the resources and tools required to plan the programme, and it emphasised the importance of the Ghant chart in meeting targets. It concluded by examining the reasoning behind monitoring and evaluating a programme such as this.

Appendix 1

| I have a commitment to life-long learning | X |  |  |  |
| --- | --- | --- | --- | --- |
| Example: I am totally committed to continually learning new skills to help in my development as a coach. |  |  |  |  |
| I am committed to supporting and encouraging others with life-long learning | X |  |  |  |
| Example: My career path has led me to teach students in the martial arts and I continue to do so. |  |  |  |  |
| I am innovative and adaptable, proactive rather than reactive |  |  | X |  |
| Example: I am innovative and adaptable but am also proactive and due to the nature of my work I am also reactive when needing to be. |  |  |  |  |
| I am an engaging and dynamic communicator (written) |  |  |  | X |
| Example: I am a dyslexic student and so this by far is my weakest point. |  |  |  |  |
| I am an engaging and dynamic communicator (oral) | X |  |  |  |
| Example: I communicate very well with people from all walks of life. |  |  |  |  |
| I am an effective networker |  |  |  | X |
| Example: I need to enhance my skills as a networker as there could always be missed opportunities if I don’t address this skill. |  |  |  |  |
| I am an effective facilitator | x |  |  |  |
| Example: I am able to break down challenges into easier sections to make learning more effective. |  |  |  |  |
| I work well in cooperation with others |  | X |  |  |
| Example: I have previously worked in a factory situation and so am familiar and at ease working with a team. |  |  |  |  |
| I am a well-practiced and effective active listener | X |  |  |  |
| Example: I pride myself on always listening to students opinions as I believe that everyone has something important to say. |  |  |  |  |
| I can organize myself and manage my time effectively |  |  | X |  |
| Example: I need to work on this skill as I often find myself trying to do more jobs than I have time to do. |  |  |  |  |
| I understand how to act as a responsible citizen | X |  |  |  |
| Example: I pride myself on being a trustworthy, honest individual, who respects authority and my elders. |  |  |  |  |
| I have a clear vision of forthcoming change and how to act to realise a sustainable future | X |  |  |  |
| Example: I am familiar with the problems we as a world are facing regarding sustainability and I realise how fragile our world has become. |  |  |  |  |
| I feel competent in leading on change for social, environmental and/or economic benefit |  |  | X |  |
| Example: I understand the need for change and can practice it effectively myself. I feel I need to be more pro active in taking the lead. |  |  |  |  |
| I feel comfortable speaking openly about my values |  | X |  |  |
| Example: I do not have any issues with openly speaking about my values. |  |  |  |  |
| I can lead with integrity driven by my own values | X |  |  |  |
| Example: I have always lived my life with integrity and honesty as my driving force. |  |  |  |  |

Appendix 2

| PLACEMENT RISK ASSESSMENT (Refer to PL1d - Placement Risk Assessment Guidance to help complete the following section) |  |  |  |  |
| --- | --- | --- | --- | --- |
| RISK FACTOR | RISK INDICATORS | RATING PROFILE | ACTIONS REQUIRED TO REDUCE RISK | ACTION COMPLETED (DATE) |
| STUDENT PLACEMENT DETERMINATION |  |  |  |  |
| QUESTION |  | YES / NO | FURTHER ACTION NEEDED | ACTION COMPLETED (DATE) |
| Is a site visit required before the placement is authorised? |  |  |  |  |
| Have all outstanding actions been completed? |  |  |  |  |
| Are the risks tolerable and the placement can be approved? |  |  |  |  |

Appendix 3

References

Ballmann, C. G. (2021). The Influence of Music Preference on Exercise Responses and

Performance: A Review. Journal of Functional Morphology and Kinesiology, 6(2), 33.

https://doi.org/10.3390/jfmk6020033

Better Health Channel. (2022, July 11). Resistance training – health benefits. Better Health

Channel. https://www.betterhealth.vic.gov.au/health/healthyliving/resistance-training-health-

benefits

Felman, A. (2023, September 29). Stretching exercises for seniors: Back, neck, and more.

Www.medicalnewstoday.com. https://www.medicalnewstoday.com/articles/stretching-

exercises-for-seniors#:~:text=Stretching%20may%20help%20older%20adults

Kumar, A. (2023, March 9). What is Implementation Planning and Why is it Important? Emeritus Online Courses. https://emeritus.org/blog/project-management-what-is-implementation-planning/

Magat, B. (2020, August 25). The Importance of Variety in Exercise Programs.

Www.uhhospitals.org. https://www.uhhospitals.org/blog/articles/2020/08/the-importance-of-

variety-in-creating-your-exercise-program

Shweta, & Bottorff, C. (2022, August 10). What Is A Gantt Chart? Here Are The Basics. Forbes Advisor. https://www.forbes.com/advisor/business/software/what-is-a-gantt-chart/

StatsWales. (2019). Population Estimates by Local Authority and Age. Gov.wales. https://statswales.gov.wales/Catalogue/Population-and-Migration/Population/Estimates/Local-Authority/populationestimates-by-localauthority-age

Staying Motivated to Exercise: Tips for Older Adults. (2020, April 3). National Institute on Aging. https://www.nia.nih.gov/health/exercise-and-physical-activity/staying-motivated-exercise-tips-older-adults#:~:text=The%20best%20way%20to%20stay%20motivated%20is%20to

updated, L. G. last. (2022, May 25). Best exercise for over 50s. Fitandwell.com. https://www.fitandwell.com/features/exercising-over-50

U.S. Sports Academy. (2008, March 14). Introducing a Risk Assessment Model for Sport Venues. The Sport Journal. https://thesportjournal.org/article/introducing-a-risk-assessment-model-for-sport-venues/

Verma, E. (2017, May 31). How To Measure The Effectiveness Of Corporate Training.

Simplilearn.com; Simplilearn. https://www.simplilearn.com/how-to-measure-effectiveness-

corporate-training-article