## Slide 1: Leading and implementing workplace change
The Eight Steps of Change – Adapted from Kotter, J. P. (1995). Leading Change: Why Transformation Efforts Fail. Harvard Business Review OnPoint (March-April), 1-10.
.

## Slide 2: The Eight Steps of Change
Establish a sense of urgency
Create a coalition
Develop a clear vision
Share the vision
Empower people to clear obstacles
Secure short-term wins
Consolidate and keep moving
Anchor the change
Kotter, J. P. (1995). Leading Change: Why Transformation Efforts Fail. Harvard Business Review OnPoint (March-April), 1-10.

## Slide 3: Establish a sense of urgency
During this stage, the change agents need to be focused on trying to sell the need for change within the organisation. Peoples attention need to be got on the urgency of the situation and they need to be fed with stories, data, etc about for example harmful events, waste of time/resources, etc to emphasis the need for change.

## Slide 4: Create a coalition
Build the team that will manage the change and formalise it. This should be proven leaders who can guide and drive the required change.
They can be people with formal power, informal opinions, professionals from outside the organisation with experience who are being consulted, etc.
You need “Management skills to control the process and the details” and “leadership skills to drive the change with a clear vision”

## Slide 5: Develop a clear vision and strategy
The leaders here have a responsibility to develop and clarify the vision and the strategy to be used to implement the change. The core values, set believes, expectations, etc that has to be changed has to be clearly set and communicated to the entire organisation. These values have to be translated into expected behaviours.
These changes have to be consistent with the vision, mission and core values of the organisation.

## Slide 6: Share the vision
During this stage, we have to keep people talking and also try to empower them through training and other methods on the change programme. The change leaders should encourage discussion, debates, arguments, disagreements, etc.
Employees have to be educated and trained on the new vision.

## Slide 7: Share the vision
It is during this stage that those interesting in resisting the change will likely emerge more powerfully.
Engagement with them may help you identify other problems that needs to be solved first before the change is implemented or clarify the actual problem.
They may be right and their questions may help the organisation strengthen and improve the change.

## Slide 8: Empower others to act
Here, employees have to be trained with the desired skills and attitude to implement the change.
Personally within teams with the vision and skills to coach others have to be identified and given different responsibilities.
Continue managing those resisting the change.

## Slide 9: Secure short-term wins
A short-term win is an organizational improvement that can be implemented in 6 to 18 months. They must be visible and clearly related to the change effort. They create difficulties with resisters to block further change.
They are important as they help to generate momentum, eliminate discouragement, and help to provide evidence to resisters of the change that the vision was valid.
They are often not the desired location, but without them, we cant achieve the organisation change effort.

## Slide 10: Consolidate and keep moving
Here, you reaffirm the vision, identify and celebrate successes and accomplishments, evaluate your training sessions and learn from them, orient new employees of the change process, current stage and success.
Communicate, communicate,

## Slide 11: Anchor the Changes in Corporate Culture
Here the change should become part of the organisational culture and the values behind the change effort must be visible in the day to day work of the organisation. The change must be seen in every aspect of the organisation.
You can talk about the progress at every opportunity, include its ideals and values when hiring and training new staff, public recognise and reward those who contributed most in implementing the change programme