## Lists (hidden)
Cyber & Technology | People & Behaviour | Operational | Physical & Environmental | Financial | Strategic
Cyber Security | Human Error | Process Failure | Physical Security | Financial Fraud | Strategic
Data Privacy | Insider Threat | Supply Chain | Natural Disaster | Budget Overrun | Political / Regulatory
System Failure | Social Engineering | Business Continuity | Environmental | Economic | Third Party / Vendor
Software/Hardware | Reputational | Compliance / Legal | Health & Safety

## Risk Register
Risk Management Register
Scenario: FinSecure Bank (Financial System) Group: 3
Risk ID | Hazard / Risk Description | Who is at Risk | Category | Sub Category | Likelihood (1–5) | Severity (1–5) | Risk Score (L × S) | Risk Level | Existing Controls | Additional Controls Needed | Responsible Person | Target Date | Residual Likelihood (1–5) | Residual Severity (1–5) | Residual Risk Score | Residual Risk Level | Status
R1 | Customer data breach | Customers, Bank | Technical | Confidentiality | 5 | 5 | 25 | Critical | Firewall, Antivirus | Encryption, DLP, Security Audits | IT Security Manager | 30/09/2026 | 2 | 5 | 10 | High | Open
R2 | Phishing attack | Customers, Employees | Technical | Social Engineering | 4 | 5 | 20 | Critical | Email Filter | MFA, Phishing Awareness Training | IT Security Manager | 30/09/2027 | 2 | 4 | 8 | Medium | Open
R3 | Malware/Ransomware infection | Bank Systems | Technical | Malware | 4 | 5 | 20 | Critical | Antivirus | EDR, Offline Backups | IT Administrator | 30/09/2028 | 2 | 4 | 8 | Medium | Open
R4 | SQL Injection attack | Database | Technical | Application Security | 3 | 5 | 15 | Critical | Input Validation | Parameterized Queries, Secure Code Reviews, WAF | Software Development Manager | 30/09/2029 | 1 | 5 | 5 | Medium | Open
R5 | DDoS attack | Online Banking Users | Technical | Network Security | 3 | 5 | 15 | Critical | Firewall | DDoS Protection, Load Balancer | Network Administrator | 30/09/2030 | 2 | 4 | 8 | Medium | Open
R6 | Weak passwords | Customers, Employees | Technical | Authentication | 4 | 3 | 12 | High | Password Policy | MFA, Strong Password Policy | IT Security Manager | 30/09/2031 | 2 | 2 | 4 | Low | Open
R7 | Insider threat | Customers, Bank | Operational | Human Resources | 3 | 5 | 15 | Critical | Access Permissions | RBAC, Activity Monitoring | HR & IT Security Manager | 30/09/2032 | 2 | 4 | 8 | Medium | Open
R8 | System failure | Customers, Employees | Operational | Infrastructure | 3 | 5 | 15 | Critical | UPS, Backup Servers | Disaster Recovery, High Availability | Infrastructure Manager | 30/09/2033 | 2 | 3 | 6 | Medium | Open
R9 | Third-party vendor compromise | Bank, Customers | Strategic | Vendor Management | 2 | 4 | 8 | Medium | Vendor Contracts | Vendor Security Assessments | Procurement Manager | 30/09/2034 | 1 | 3 | 3 | Low | Open
R10 | Regulatory non-compliance | Bank | Compliance | GDPR / Financial Regulations | 2 | 5 | 10 | High | Existing Policies | Compliance Audits, Staff Training | Compliance Officer | 30/09/2035 | 1 | 4 | 4 | Low | Open
RISK LEVEL LEGEND
Critical (15–25) |  |  |  | Immediate action — stop or redesign activity
High (10–14) |  |  |  | Urgent controls needed — inform senior management
Medium (5–9) |  |  |  | Monitor closely — additional controls required
Low (1–4) |  |  |  | Acceptable — review periodically

## Risk Heatmap
RISK SCORE HEATMAP - Likelihood × Severity
Use this matrix to identify the risk level for any combination of Likelihood and Severity.
SEVERITY →
← LIKELIHOOD |  | 1 Negligible | 2 Minor | 3 Moderate | 4 Major | 5 Catastrophic
| 5 – Almost Certain | 5 Medium | 10 High | 15 Critical | 20 Critical | 25 Critical
| 4 – Likely | 4 Low | 8 Medium | 12 High | 16 Critical | 20 Critical
| 3 – Possible | 3 Low | 6 Medium | 9 Medium | 12 High | 15 Critical
| 2 – Unlikely | 2 Low | 4 Low | 6 Medium | 8 Medium | 10 High
| 1 – Rare | 1 Low | 2 Low | 3 Low | 4 Low | 5 Medium

## Action Tracker
RISK CONTROL ACTION TRACKER
Risk ID | Risk Description | Action Required | Priority | Responsible Person | Start Date | Target Date | Completion Date | Evidence / Notes | Status
R1 | Customer data breach | Implement encryption, DLP and security audits | Critical | IT Security Manager | 21/07/2026 | 30/09/2026 |  | Encryption enabled, audit reports | In Progress
R2 | Phishing attack | Deploy MFA and phishing awareness training | Critical | IT Security Manager | 21/07/2027 | 30/09/2027 |  | Training records, MFA logs | In Progress
R3 | Malware/Ransomware | Deploy EDR, patch systems and backup data | Critical | IT Administrator | 21/07/2028 | 30/09/2028 |  | Backup reports, EDR dashboard | In Progress
R4 | SQL Injection | Secure code review and implement parameterized queries | Critical | Software Development Manager | 21/07/2029 | 30/09/2029 |  | Code review results | In Progress
R5 | DDoS attack | Implement DDoS protection and load balancing | Critical | Network Administrator | 21/07/2030 | 30/09/2030 |  | Network monitoring logs | Planned
R6 | Weak passwords | Enforce password policy and MFA | High | IT Security Manager | 21/07/2031 | 30/09/2031 |  | Password policy documentation | In Progress
R7 | Insider threat | Implement RBAC and activity monitoring | Critical | HR & IT Security Manager | 21/07/2032 | 30/09/2032 |  | Access review reports | Planned
R8 | System failure | Implement disaster recovery and redundancy | Critical | Infrastructure Manager | 21/07/2033 | 30/09/2033 |  | DR testing reports | Planned
R9 | Third-party vendor compromise | Conduct vendor security assessments | Medium | Procurement Manager | 21/07/2034 | 30/09/2034 |  | Vendor assessment reports | Planned
R10 | Regulatory non-compliance | Perform compliance audits and staff training | High | Compliance Officer | 21/07/2035 | 30/09/2035 |  | Audit reports and training records | In Progress

## Guidance Notes
HOW TO USE THIS RISK MANAGEMENT WORKBOOK
SHEETS OVERVIEW
| Risk Register | Complete one row per identified hazard. Risk Score and Risk Level are auto-calculated.
| Risk Heatmap | 5×5 colour-coded matrix showing how Likelihood and Severity combine into a risk level.
| Action Tracker | Log all control actions, assign responsibility, and track completion.
| Guidance Notes | This page — definitions and instructions.
LIKELIHOOD SCALE
| 1 – Rare | Could happen but probably never will (once every 5+ years)
| 2 – Unlikely | Not expected but possible (once every 2–5 years)
| 3 – Possible | Could occur at some time (once per year)
| 4 – Likely | Will probably occur in most circumstances (monthly)
| 5 – Almost Certain | Expected to occur in most circumstances (weekly/daily)
SEVERITY SCALE
| 1 – Negligible | No impact; minor inconvenience
| 2 – Minor | Small impact; easily recoverable
| 3 – Moderate | Noticeable impact; some recovery effort needed
| 4 – Major | Significant impact; difficult to recover from
| 5 – Catastrophic | Severe or irreversible impact
RISK LEVEL GUIDE
| Low (1–4) | Monitor and review periodically; standard controls sufficient
| Medium (5–9) | Manage through routine procedures; monitor more frequently
| High (10–14) | Urgent action required; inform responsible person immediately
| Critical (15–25) | Stop or redesign activity until risk is reduced to acceptable level
RISK CATEGORIES
| Cyber & Technology | Cyber Security, Data Privacy, System Failure, Software/Hardware
| People & Behaviour | Human Error, Insider Threat, Social Engineering, Reputational
| Operational | Process Failure, Supply Chain, Business Continuity, Compliance / Legal
| Physical & Environmental | Physical Security, Natural Disaster, Environmental, Health & Safety
| Financial | Financial Fraud, Budget Overrun, Economic
| Strategic | Strategic, Political / Regulatory, Third Party / Vendor
TIPS FOR STUDENTS
| Research first | Identify risks through research before filling in the register
| Be specific | Describe the hazard clearly — avoid vague terms like 'something goes wrong'
| Think about controls | Consider both existing controls and what additional ones are needed
| Residual risk | After controls are applied, re-score Likelihood and Severity to get residual risk
| Hierarchy of controls | Eliminate > Substitute > Engineering > Administrative > PPE