## Sheet1
Risk ID | Asset at Risk | Risk Description | Threat Source | Vulnerability | Likelihood | Impact | Risk Level | Treatment / Controls | Risk Owner | Review Date
R-01 | Customer Personal Data | Data breach due to weak passwords | External attacker | Weak password habits; no MFA | High | High | Critical | Enforce MFA, Password Policy, monitoring logs | IT Manager | 30 days
R-02 | Cloud Storage | Data exposure due to cloud misconfiguration | IT staff error | No cloud security baseline | High | High | Critical | Cloud Hardening Guide, monthly audits | Cloud Administrator | 15 days
R-03 | Wireless Network | Unauthorised access via insecure Wi-Fi | Nearby attacker | Weak encryption | Medium | High | High | WPA3 upgrade, network segmentation, log monitoring | Network Engineer | 45 days
R-04 | BYOD Devices | Malware infection or data leakage through personal devices | Employees / malicious apps | No MDM, unregulated personal devices | High | Medium | High | BYOD agreement | Security Lead | 30 days
R-05 | Remote Work Systems | Data interception on public/unsafe Wi-Fi | Man-in-the-middle attackers | No VPN enforcement | Medium | High | High | Mandatory VPN, encryption, secure Wi-Fi rules | IT Security Officer | 60 days
R-06 | Admin Accounts | Privilege misuse or incorrect changes | Internal admin | No privileged access management | Low | High | High | Admin charter, SoD | Head of IT | 30 days
R-07 | Third-Party Cloud Providers | Provider fails GDPR obligations | External vendor | No SLA; no compliance clauses | Medium | High | High | SLA with GDPR clauses, audit rights | Compliance Officer | 30 days