## DT
Library & Community Hwb - UWTSD
Line | Name | Duration | Month -9 |  |  |  |  | Month -8 |  |  |  | Month -7 |  |  |  | Month -6 |  |  |  |  | Month -5 |  |  |  | Month -4 |  |  |  | Month -3 |  |  |  |  | Month -2 |  |  |  | Month -1 |  |  |  | Month 1 |  |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  | Month 6 |  |  |  |  | Month 7 |  |  |  | Month 8 |  |  |  | Month 9 |  |  |  |  | Month 10 |  |  |  | Month 11 |  |  |  | Month 12 |  |  |  |  | Month 13 |  |  |  | Month 14 |  |  |  | Month 15 |  |  |  |  | Month 16 |  |  |  | Month 17 |  |  |  | Month 18 |  |  |  |  | Month 19 |  |  |  | Month 20 |  |  |  | Month 21
|  |  | 2023-10-01 |  |  |  |  | 2023-11-01 |  |  |  | 2023-12-01 |  |  |  | 2024-01-01 |  |  |  |  | 2024-02-01 |  |  |  | 2024-03-01 |  |  |  | 2024-04-01 |  |  |  |  | 2024-05-01 |  |  |  | 2024-06-01 |  |  |  | 2024-07-01 |  |  |  |  | 2024-08-01 |  |  |  | 2024-09-01 |  |  |  |  | 2024-10-01 |  |  |  | 2024-11-01 |  |  |  | 2024-12-01 |  |  |  |  | 2025-01-01 |  |  |  | 2025-02-01 |  |  |  | 2025-03-01 |  |  |  |  | 2025-04-01 |  |  |  | 2025-05-01 |  |  |  | 2025-06-01 |  |  |  |  | 2025-07-01 |  |  |  | 2025-08-01 |  |  |  | 2025-09-01 |  |  |  |  | 2025-10-01 |  |  |  | 2025-11-01 |  |  |  | 2025-12-01 |  |  |  |  | 2026-01-01 |  |  |  | 2026-02-01 |  |  |  | 2026-03-01
|  |  | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 2 | 9 | 16 | 23 | 30
0 | Library & Community Hwb - UWTSD (Riba Stages 0-7) | 128 Weeks
1 | Stage 0 - Strategic Definition | 1 Week | bar: 2023-10-01 2
2 | Issues of masterplan and client requiremtns | 1 Week | bar: 2023-10-01 2
3 | EIRS | 1 Week | bar: 2023-10-01 2
4 | Project Risk Assesment | 1 Week | bar: 2023-10-01 2
5 | Project Budget Plan | 1 Week | bar: 2023-10-01 2
6 | Site Survey information | 1 Week | bar: 2023-10-01 2
7 | Stage 1 - Preparation & Brief | 16 Weeks | bar: 2023-10-01 2 to 2024-01-01 15
8 | Prepare Project Brief | 5 Weeks | bar: 2023-10-01 2 to 2023-10-01 30
9 | Prepare project programme | 11 Weeks | bar: 2023-11-01 6 to 2024-01-01 15
10 | Sustainability Outcomes | 11 Weeks | bar: 2023-11-01 6 to 2024-01-01 15
11 | Project outocmes | 11 Weeks | bar: 2023-11-01 6 to 2024-01-01 15
12 | Quality objectives | 11 Weeks | bar: 2023-11-01 6 to 2024-01-01 15
13 | Project execution plan | 11 Weeks | bar: 2023-11-01 6 to 2024-01-01 15
14 | Site information and surveys | 11 Weeks | bar: 2023-11-01 6 to 2024-01-01 15
15 | Feasability Study | 11 Weeks | bar: 2023-11-01 6 to 2024-01-01 15
16 | Stage 2 - Conecpt Design | 10 Weeks | bar: 2024-01-01 22 to 2024-03-01 25
17 | Concept design | 10 Weeks | bar: 2024-01-01 22 to 2024-03-01 25
18 | Consult with planning | 10 Weeks | bar: 2024-01-01 22 to 2024-03-01 25
19 | Cost plan | 10 Weeks | bar: 2024-01-01 22 to 2024-03-01 25
20 | Project strategies | 10 Weeks | bar: 2024-01-01 22 to 2024-03-01 25
21 | Design review | 10 Weeks | bar: 2024-01-01 22 to 2024-03-01 25
22 | Final project brief | 10 Weeks | bar: 2024-01-01 22 to 2024-03-01 25
23 | Submitting planning applications | 10 Weeks | bar: 2024-01-01 22 to 2024-03-01 25
24 | Stage 3 - Spatial Coordination | 14 Weeks | bar: 2024-02-01 5 to 2024-04-01 29
25 | Develop design | 14 Weeks | bar: 2024-02-01 5 to 2024-04-01 29
26 | Updated cost plan | 14 Weeks | bar: 2024-02-01 5 to 2024-04-01 29
27 | Project strategies | 14 Weeks | bar: 2024-02-01 5 to 2024-04-01 29
28 | Outline specification | 14 Weeks | bar: 2024-02-01 5 to 2024-04-01 29
29 | Change control procedures | 14 Weeks | bar: 2024-02-01 5 to 2024-04-01 29
30 | Stage 4 - Technical Design | 19 Weeks | bar: 2024-03-01 4 to 2024-07-01 8
31 | Technical Design | 19 Weeks | bar: 2024-03-01 4 to 2024-07-01 8
32 | Building systems information | 19 Weeks | bar: 2024-03-01 4 to 2024-07-01 8
33 | Submit building regulations application | 19 Weeks | bar: 2024-03-01 4 to 2024-07-01 8
34 | Prepare construction phase plan | 19 Weeks | bar: 2024-03-01 4 to 2024-07-01 8
35 | Stage 5 - Manufacturing aand Construction | 83 Weeks | bar: 2024-07-01 15 to 2026-02-01 9
36 | Phase 1 South - (Pre-construction , Enabling Works and Substructure) | 3 Weeks | bar: 2024-07-01 15 to 2024-07-01 29
37 | Pre-construction and Enabling Works | 3 Weeks | bar: 2024-07-01 15 to 2024-07-01 29
38 | Site logistics | 3 Weeks | bar: 2024-07-01 15 to 2024-07-01 29
39 | H&S File | 3 Weeks | bar: 2024-07-01 15 to 2024-07-01 29
40 | Site set up. Welfare, offices and canteen | 3 Weeks | bar: 2024-07-01 15 to 2024-07-01 29
41 | Site security | 3 Weeks | bar: 2024-07-01 15 to 2024-07-01 29
42 | Plant, Material storage and site parking | 3 Weeks | bar: 2024-07-01 15 to 2024-07-01 29
43 | Prepare zone for crane zone for when needed | 3 Weeks | bar: 2024-07-01 15 to 2024-07-01 29
44 | Temporary road for phase 1. | 3 Weeks | bar: 2024-07-01 15 to 2024-07-01 29
45 | Substructure for Phase 1 | 13 Weeks | bar: 2024-08-01 5 to 2024-10-01 28
46 | Check existing services | 1 Week | bar: 2024-08-01 5
47 | Set out site | 1 Week | bar: 2024-08-01 5
48 | Total excavation of site for foundations and drainage | 2 Weeks | bar: 2024-08-01 12 to 2024-08-01 19
49 | Set out for piling | 1 Weeks | bar: 2024-08-01 26
50 | Pile excavation | 1 Weeks | bar: 2024-09-01 2
51 | Piling works to phase 1 | 3 Weeks | bar: 2024-09-01 9 to 2024-09-01 23
52 | Raft - Underslab and driange works | 4 weeks | bar: 2024-09-01 16 to 2024-10-01 7
53 | Install DPM | 1 Weeks | bar: 2024-10-01 14
54 | Placement of Slab | 3 Weeks | bar: 2024-10-01 14 to 2024-10-01 28
55 | Substructure complete for phase 1 South. | bar: 2024-10-01 28
56 | Phase 2 South - Superstructure | 67 Weeks | bar: 2024-11-01 4 to 2026-02-01 9
57 | Crane into positon | 1 Weeks | bar: 2024-11-01 4
58 | Install base plates | 1 Weeks | bar: 2024-11-01 4
59 | Glulam arrives to site | 1 Weeks | bar: 2024-11-01 11
60 | Errect Glulam | 2 Weeks | bar: 2024-11-01 18 to 2024-11-01 25
61 | Elevator shafts craned in and installed | 1 Weeks | bar: 2024-12-01 2
62 | Stairs craned in and installed | 1 Weeks | bar: 2024-12-01 2
63 | Timber floors craned in and installed to FF | 1 Weeks | bar: 2024-12-01 2
64 | Scaffold Lift | 1 Weeks | bar: 2024-12-01 2
65 | Replicate works for First floor to Second Floor | 5 Weeks | bar: 2024-12-01 2 to 2024-12-01 30
66 | Replicate works for Second floor to Third Floor. | 5 Weeks | bar: 2025-01-01 6 to 2025-02-01 3
67 | Replicate works for Third Floor and Fourth Floor | 5 Weeks | bar: 2025-02-01 10 to 2025-03-01 10
68 | Installation of CLT Panels | 13 Weeks | bar: 2025-01-01 6 to 2025-03-01 31
69 | Roof | 2 Weeks | bar: 2025-04-01 7 to 2025-04-01 14
70 | Windows and Doors | 2 Weeks | bar: 2025-04-01 21 to 2025-04-01 28
71 | Drop scaffolding | 1 Week | bar: 2025-04-01 28
72 | Take away Crane | 1 Week | bar: 2025-04-01 28
73 | First fix Carpentry | 13 Weeks | bar: 2025-05-01 5 to 2025-07-01 28
74 | First fix Plumbing and services | 13 Weeks | bar: 2025-05-01 5 to 2025-07-01 28
75 | First fix Mechanical | 13 Weeks | bar: 2025-05-01 5 to 2025-07-01 28
76 | First fix Electrical | 13 Weeks | bar: 2025-05-01 5 to 2025-07-01 28
77 | Drylining | 13 Weeks | bar: 2025-07-01 7 to 2025-09-01 29
78 | Second fix carpentry | 13 Weeks | bar: 2025-09-01 1 to 2025-11-01 24
79 | Second fix Plumbing and services | 13 Weeks | bar: 2025-09-01 1 to 2025-11-01 24
80 | Second fix Mechanical | 13 Weeks | bar: 2025-09-01 1 to 2025-11-01 24
81 | Second fix Electrical | 13 Weeks | bar: 2025-09-01 1 to 2025-11-01 24
82 | Toilets and services fitted | 13 Weeks | bar: 2025-09-01 1 to 2025-11-01 24
83 | Kitchen / resturant services fitted | 13 Weeks | bar: 2025-09-01 1 to 2025-11-01 24
84 | Wall and floor tiles | 9 Weeks | bar: 2025-12-01 1 to 2026-01-01 26
85 | Decoration | 9 Weeks | bar: 2025-12-01 1 to 2026-01-01 26
86 | Builders Clean | 2 Weeks | bar: 2026-02-01 2 to 2026-02-01 9
87 | Inspections | 2 Weeks | bar: 2026-02-01 2 to 2026-02-01 9
88 | Snagging | 2 Weeks | bar: 2026-02-01 2 to 2026-02-01 9
89 | Superstructure Completion for the Libary & Community Hwb
90 | Phase 3 South - Landscaping | 19 Weeks | bar: 2025-10-01 6 to 2026-02-01 9
91 | External Lighting Services | 1 Week | bar: 2025-10-01 6
92 | Hard landscaping | 8 Weeks | bar: 2025-10-01 6 to 2025-11-01 24
93 | Soft landscaping | 9 Weeks | bar: 2025-11-01 3 to 2025-12-01 29
94 | Street furniture | 4 Weeks | bar: 2026-01-01 5 to 2026-01-01 26
95 | Decomission Site | 2 Weeks | bar: 2026-02-01 2 to 2026-02-01 9
96 | Completion of RIBA plan of works stage 5.
97 | Stage 6 - Handover | 2 Weeks | bar: 2026-02-01 23 to 2026-03-01 2
98 | Building quality inspections | 2 Weeks | bar: 2026-02-01 23 to 2026-03-01 2
99 | Comissioning building | 2 Weeks | bar: 2026-02-01 23 to 2026-03-01 2
100 | Building Handover | 2 Weeks | bar: 2026-02-01 23 to 2026-03-01 2
101 | Aftercare | 2 Weeks | bar: 2026-02-01 23 to 2026-03-01 2
102 | feedback on project | 2 Weeks | bar: 2026-02-01 23 to 2026-03-01 2
103 | Rectify defects | 2 Weeks | bar: 2026-02-01 23 to 2026-03-01 2
104 | Stage 7 - Use | 1 Week | bar: 2026-03-01 9
105 | Post Occupancy outcomes | 1 Week | bar: 2026-03-01 9
106 | Implement Facilites Management and asset Management | 1 Week | bar: 2026-03-01 9
107 | Verify Project Outcomes and Sustainability Outcomes | 1 Week | bar: 2026-03-01 9
List of Activities
Stage 0 Progress
Stage 1 Progress
Stage 2 Progress
Stage 3 Progress
Stage 4 Progress
Stage 5 Progress
Stage 6 Progress
Stage 7 Progress
Day of completion for that task
Duration of that stage
Duration of that stage
Completion of Construction (Stage 5 RIBA)