Name: Emmanuel Itua.

Student ID: 2019391.

Module Code: BMSW5104.

Module Title: Managing Projects in the Organisation.

Assignment Title: Task 2, Individual written report.

Lecturer’s Name: Dr Rexon Nting.

Table of Contents

Introduction………………………………………………………………………………3

Business Case…………………………………………………………………………..3

Stakeholder Analysis……………………………………………………………………4

Work Breakdown Structure…………………………………………………………….5

Cost/Resources Analysis……………………………………………………………….6

Project Schedule/Gant Chart…………………………………………………………..7

Risk Assessment………………………………………………………………………..7

Conclusion……………………………………………………………………………….8

References………………………………………………………………………………9

Introduction

In this report, I will be writing about a project proposal for The London Borough of Barking and Dagenham. This project is ‘The Construction of a 2 Bedroom house for Mr Williams’.

The aim of this project is to build a retirement home for Mr Williams who is a disabled man with special needs. Mr Williams is 67yrs old, nearing retirement and currently working in a local supermarket.

I believe this project will not only be beneficial to Mr Williams and the council but also future retirees residing in the borough. The house will be built and equipped with special installations bearing in mind that Mr Williams is disabled. These installations will make life easier for its occupant without needing much help in the absence of a carer.

The objective of the project is to build a sustainable home for disabled retirees in the borough. In a recent study by Michael Jones, the borough of Barking and Dagenham has the lowest retirement homes for disabled people. Building these homes will help reduce the need for the council to pay for temporary hotel accommodations for disabled occupants of the borough.

The sum of £270,000.00 has been budgeted and a piece of land allocated for its execution. It is expected to last a year from 20th of September 2022 to the 19th of September 2023.

The main body of the report is arranged in the following order, Stakeholder Analysis, Work breakdown Structure, Cost/Resources Analysis, Project schedule/Gant Chart and Risk assessment. A conclusion is provided in a final section.

Business Case

This proposed project to build a two-bedroom house for Mr A. Williams is needed to reduce overcrowding at the hotels paid for by the London Borough of Barking and Dagenham for retired members of the borough.

For some time now, the council has been housing retirees at rented apartments and hotel rooms due to insufficient houses. This has put a strain on the council’s finances knowing fully well that there is a high number of people in the retirement age within the borough.

Building this house is just a start which will ease the current overcrowding in the hotels and rented apartments. This will benefit the council tremendously and reduce its reliance on hotels and paying landlords ridiculous amounts to house the retired members.

The amount of £270,000.00 has been set aside for the project which is scheduled to start on 20th of September 2022 and end on the 19th of September 2023 with a 300sqm of land located on Downing Road in Dagenham.

Stakeholder Analysis

The table below shows who the stakeholders of this proposed project are and a breakdown of how, when and the format with which they can be contacted.

| Stakeholders | Name of Document | Document Format | Contact Person | Due Date |
| --- | --- | --- | --- | --- |
| London Borough of Barking and Dagenham (Sponsor) | Contract Document and Weekly status report | Hard copy, meetings, Phone calls and email | Helen Lords | First Monday of the month excluding Bank Holidays. |
| Mr A. Williams | Status Report Monthly | Emails and phone calls | Mr A. Williams | Status report first week of the month |
| LG Construction Ltd (Client) | Contract document, Weekly status report | Emails, Phone calls and meetings | Paul Higgins | Every Monday excluding Bank Holidays |
| Project Manager | Contract Document | Email, meetings, Phone calls, hard copy | John Doorman | Daily Progress Report |

London Borough of Barking and Dagenham is the sponsor of this project, and they will be in possession of the contract document and will be updated weekly on the progress of the project by having meetings, phone calls and email reports from LG Construction Ltd and the Project Manager.

Helen Lord is the contact person at the Council who shall be following up on the project and will be updated weekly on Mondays excluding bank holidays.

Mr A. Williams for whom the house is being built also has a stake in the project. He will be updated monthly by phone calls and emails from the council.

LG Construction Ltd shall be the builder of this project and has been awarded the contract by the council. They will also be in possession of the contract document so they can build according to specification. They will be updating the council on progress of the project by having meetings, making phone calls, and sending emails every Monday of the week excluding bank holidays. The contact person is Paul Higgins.

John Doorman is the Project Manager. He will oversee the overall timely deliverance of the project. He shall also be in possession of the contract document and shall be the intermediary between LG Construction Ltd and the project sponsor (London Borough of Barking and Dagenham). He will be having meetings, sending emails, making phone calls between the LG Construction Ltd and London Borough of Barking and Dagenham.

Work Breakdown Structure

Site Cleaning

Excavation

Laying the foundation and the installation of electrical pipes, drainage, sewer and water pipes.

Inspection of foundation and approval.

Ground floor works (concrete works, building of columns,doors, windows anddoor areas.

First floor works( concrete slabs, demarcation of rooms, bathrooms, windows and doors.

Roofing works

Internal installations and finishes (Electrical wiring and panelling,plumbings, paintings, installation of doors, windows,and bathtubs.

Exterior finishes( Landscaping)

Final inspection and project handover

The above diagram shows the sequence of work to be carried out from the start of the project to finish.

Works are going to begin by bringing machinery to site to clear the trees and bushes and removed on the allocated site in other for other works such as foundation to begin. This is followed by the excavation works. This involves setting out corner benchmarks, ground surveys, digging to specified depths, marking boundaries.

Foundation laying follows. This is the part of works that has direct contact with the soil, it involves soil testing, digging trenches, pouring concrete, metal works and laying the ground floor slab.

When the foundation work is done, this is inspected and approved if it follows specifications in the building design.

Once approved, the ground floor works begins. This involves structures such as columns, wall, demarcation of living room, kitchen, visitor’s toilet, and the dining area. Windows up to lintel level is also done.

The first-floor works begins by first laying a slab for the floor followed by erecting columns, laying blocks and demarcation of rooms and the bathroom on the floor. While doing this, installation of windows and doors can start simultaneously on the ground floor. Electrical wires can begin running and plumbing works can also start.

Roofing works can begin after the columns has been erected, blocks laid, and windows done up to the lintel level. Roofing involves laying some timber works that the roofing sheets are going to be laid on top.

Internal installations can continue while the first-floor works, and roofing works are going on. Walls will be prepared ready for painting, internal doors can be installed, flooring works for ground and first floor can continue so is internal paintings.

At this point, land scaping works can start outside the building. Flowers and grass can be planted to give the building a facelift.

When everything in the interior and exterior of the building has been completed and the landscaping has been done, the house will be ready for inspection and hand over.

Material and Human Resources Analysis

| Human Resources | Cost/Hour | Hours/week |
| --- | --- | --- |
| Project Manager | £20/hour | 40 |
| Site Manager | £17/hour | 40 |
| Assistant Site Manager | £16/hour | 40 |
| Machine drivers | £13/hour | 40 |
| Electricians | £13/hour | 40 |
| Plumbers | £12.50/hour | 40 |
| Steel Erectors | £11.50/hour | 40 |
| Concrete workers | £10.50/hour | 40 |
| Brick Layers | £12/hour | 40 |
| Landscapers | £11/hour | 40 |
| General Labourers | £8/hour | 40 |
| Carpenters | £12/hour | 40 |
| Projected Cost | £152,000 |  |
| Material Resources | Cost |  |
| Machinery | £10,000 |  |
| Timber | £10,000 |  |
| Concrete | £12,500 |  |
| Cement | £9,000 |  |
| Electrical materials | £13,000 |  |
| Plumbing materials | £17,500 |  |
| Bricks and blocks | £9,000 |  |
| Steel materials | £18.500 |  |
| Landscaping materials | £9,500 |  |
| Doors and windows | £7,000 |  |
| Paints | £5,000 |  |
| Wood floorings | £6,500 |  |
| Total | £118,000 |  |

The table above breaks down the projected cost of human and material resources needed to complete the project within the stipulated period of one year.

The costs mentioned in the table are subject to change if conditions such as weather or change in human resources condition causes disruptions.

Project Schedule

| Task | Start Date | Finish Date | Duration |
| --- | --- | --- | --- |
| Excavation | 20/09/2022 | 04/10/2022 | 2 Weeks |
| Foundation | 12/10/2022 | 22/12/2022 | 9 Weeks |
| Ground Floor | 04/01/2023 | 29/03/2023 | 12 Weeks |
| First Floor | 30/03/2023 | 28/06/2023 | 12 Weeks |
| Roofing | 29/06/2023 | 20/07/2023 | 3 Weeks |
| External | 21/07/2023 | 25/08/2023 | 5 Weeks |
| Landscaping | 28/08/2023 | 15/09/2023 | 3 Weeks |
| Inspection and Project Handover | 18/09/2023 | 19/09/2023 | 2 Days |

The above table shows the schedule of which the project will follow from start to finish. The project is expected to last for a year from 20/092022 to 19/09/2023.

Excavation works are expected to start on the 20th of September 2022 and last for about 2 weeks followed by the foundation which is expected to last for 9 weeks.

Ground floor works will commence on the 4th of January 2023 and finish on the 29th of March 2023 to last for 12 weeks, and this will be followed immediately by work commencement on the first floor starting on 30th of March 2023 and finish on 28th of June 2023 for a duration of 12 weeks.

Roofing is expected to commence on the 29th of June 2023 and end on the 20th of July 2023 for 3 weeks followed by the external works starting on the 21st of July 2023 and expected to finish on the 25th of August 2023 for a duration of 5 weeks.

Landscaping of the building exterior is expected start on the 28th of August 2023 and finish on the 15th of September 2023 for 3 weeks duration.

When landscaping is completed, the house will be inspected by officials of The London Borough of Barking and Dagenham in the presence of representatives of LG Construction Ltd and John Doorman the Project Manager on the 18th of September 2023.

After a satisfactory inspection that the project has been completed and has been built to the specified standard, it will officially be handed over to the borough on the 19th of September 2023 thereby officially putting the project to conclusive end,

Risk Assessment

| Risk | Probability | Impact |
| --- | --- | --- |
| Theft and Corruption | High | High |
| Design Risks | Medium | High |
| Organisational Risk | Low | Medium |
| Right of Way Risk | Low | Medium |
| Site Injury | Medium | Low |
| External Risk | Low | Low |
| Project Management Risk | Low | High |

The table above shows the risks capable of happening their probability of happening and its impact on the project.

Theft and corruption are a high risk because if the prices of materials are for example manipulated for personal gains or cheaper materials are bought in place of good quality materials, this can have a very high impact on the project being that the project might end up costing far more than anticipated and the quality of the building can be compromised.

Designs risks occurs when the design of a project does not meet its requirement. This risk happens but its not a common occurrence however the probability of it happening is medium while its impact if it does occur High. This can set the project back tremendously in terms of finance and project delivery.

Organisational Risks occurs when there are for example delayed deliveries, inexperienced workforce is used and when the site lacks protection. Then probability of it happening is low while the impact is medium.

Right of the way risk is low in probability while its impact is medium. This can usually occur when for example, expired temporary construction permits are used or when document information contradicts each other.

Site injury risks do occur very often. But it depends on the type of injury. Injury leading to death on site though its not common can lead to the site being shut down by the health and safety officials while investigations are ongoing which can in turn affect project delivery. But in general, site injury probability is classed as medium while impact is rated low.

External risks can occur when for example tax changes comes up during the project, when there are public objections or when laws and local standards change. These occurrences are not common but when it does happen the impact of it on a project is high.

Project management risks are risks associated with costs, performance, and schedule. The probability of this happening is low while its impact if it occurs is high.

Conclusion

I would like to conclude my writing by thanking the London Borough of Barking and Dagenham for giving me the opportunity to propose this essential project.

Mr A. Williams and future members of the borough would be glad to have a roof over their heads after retirement from active work. This is a project that is beneficial to the council on the long term. It is currently spending a lot of its finances housing retired men and women with no homes to stay in hotels and rented apartments at high cost to their budget. Doing this project and similar projects in the future will save the borough a lot of money while at the same time creating solution to a problem that has existed for a while now.

I hope this project gets approved as soon as possible so work can start earnestly as everything to get it running has already been put in place.

References

What are project management risks? (no date). Available at: https://www.knowledgehut.com/blog/project-management/what-are-project-management-risks (Accessed: 4 September 2022).

Hazem, Z. (2019). 7 Major builders risk categories and how to avoid them. [online] PlanRadar. Available at: https://www.planradar.com/gb/builders-risk/.

Appendix

My PowerPoint presentation is attached below in the link.

MPO Presentation BMSW5104.pptx