Activity Network and Gantt Chart Example

1.

| Activity | Dependent On | Length in Weeks |
| --- | --- | --- |
| A | - | 7 |
| B | A | 4 |
| C | B | 5 |
| D | C | 7 |
| E | A | 6 |
| F | E | 2 |
| G | A | 4 |
| H | G | 5 |
| I | H | 3 |
| J | D, F, I | 3 |

Draw up an Activity Network and Gantt Chart for the above project activities. Identify the critical path and calculate the expected project duration.

A testing room is required for Tasks D, F and I. Is this possible?

An analyst is required for Tasks B, E and G. Is this possible?

Tasks B and E are both delayed for 2 weeks due to staff illness. A replacement member of staff is available. Which task should they be assigned to?

2.

Complete an activity network and a Gantt chart for the following project activities.

| Task | Depends On | Time (weeks) |
| --- | --- | --- |
| A | - | 2 |
| B | - | 7 |
| C | - | 2 |
| D | A | 3 |
| E | C | 3 |
| F | D | 1 |

Label the critical path on the activity network and state the expected project duration.

b) Answer the following questions relating to the above project. Give brief explanation in each case.

- Task C is delayed by one week. What is the effect on the project duration?

- Task B is delayed by two weeks. What is the effect on the project duration?

- The project manager proposes using a systems analyst full time for tasks D and E. Is this possible?

- A meeting room needs to be booked for tasks A and E. Can the same room be used?

3. Input the following project details using Indent and Outdent to create tasks and sub tasks.

Analysis			21d	Tue 19/01/10	Tue 16/02/10

Fact Finding		7d	Tue 19/01/10	Wed 27/01/10

Data Flow Diagrams	7d	Thu 28/01/10	Fri 05/02/10	2

Produce Requirements Spec	7d	Mon 08/02/10	Tue 16/02/10	"2,3"

Design			19d	Wed 17/02/10	Mon 15/03/10	1

Data Flow Diagrams	6d	Wed 17/02/10	Wed 24/02/10

Pseudocode		5d	Thu 25/02/10	Wed 03/03/10	6

System Specification	8d	Thu 04/03/10	Mon 15/03/10	7

Implementation		30d	Tue 16/03/10	Mon 26/04/10	5

Database			14d	Tue 16/03/10	Fri 02/04/10

Web			16d	Tue 16/03/10	Tue 06/04/10

Synthesis			7d	Wed 07/04/10	Thu 15/04/10	"10,11"

System Chaecking		7d	Fri 16/04/10	Mon 26/04/10	12

Testing			14d	Tue 27/04/10	Fri 14/05/10	9

System Testing		7d	Tue 27/04/10	Wed 05/05/10

User Testing		7d	Thu 06/05/10	Fri 14/05/10	15

Changeover		36d	Mon 17/05/10	Mon 05/07/10	14

User Training		7d	Mon 17/05/10	Tue 25/05/10

System Implementation	15d	Wed 26/05/10	Tue 15/06/10	18

Handover			14d	Wed 16/06/10	Mon 05/07/10	19

3.

In assessing project risks, three estimates are produced for each activity

Most likely time (m)

Optimistic time (a)

Pessimistic (b)

| Task | a | M | b | Depends on: |
| --- | --- | --- | --- | --- |
| A | 5 | 7 | 10 | - |
| B | 3 | 4 | 7 | A |
| C | 4 | 5 | 7 | B |
| D | 6 | 7 | 9 | - |
| E | 5 | 6 | 7 | D |
| F | 2 | 2 | 4 | E |
| G | 3 | 4 | 6 | - |
| H | 3 | 5 | 9 | G |
| I | 3 | 3 | 6 | H |
| J | 2 | 3 | 5 | C, F, I |

For each activity, calculate the expected time and activity standard deviation. For the paths through the project, calculate total expected duration and standard deviation.