## Front
NRM1 Cost Plan Template
Omega Construction Limited
Port Talbot Theatr
Harri Morgan
1908064
01/05/2024

## Information Used
Omega Construction Ltd
Port Talbot Theatr
Schedule of rates
Harri Morgan
Information Used & Assumptions
| 1 | Information Used
Spring Design Drawings;
Concept
Materplan
00 Schedule of accommodation
01 Site analysis
02 Site plan
03 Design strategy
04 Design concept
05 Floor plan 1
06 Floor plan 2
07 Section elevation
08 Interior images
09 Auditoriam
10 Elevations 1
11 Elevations 2
12 Site sections
13 Exterior views
6043-ACECP-XX-XX-L-K-0001-AIR
6043-ACECP-XX-XX-T-K-0001-EIR
Utility information provided by client
Technical detail 1 to 5
Technical detail 1 to 20
A1 Elevational Section
| 2 | General assumptions;
FF&E is excluded unless specifically identified within the cost plan.
Costs are based upon the information as provided.
We have assumed a project bank account will not be required for this scheme.
We have assumed that the area of works will be decanted for the project. No allowance is made for throughways or dealing with building occupants.
The exact nature of specification for all internal works have been assumed
All costs are provisional awaiting design development.
All costs have been generated through SPONS Architect and Civils 2022
Location factor for Wales has been retreived from SPONS Architect 2022
TPI has been obtained through BCIS
Superstructure shell costs has been estimated through use of SPONS. 'SPONS Civils page 109 states that Theatres with over 500 seats have an estimated cost of £5900 p/m2
| 3 | General notes and exclusions;
All included costs are subject to variation following design development.
Risks associated with BREXIT are not considered.
A risk allowance of 10% is included for this estimate.
VAT is excluded from the estimate.
Works will be undertaken in a single phase.
All works associated with the Theatr and external façade has been included within this estimate
All demolition works to the buildings at the North of the site have been allowed
Entire site clearance has been allowed, including future phases
Project design fees has been calculated as a provisional sum based on other developments

## Summary Original
Omega Construction Ltd
Port Talbot Theatr
Schedule of rates
Harri Morgan
1908064
| Project details |  | NRM1 elemental cost plan template
| Description |  | Port Talbot Theatr
Works cost estimate
Cost
Building works estimate
|  | Group element 0 | FACILITATING WORKS | 436310.92
|  | Group element 1 | SUBSTRUCTURE | 502920
|  | Group element 2 | SUPERSTRUCTURE | 14193330
|  | Group element 3 | INTERNAL FINISHES | 402761.73 | 0
|  | Group element 4 | FITTINGS AND FURNISHINGS | 1000000
|  | Group element 5 | SERVICES | 1245100 | 0
|  | Group element 8 | EXTERNAL WORKS | 264820
|  | Group element 9 | MAIN CONTRACTOR'S PRELIMINARIES | 1710601.173
| Works cost estimate (sub total A) |  |  | 19755843.823 | 0
Project design team fees and other development costs (sub total B)
124500
0
| Base cost estimate A + B (sub total C) |  |  | 19880343.823
|  | Location Factor | 0.85 | -250160.9931
| Total Risk allowances (sub total D) |  | 10% | 1963018.283
0
| Total Construction Cost (C + D) |  |  | 21593201.1129
FUNDING SPLIT
|  | ACE | 75% | 16194900.8347
|  | HERITAGE LOTTERY FUNDING | 25% | 5398300.2782
21593201.1129
TRUE
0
0
0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0

## NRM1 CP template
Cost Plan for Port Talbot Theatr
Elemental Cost Plan
Omega Construction Ltd
Port Talbot Theatr
Schedule of rates
Harri Morgan
1908064
|  |  |  | £ | £ | £
0 | FACILITATING WORKS |  |  |  |  | 436310.92
0.1 | Toxic/hazardous material
| Toxic or hazardous material removal: Details to be stated e.g Removal of asbestos |  | item | 0 | 0
Site Clearance
| Break up exisiting car park and site clearance of entire area within boundary | 4936 | m2 | 20.97 | 103507.92
| Provisional sum. Utility diversions for gas, water and electric currently running through centre of the site | 3 | item | 20000 | 60000
| Hoard off site on completion for future phases to develop | 277 | m | 85 | 23545
0.2 | Major demolition works
Demolition of entire buildings: details to be stated.
| Demolition of entire structure | 9675 | m3 | 13.36 | 129258
0.3 | Site set up, compound, car park etc | 1 | Sum | 120000 | 120000
1 | SUBSTRUCTURE |  |  |  |  | 502920
1.1 | Foundations
| Foundations - piles | 60 | No | 4400 | 264000
| Foundations - beams | 1139 | m2 | 135 | 153765
| Plant set up | 1 | No | 24000 | 24000
| Pile testing | 1 | No | 9900 | 9900
| Provision for ground improvement following full foundation and ground assessment | 1139 | m2 | 45 | 51255
2 | SUPERSTRUCTURE |  |  |  |  | 14193330
2.1 | Frame
Structural steel frame, including fittings and fixings: details to be stated.
| SPONS Civils page 109 states that Theatres with over 500 seats have an estimated cost | 2277.5 | m2 | 5900 | 13437250
| Steel frame;composite beam and slab floors |  | m2 |  | 0
2.2 | Upper Floors
| Concrete upper floors | 0 | m2 |  | 0
2.3 | Roof
| Roof structure - pitched roofs: details, including design loads (kN/M2), spans (m) and angle of pitch (degtrees). To be stated | [5 empty] | Allowed within frame cost estimate
| Construction of new flat roof to 4th floor | 0 | m2 |  | 0
| New flat roof to 1st floor and 3rd floor | 0 | m2 |  | 0
| allowance for rainwater goods | 0 | item |  | 0
| Allowance for trims and flashings | 0 | item |  | 0
2.4 | Stairs & Ramps
Stair structures: details, includng vrtical rise of starcase to be stated
| Main Staircase | 0 | no |  | 0 |  | Allowed within frame cost estimate
| Balustrading to roof terrace, glazed | 0 | m2 |  | 0
2.5 | External Walls
| External walls: Details to be stated. | [5 empty] | Allowed within frame cost estimate
| Cladding to elevations | 0 | m2 |  | 0
| Extra over for projected fins to elevation windows 8.6m x 6m | 0 | nr | 0 | 0
2.6 | Windows and external doors
| Windows : details, including overall size of opening (mm) to be stated. | [5 empty] | Allowed within frame cost estimate
Windows
| Projection for windows | 0 | nr | 0 | 0
| UPVC 1400 x 900 mm | 0 | nr | 0 | 0
| UPVC 1600 x 1400 mm | 0 | nr | 0 | 0
| UPVC 1100 x 900 mm | 0 | nr | 0 | 0
| UPVC 1100 x 400 mm | 0 | nr | 0 | 0
External doors: details, including type, number of door leaves (nr) size of each door leaf (mm) and overall size of opening (mm) to be stated.
External doors
| Stainless steel entrance screens and doors - automatic | 2 | no | 3050 | 6100
| Softwood double leaf; emergency fire exit | 5 | no | 3100 | 15500
|  | 0 | no | 0 | 0
2.7 | Internal walls
Internal walls:details, including thickness, to be stated
| Steel partition with plasterboard each side | 7980 | m2 | 85 | 678300
| extra for plaster and emulsion | 0 | m2 | 0 | 0
fixed partitions:details, including thickness, to be stated
| New internal metal stud partitions, including skim to receive plaster both sides | 0 | m2 | 0 | 0
2.8 | Internal doors & screens
Internal doors: details, including type, number of door leaves (nr), size of each door leaf (mm), and overall size of opening (mm), to be stated.
0
Fire resisting doors: details, including type, number of door leaves (nr), fire rating (hours), size of each door leaf (mm), and overall size of opening (mm), to be stated.
| Fire rated doors single leaf, timber veneer with vision panel | 106 | nr | 530 | 56180
3 | INTERNAL FINISHES |  |  |  |  | 402761.73
3.1 | Wall finishes
Finishes to walls and columns: details to be stated.
| Paint finish | 7980 | m2 | 23.501 | 187537.98
3.2 | Floor finishes
Finishes to floors: details to be stated.
| vinyl safety flooring; 3.5 mm thick heavy duty | 2277.5 | m2 | 71 | 161702.5
| Resin paint to floor | 0 | m2 | 0 | 0
| Carpet to apartment floors | 0 | m2 | 0 | 0
| Carpet, higher specification to circulation | 0 | m2 | 0 | 0
3.3 | Ceiling finishes
Finishes to ceilings: details to be stated.
| Plasterboard to soffit | 0 | m2 | 0 | 0
| Decoration | 2277.5 | m2 | 23.5 | 53521.25
4 | FITTINGS AND FURNISHINGS |  |  |  |  | 1000000
4.1 | General fittings, furnishings and equipment
| Fittings and furnishes provision sum | 1 | no | 1000000 | 1000000
5 | SERVICES |  |  |  |  | 1245100
5.1 | Sanitary installations
Sanitary appliance: details to be stated.
| WC Installation | 0 | no | 0 | 0
| WC Sink installation | 0 | no | 0 | 0
| baths including bath panels & trims | 0 | no | 0 | 0
0
5.3 | Disposal Installations
Drainage to sanitary appliance: details to be stated.
| Generally | 0 | item | 0 | 0
5.4 | Water installations
Mains water supply: details, including the number of draw-off points (nr), to be stated.
| Cold & hot water | 0 | no | 0 | 0
5.5 | Heat source
Heat source (nr): details, including output of heat source (kW), to be stated.
| Boilers + Radiators | 0 | no | 0 | 0
5.8 | Electrical installations
| Power & Data distribution | 0 | no | 0 | 0
5.1 | Lift and Conveyor installations
Passenger lifts: details, including capacity (i.e. number of persons), speed (in m/sec), number of doors (nr), door heights and number of levels serviced (nr), to be stated.
| Passenger lift - 8-person; 4 stops; 1.6 m/s speed | 2 | no | 110000 | 220000
5.11 | Fire and lightning protection
| Fire alarm to apartments | 0 | no | 0 | 0
5.12 | Communication, security and control systems
Telecommunication systems: details of each type of system to be stated.
Data transmission systems: details of each type of system to be stated.
| Power & Data distribution | 0 | no | 0 | 0
| SERVICE ALLOWANCE BASED ON GIFA £450 M2 | 2278 | M2 | 450 | 1025100
8 | EXTERNAL WORKS |  |  |  |  | 264820
8.1 | Site Preparation works
| See above |  |  |  | 0
8.2 | Roads, Paths, pavings and surfacings
Roads: details, including width, to be stated.
| Tarmacadam to external areas not shown as landscaping | 1436 | m² | 120 | 172320
| Tarmacadam to road and parking spaces | 0 | m² | 0 | 0
| Tarmacadam to road and parking spaces | 0 | m² | 0 | 0
| Edgings | 0 | m | 0 | 0
8.3 | Soft landscapes, planting and irrigation systems
Grassed areas: details to be stated.
| soft landscaping - provisional sum | 1 | sum | 55000 | 55000
0
8.4 | Fencing,railings and walls
Walls: details, including height (m), to be stated.
| 2.1 High brick boundary wall | 0 | m | 0 | 0
Fencing: details, including height (m), to be stated.
| 2.1 High timber boundary fence | 0 | m | 0 | 0
Gates: details to be stated.
| Electric access gates | 0 | nr | 0 | 0
8.6 | External Drainage
| Drainage allowance | 0 | nr | 0 | 0
8.7 | External Services
Electrical
Connections to statutory undertaker's electricity main: details to be stated.
| Main electrical supply to building | 1 | item | 0 | 0
| Disconnections | 0 | item | 0 | 0
| Electrical substation | 0 | item | 0 | 0
Water
Connections to statutory undertaker's water main: details to be stated.
| Mains layout cost | 0 | item | 0 | 0
| Service costs | 0 | item | 0 | 0
| Water/sewerage infrastructure costs | 0 | item | 0 | 0
| Disconnections of water mains | 0 | item | 0 | 0
Gas
Connections to statutory undertaker's gas main: details to be stated.
| Works Allowance | 0 | item | 0 | 0
|  |  | M2 |  | 0
| Works Allowance | 0 | item | 0 | 0
Professional Fees
| Site investigation | 1 | item |  | 15000
| Ecological survey | 1 | item |  | 7500
| Bore hole study | 1 | item |  | 5000
| Contaminated land | 1 | item |  | 10000
9 | MAIN CONTRACTOR'S PRELIMINARIES |  |  |  |  | 1710601.173
| Main contractors preliminaries & OHP | 10 | % | 17106011.73 | 1710601.173
| SECTION SUB-TOTAL |  |  |  |  | 19755843.823
74373.964

## Monthly Cash Flow
Omega Construction Ltd
Port Talbot Theatr
Schedule of rates
Harri Morgan
1908064
START DATE |  | 2023-10-01 |  |  |  |  | 2023-10-01
COMPLETION DATE |  | 2025-08-01 |  |  |  |  | 2025-08-01
NUMBER OF MONTHS |  | 23 |  |  |  |  | 23
GROSS TOTAL VALUATION |  | 21593201.1129 |  |  |  |  | 21389367.2093
Period | Month | Cost in period | Gross Valuation | Cost to complete |  |  | Cost in period
1 | 2023-10-01 | 218637.33 | 218637.33 | 21374563.7829 | Design fees, 1 month prelim, surveys | Risk - 84542.95 | 230436.91 | 11799.58 | 218637.33
2 | 2023-11-01 | 188637.33 | 407274.66 | 21185926.4529 | Design fees, 1 month prelim | Risk - 84542.95 | 200436.91 | 11799.58 | 188637.33
3 | 2023-12-01 | 248637.33 | 655911.99 | 20937289.1229 | Design fees, service diversions, 1 month prelim | Risk - 84542.95 | 260436.91 | 11799.58 | 248637.33
4 | 2024-01-01 | 170682.33 | 826594.32 | 20766606.7929 | Hoarding, 1 month prelim | Risk - 84542.95 | 182481.91 | 11799.58 | 170682.33
5 | 2024-02-01 | 147137.33 | 973731.65 | 20619469.4629 | 1 month prelims | Risk - 84542.95 | 158936.91 | 11799.58 | 147137.33
6 | 2024-03-01 | 154637.33 | 1128368.98 | 20464832.1329 | Ecology Survey, 1 month prelimd | Risk - 84542.95 | 166436.91 | 11799.58 | 154637.33
7 | 2024-04-01 | 499903.25 | 1628272.23 | 19964928.8829 | Demolitions, compound, clearance, 1 month prelims | Risk - 84542.95 | 511702.83 | 11799.58 | 499903.25
8 | 2024-05-01 | 549473.33 | 2177745.56 | 19415455.5529 | 80% of founds + 1 month prelims | Risk - 84542.95 | 561272.91 | 11799.58 | 549473.33
9 | 2024-06-01 | 247721.3363 | 2425466.8963 | 19167734.2166 | 20% of founds + 1 month prelims | Risk - 84542.95 | 259520.9163 | 11799.58 | 247721.3363
10 | 2024-07-01 | 4626220.66 | 7051687.5563 | 14541513.5566 | Superstructure split over 3 months + 1 month prelims | Risk - 84542.95 | 4638020.24 | 11799.58 | 4626220.66
11 | 2024-08-01 | 4626220.66 | 11677908.2163 | 9915292.8966 | Superstructure split over 3 months + 1 month prelims | Risk - 84542.95 | 4638020.24 | 11799.58 | 4626220.66
12 | 2024-09-01 | 4626220.66 | 16304128.8763 | 5289072.2366 | Superstructure split over 3 months + 1 month prelims | Risk - 84542.95 | 4638020.24 | 11799.58 | 4626220.66
13 | 2024-10-01 | 847037.33 | 17151166.2063 | 4442034.9066 | Internals, 1 month prelims, internal and external doors | Risk - 84542.95 | 858836.91 | 11799.58 | 847037.33
14 | 2024-11-01 | 645017.33 | 17796183.5363 | 3797017.5766 | Internals, 1 month prelims, services split over 3 months | Risk - 84542.95 | 656816.91 | 11799.58 | 645017.33
15 | 2024-12-01 | 588837.33 | 18385020.8663 | 3208180.2466 | Fittings and furnishings split over 10 months, 1 month prelims, services split over 3 months | Risk - 84542.95 | 600636.91 | 11799.58 | 588837.33
16 | 2025-01-01 | 808837.33 | 19193858.1963 | 2399342.9166 | Fittings and furnishings split over 10 months, 1 month prelims, lifts, services split over 3 months | Risk - 84542.95 | 820636.91 | 11799.58 | 808837.33
17 | 2025-02-01 | 434675.31 | 19628533.5063 | 1964667.6066 | Fittings and furnishings split over 10 months, 1 month prelims, wall painting | Risk - 84542.95 | 446474.89 | 11799.58 | 434675.31
18 | 2025-03-01 | 300658.58 | 19929192.0863 | 1664009.0266 | Fittings and furnishings split over 10 months, 1 month prelims, ceiling painting | Risk - 84542.95 | 312458.16 | 11799.58 | 300658.58
19 | 2025-04-01 | 408839.83 | 20338031.9163 | 1255169.1966 | Fittings and furnishings split over 10 months, 1 month prelims, floor finishes | Risk - 84542.95 | 420639.41 | 11799.58 | 408839.83
20 | 2025-05-01 | 247137.33 | 20585169.2463 | 1008031.8666 | Fittings and furnishings split over 10 months, 1 month prelims | Risk - 84542.95 | 258936.91 | 11799.58 | 247137.33
21 | 2025-06-01 | 247137.33 | 20832306.5763 | 760894.5366 | Fittings and furnishings split over 10 months, 1 month prelims | Risk - 84542.95 | 258936.91 | 11799.58 | 247137.33
22 | 2025-07-01 | 379547.33 | 21211853.9063 | 381347.2066 | Fittings and furnishings split over 10 months, 1 month prelims, extenral works over 2 months | Risk - 84542.95 | 391346.91 | 11799.58 | 379547.33
23 | 2025-08-01 | 381347.21 | 21593201.1163 | -0.0034218 | Fittings and furnishings split over 10 months, 1 month prelims, extenral works over 2 months | Risk - 84542.95 | 393146.91 | 11799.58 | 381347.33
|  | 21593201.1163 |  |  |  |  | 21864591.5763 |  | 21593201.2363

## Daywork schedule of rates
Omega Construction Ltd
Port Talbot Theatr
Schedule of rates
Harri Morgan
1908064
| Description | / Hour | / Day | / Week
1 | Labourer | 14.124 | 112.992 | 564.96 | 12.84
2 | Skilled labourer | 15.268 | 122.144 | 610.72 | 13.88
3 | Apprentice | 0 | 0 | 0
4 | Banksman | 0 | 0 | 0
5 | Groundworker | 15.268 | 122.144 | 610.72 | 13.88
6 | Concrete | 20.13 | 161.04 | 805.2 | 18.3
7 | Steel Fitter | 20.13 | 161.04 | 805.2 | 18.3
8 | Formwork | 18.986 | 151.888 | 759.44 | 17.26
9 | Bricklayer | 18.986 | 151.888 | 759.44 | 17.26
10 | Carpenter | 18.986 | 151.888 | 759.44 | 17.26
11 | Roofer | 0 | 0 | 0
12 | Plubming | 0 | 0 | 0
13 | Electrician | 0 | 0 | 0
14 | Painter | 0 | 0 | 0
15 | Plasterer | 0 | 0 | 0
16 | Tiler | 0 | 0 | 0
17 | Painter | 0 | 0 | 0
18 | Foreman | 20.13 | 161.04 | 805.2 | 18.3
19 | Site Manager | 52.1125 | 416.9 | 2084.5 | 47.375
20 | Assistant Site Manager | 0 | 0 | 0
21 | Fotklift Driver | 0 | 0 | 0
22 | Scaffold tower | 4.169 | 33.352 | 166.76 | 3.79
23 | Mobile crane - 30 tonnes | 42.306 | 338.448 | 1692.24 | 38.46
24 | 17m Forklift | 11.847 | 94.776 | 473.88 | 10.77
25 | 15 Tonne dumper | 31.416 | 251.328 | 1256.64 | 28.56
26 | 30 Tonne excavator | 48.191 | 385.528 | 1927.64 | 43.81
27 | Engineer | 36.3 | 290.4 | 1452 | 33
28 | Secutiry | 14.025 | 112.2 | 561 | 12.75
29 | Office cabin 24ft x 9ft | 41.25 | 330 | 1650 | 37.5
30 | Meeting room 24ft x 9ft | 41.25 | 330 | 1650 | 37.5
31 | Container x4 | 15.95 | 127.6 | 638 | 14.5
32 | Toilets 13ft x 9ft | 63.8 | 510.4 | 2552 | 58
33 | Drying room | 56.1 | 448.8 | 2244 | 51
34 | 15 KVA Generator | 6.325 | 50.6 | 253 | 5.75
35 | Mixer | 1.76 | 14.08 | 70.4 | 1.6
36 | Large dehumidifier | 2.585 | 20.68 | 103.4 | 2.35
37 | Road Sweep | 0 | 0 | 150
|  | 0 | 0 | 0

## TPI & Funding split
Your Total for project etc |  | 19880343.823
Current TPI | 1.2
2023 Q4 TPI | 1.394
23094332.7411
Wales location Factor | 0.85
New Total |  | 19630182.8299
-250160.9931
FUNDING SPLIT
ACE | 75% | 14910257.8672
HERITAGE LOTTERY FUNDING | 25% | 4970085.9557
19880343.823
TRUE

## Material Cost Comparison
Material Cost Comparison
Item | Spec | Cost | Spec | Cost | Difference
Frame | Steel frame; composite beam and slab floors | £200 /m2 | Concrete frame; flat slab reinforced concrete floors up to 250 mm thick | £190 /m2 | 10
External Façade | Glazed curtain walling stick curtain walling with double glazed units, aluminium structural framing and spandrel rails. Standard colour powder coated capped. | £660 / m2 | Glazed curtain walling unitized curtain walling bespoke project specific system with double glazed units, aluminium structural framing and spandrel rails. Standard colour powder coated. | £1,375 / m2 | -715
External Façade | Glazed curtain walling stick curtain walling with double glazed units, aluminium structural framing and spandrel rails. Standard colour powder coated capped | £660 / m2 | Cavity wall; facing brick outer skin; insulation; with plaster on standard weight block inner skin; emulsion | £175 / m2 | 485
Windows | Steel windows (U-value = 1.6 W/m2 K) Standard windows double glazed; powder coated | £780 / m2 | uPVC windows Windows; standard ironmongery; sills and factory glazed with low-e 24 mm double glazing standard with low-e 24 mm double glazing | £280 /m2 | 500
Floor coverings | vinyl safety flooring; 3.5 mm thick heavy duty | £71 / m2 | Cement and sand (1:3) screeds; steel trowelled 50mm | £22 /m2 | 49
Wall finishes | Flame-retardant paint Unitherm or similar; two coats | £23.50 /m2 | Wax polish and stain | £22 /m2 | 1.5
0