## Project
Project Planner - Ganntt Chart
[8 empty] | Legend |  |  | Plan |  | % Complete
| PLAN | PLAN
ACTIVITY | START | DURATION | PERIODS | [8 empty] | Target End Date |  |  |  | Actual End Date
|  |  | 2021-01-25 | 2021-02-01 | 2021-02-08 | 2021-02-15 | 2021-02-22 | 2021-03-01 | 2021-03-08 | 2021-03-15 | 2021-03-22 | 2021-03-29 | 2021-04-05 | 2021-04-12 | 2021-04-19 | 2021-04-26 | 2021-05-03 | 2021-05-10 | 2021-05-17 | 2021-05-24 | 2021-05-31
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
Initial Meeting (All) | 1 | 1 | bar: 2021-01-25
Get Brief (All) | 1 | 1 | bar: 2021-01-25
Complie Aims (All) | 2 | 1 | bar: 2021-01-25 to 2021-02-01
Research: History of Caps | 3 | 3 | bar: 2021-02-08 to 2021-02-22
Research: Future Implications of Super-Caps | 3 | 3 | bar: 2021-02-08 to 2021-02-22
Research: Variations of Caps | 3 | 3 | bar: 2021-02-08 to 2021-02-22
Research: Manufacturing Methods of Super Caps | 3 | 3 | bar: 2021-02-08 to 2021-02-22
Research: Design of Batteries | 3 | 3 | bar: 2021-02-08 to 2021-02-22
Research: Designs of Capacitors +Super Caps | 3 | 3 | bar: 2021-02-08 to 2021-02-22
Research: Compare battery vs Super Capacitor | 3 | 3 | bar: 2021-02-08 to 2021-02-22
Research: Required Calculations | 3 | 3 | bar: 2021-02-08 to 2021-02-22
Design Testing Circuit | 6 | 2 | bar: 2021-03-01 to 2021-03-08
Design: Programme for Testing Circuit | 6 | 2 | bar: 2021-03-01 to 2021-03-08
Methodology (All) | 7 | 1 | bar: 2021-03-08
Construct Testing Circuit (All) | 8 | 1 | bar: 2021-03-15
Test 1 (electrolyte 1) (AH) | 9 | 1 | bar: 2021-03-22
Test 2 (electrolyte 2) (KT) | 9 | 1 | bar: 2021-03-22
Test 3 (electrolyte 3) (KM) | 9 | 1 | bar: 2021-03-22
Results (Group) | 10 | 2 | bar: 2021-03-29 to 2021-04-05
Analysis (Group) | 10 | 2 | bar: 2021-03-29 to 2021-04-05
Compile Final Report (Group) | 12 | 3 | bar: 2021-04-12 to 2021-04-26
Report Submission (Group) | 14 | 1 | bar: 2021-04-26
Viva / Presentation (Group) | 15 | 1 | bar: 2021-05-03