## Front
Plot E9 - Project Costings
Project Name: Plot E9 (UWTSD)
Brief Description: Full Project Costing for the proposed development
Client: UWTSD
Prepared By: Jay Weaver (Alliance Construction Ltd)
Date: 01/02/2022

## Assumptions
Information Used & Assumptions
1 | Information Used
PDF document named 'Ground Floor Plan - Marked Up (Piling Mat)'
PDF document named ' ALLIANCE 3D MODEL floor plan pile caps'
Alliance Construction Ltd's Construction Programme - produced by E Williams
NRM1 Document
SPONS Architects 2020
SPONS Civil 2020
Alliance Construction Ltd's Structural Report - produced by SP Griffiths
Word document "material choices" - produced by SP Griffiths
2 | General Assumptions;
I have assumed there is no contaminated land on this site
I have assumed the project is located at Plot E9, SA1, Swansea. This site also has easy access and no restrictions
The project is due to commence in May 2022 - as per E Williams' programme
The cost plan is for a Student Accomodation block, with retail units at the Ground Floor
The project is currently at Design Stage, and there are no planning restrictions or conditions
I have assumed that all material excavated for the foundations works are to be disposed on site and none is to be removed from site (unless otherwise stated)
I have assumed there are 3x lifts as per Ground Floor drawing provided
I assumed that there is adequate services provision and drainage capacity available and are adjacent to the site
No fitting out costs allowed - this is to be with the leaseholder of the retail units
No tree stumps or contaminated land on the site
No cut and fill required - (no muck away or import required)
Concrete stairs assumed
Stainless steel handrails to stairs assumed
Assumed 2.4m internal wall height to Accomodation Floors (1st and 2nd floor)
Assumed 3.0m internal wall height to all ground floor
8.2m total height of building has been allowed
Assumed no flooring to be fitted in retail units, but a screed finish has been allowed for
No allowance for retaining walls on the site as the site is flat
3 | General Notes and Exclusions;
Precast driven piles with Reinforced Concrete strip foundations have been allowed for, as per SP Griffiths' structural report
I have used the Tender Price Index - as this is the cost to the client, not the cost to the contractor
Exclusions:
VAT
Works beyond established scope
Land costs and associated legal fees
Any major earthworks to deal with large changes in ground level

## Summary Page
Project details: | Plot E9 (UWTSD)
Description: | Full Project Costing for the proposed development
Building Works Estimate
Based on GIA of: | 4465.29 | m2
| Group Element | Element Type | Total | £/m2
Works cost estimate (sub total A) | Group element 0 - Facilitating Works | 0 | 13365 | 2.9931
| Group element 1 - Substructure | 1 | 542833.708 | 121.5674
| Group element 2 - Superstructure | 2 | 3763245.023 | 842.7773
| Group element 3 - Internal Finishes | 3 | 1321060.3 | 295.851
| Group element 4 - Fittings, Furnishings and Equipment | 4 | 1048800 | 234.8784
| Group element 5 - Services | 5 | 2361129.349 | 528.774
| Group element 8 - External Works | 8 | 288721.689 | 64.6591 | 4372548.3682
|  |  | 9339155.069 | 2091.5002 | 46.82%
Project design team fees and other development costs (sub total B) |  |  |  |  | 4372548.3682
Provisional Sums |  |  |  |  | 13711703.4372
Design Fees |  |  | 65000 | 14.5567
Juliett balconies - all associated works |  |  | 25000 | 5.5987
Unknown facilitating works - i.e contaminated land etc |  |  | 75000 | 16.7962
Wind Turbine - all associated works |  |  | 500000 | 111.9748
Mechanical and Electrical works - including Air Source Heat Pumps to flats |  |  | 588000 | 131.6824
Mechanical and Electrical works - including Air Source Heat Pumps to retail units |  |  | 35000 | 7.8382
Fixed and loose furniture - accomodation communal areas |  |  | 50000 | 11.1975
Fixed and loose furniture - flats (£1500 per flat) |  |  | 126000 | 28.2177
Provision for Statutory Service Connections (electric & water) including 3 phase supply to retail units |  |  | 115800 | 25.9334
External Drainage Works |  |  | 175000 | 39.1912
External works (Roads/Kerbs/Street furniture/street lighting/bollards/signs) |  |  | 75000 | 16.7962
Base cost estimate A + B (sub total C) |  |  | 11168955.069 | 2501.2832
| Design Contingency | Risk allowance @ 2.5% | 279223.8767 | 62.5321
| Construction Risk | Risk allowance @ 2.5% | 279223.8767 | 62.5321
| Employers Change Risk | Risk allowance @ 2.5% | 279223.8767 | 62.5321
| Other Mis. Risk | Risk allowance @ 2.5% | 279223.8767 | 62.5321
| Preliminaries | Risk allowance @ 12% | 1340274.6083 | 300.154
Total Risk allowances (sub total D) |  |  | 13626125.1842 | 3051.5656
Inflation Adjustment
| SPONS Value - Based on London Rates | 124 | 13626125.1842
| CONVERSION TO BCIS INDEX FORECAST FOR PROJECT DURATION (AVERAGE TAKEN OF PROJECT DURATION - MAY 2022 - JUNE 2023) |  | 0.18386
| CONVERSION TO BCIS INDEX FORECAST FOR PROJECT DURATION (AVERAGE TAKEN OF PROJECT DURATION) AS A PERCENTAGE |  | 18.39%
| CONVERSION TO BCIS INDEX FORECAST FOR PROJECT DURATION (MAY 2022 - JUNE 2023) | 0 | 2505290.6243
|  | Total | 16131415.8084
Location Adjustment
| London | 100% | 16131415.8084
| Wales | 85% | 13711703.4372
Total Construction Cost (C + D) |  |  | 13711703.4372 | 3070.7308

## Elemental Cost Plan
Cost Plan for: |  | Full Project Costing for the proposed development
Elemental Cost Plan
| Elements in red are NRM1 Phraseologies | [7 empty] | 9339155.069
Ref. | Element | Timesing | Quantity |  | Unit |  | Rate | Sub-Total | Group-Total | Notes
[7 empty] | £ | £ | £
0 | FACILITING WORKS
SITE CLEARANCE AND PREPERATION
Clearing Site vegetation
| bushes,scrub, undergrowth, hedges and treesand tree stumps not exceeding 500mm girth |  | 90 |  | m | width of plot
|  |  | 90 |  | m | length of plot
|  |  |  | 8100 | m2 | area of plot | 1.65 | 13365 | 13365 | As per page 284 of SPONS 2020 (ARCHITECT edition)
1 | SUBSTRUCTURE
1.1 | 1.1 FOUNDATIONS
Piling
| Enabling Work: | [8 empty] | Piling mat specification is as per SPG's Structural Report
excavate to form piling mat; supply and lay imported hardcore - recycled brick and similar to form piling mat
|  |  |  | 264.84 | lm | perimeter of building
|  |  |  | 5 | m | width of piling mat
|  |  |  | 1324.2 | m2 | area of piling mat
|  |  |  | 0.2 | mm | depth of piling mat
|  |  |  | 264.84 | m3 |  | 13.7 | 3628.308 |  | As per page 133 of SPONS 2020 (CIVIL edition)
1.2 | provision of plant (1 nr rig); including bringing to and removing from site;
| maintenance, erection and dismantling at each pile position |  | 1 | 1 | no |  | 23000 | 23000 |  | As per page 133 of SPONS 2020 (CIVIL edition)
1.3 | Supply and install concrete Continuous Flight Auger (CFA) piles; cart away
inactive spoil; measure total length of pile
| 450mm dia. reinforced concrete CFA piles |  | 61 | 61 | no | number of pile caps |  |  |  | As per pile cap drawing from SPG
|  |  | 3 | 3 | no | piles per pile cap
|  |  |  | 183 | no | number of piles
|  |  |  | 25 | m | depth of piles
|  |  |  | 4575 | m | total meterage of piles | 63 | 288225 |  | As per page 133 of SPONS 2020 (CIVIL edition)
1.4 | Pile testing
| using tension piles as reaction; typical loading test 1000 kN to 2000 kN |  | 3 | 3 | no | assuming 3x tests required | 9500 | 28500 |  | As per page 133 of SPONS 2020 (CIVIL edition)
| integrity testing; minimum 20 per visit |  | 10 | 10 | no | minimum 20x per visit (183/20 = 9.15, so allowed 10) | 19.3 | 193 |  | As per page 133 of SPONS 2020 (CIVIL edition)
Piling Caps
1.5 | Excavate pit in firm ground by machine, partial backfill, partial disposal, | [8 empty] | As per pile cap drawing from SPG
support, compaction, cut off pile and prepare reinforcement, formwork;
reinforced in situ concrete cap 25 N/mm²; reinforcement at 50 kg/m³; rates
per cap for cap size
| 2100mm× 2100mm× 1000 mm; 2–3 piles |  | 61 | 61 | no | number of pile caps
|  |  |  | 61 | no |  | 2050 | 125050 |  | As per page 134 of SPONS 2020 (CIVIL edition)
Concrete Lift Pits
1.6 | Excavate and disposal; reinforced concrete floor and walls; bitumen tanking
| as necessary | [8 empty] | As per Ground Floor Plan
| 1.80m× 2.50m× 1.60m deep pit −13 person lift/1000 kg |  | 3 | 3 | no | number of lifts required
|  |  |  | 3 | no |  | 4000 | 12000 |  | As per page 134 of SPONS 2020 (CIVIL edition)
Strip Foundations
1.7 | Excavate trench 600mm wide, partial backfill, partial disposal, earthwork support
(risk item), compact base of trench, plain in situ concrete 20.00 N/mm² – 20mm
aggregate (1:2:4), 250mm thick, 3 courses of common brick up to DPC level,
cavity brickwork/blockwork in cement mortar (1:3), pitch polymer damp-proof
course machine excavation
With 3 courses of facing brick outer skin up to DPC level
(PC bricks @ £700/1000)
600mm× 1500mm deep
|  |  |  | 264.84 | lm | perimeter of building | 235 | 62237.4 |  | As per page 216 of SPONS 2020 (ARCHITECTS edition)
542833.708
2 | FRAME
Frame
2.1 | Steel frame; composite beam and slab floors
Suspended slab; permanent steel shuttering with 130mm thick concrete; no
coverings or finishes
| up to 6 storeys | 3 | 1488.43 |  | m2 | GIFA - 1x floor
|  |  |  | 4465.29 | m2 | Total GIFA | 180 | 803752.2 |  | As per page 219 of SPONS 2020 (ARCHITECTS edition)
Floors
2.2.1 | Composite steel deck flooring | [8 empty] | As per SP Griffiths Structural report
Composite steel and concrete upper floors (Note: all floor thicknesses are
nominal); A142 mesh reinforcement:
| Trapezoidal steel decking 1.20mm thick; 150mm reinforced concrete topping | 2 | 1488.43 |  | m2 | Floor Area |  |  |  | Only required to 1st and 2nd floor
|  |  |  | 2976.86 | m2 |  | 105 | 312570.3 |  | As per page 222 of SPONS 2020 (ARCHITECTS edition)
2.3 | Roof
Concrete
precast concrete suspended slab with sand: cement screed over m2 82.00 to 99.00
| reinforced concrete slabs; on steel permanent steel shuttering; 150mm |  | 1488.43 |  |  | roof area
|  |  |  | 1488.43 | m2 |  | 99 | 147354.57 |  | As per page 223 of SPONS 2020 (Architects edition)
2.3.2 | Roof Coverings
Flat roofing systems
Includes insulation and vapour control barrier; excludes decking (U-value =
0.25W/m2 K)
Includes insulation and vapour control barrier
| high performance bitumen felt roofing system |  | 1488.43 |  |  | roof area
|  |  |  | 1488.43 | m2 |  | 120 | 178611.6 |  | As per page 225 of SPONS 2020 (Architects edition)
2.3.3 | Specialist Roof System
Not applicable for this project
2.3.4 | Roof Drainage
| Gutters |  |  |  | lm | perimeter of building
| 100mm uPVC gutter |  |  | 264.84 |  |  | 34.5 | 9136.98 |  | As per page 225 of SPONS 2020 (Architects edition)
Rainwater downpipes pipes; fixed to backgrounds; including offsets and shoes
| 68mm dia. uPVC |  |  | 264.84 | lm | perimeter of building | 31 | 8210.04 |  | As per page 225 of SPONS 2020 (Architects edition)
2.3.5 | Rooflights/Patent Glazing and Glazed Roofs | [8 empty] | Assumed rooflight 1.5m wide, above internal corridor on 2nd floor to increase lighting
Rooflights
| individual polycarbonate rooflights; rectangular; electric opening |  | 1.5 |  |  | width of rooflight
|  |  | 132.85 |  |  | length of rooflight
|  |  |  | 199.275 | m2 | total area of rooflight | 1325 | 264039.375 |  | As per page 226 of SPONS 2020 (Architects edition)
2.3.6 | Roof Features
Flat roof feature
| roof walkways 600mm× 600mm× 50mm precast concrete slabs on support |  | 1488.43 |  | m2 | roof area |  |  |  | Assumed pedestrian access in order to access solar panels on roof for maintenance reasons
| pedestrian access |  | -199.275 |  | m2 | rooflight area
|  |  |  | 1289.155 | m2 | area of roof walkways (all roof area minus rooflight area) | 52 | 67036.06
2.4 | STAIRS AND RAMPS
2.4.1 | 2.4.1 Stair/Ramp Structures
Reinforced concrete construction
Staircase; terrazzo finish; mild steel balustrades and handrails; plastered soffit;
balustrades and staircase soffit decorated
| 3.00m rise; dogleg | 2 | 3 |  | nr | 3x stairs per floor (2x floors)
|  |  |  | 6 | nr | total number of staircases | 12000 | 72000 |  | As per page 227 of SPONS 2020 (Architects edition)
2.4.3 | Stair/Ramp Balustrades and Handrails
| stainless steel handrail and brackets | 3 |  | 30 |  | assumed 10m per staircase
|  |  |  | 90 | lm |  | 240 | 21600 |  | As per page 228 of SPONS 2020 (Architects edition)
2.5 | EXTERNAL WALLS
2.5.1 | External Enclosing Walls above ground level
| Facing brick walls; sand faced facings; bricks PC £500.00/1000 | [8 empty] | Assumed dense block wall with facing brick finish
| half brick thick; pointed one side |  | 17.31 |  | m2
|  |  | 15.25 |  | m2
|  |  | 119.17 |  | m2
|  |  | 81.17 |  | m2
|  |  | 99.06 |  | m2
|  |  | 14.49 |  | m2
|  |  | 15.28 |  | m2
|  |  | 29.06 |  | m2
|  |  | 3.27 |  | m2
|  |  |  | 394.06 | m2 | total area of birckwork required | 89 | 35071.34 |  | As per page 228 of SPONS 2020 (Architects edition)
Dense aggregate block walls
| 100mm thick |  |  | 394.06 | m2 | total area of blockwork required | 51 | 20097.06 |  | As per page 229 of SPONS 2020 (Architects edition)
Sheet Claddings
Cement fibre profiled cladding
P61 Insulated System; natural grey finish; 100mm lightweight concrete block
| (U-value = 0.30W/m2 K) |  | 272.34 |  | m2
|  |  | 252.55 |  | m2
|  |  | 167.59 |  | m2
|  |  | 166.13 |  | m2
|  |  |  | 858.61 | m2 | total area of cladding required | 110 | 94447.1 |  | As per page 230 of SPONS 2020 (Architects edition)
Glazed walling
Curtain Walling
unitized curtain walling bespoke project specific system with double glazed
units, aluminium structural framing and spandrel rails. Standard colour
| powder coated | 1 | 7.5 | 7.5 | m2
|  | 5 | 2.54 | 12.7 | m2
|  | 23 | 3.96 | 91.08 | m2
|  | 4 | 16.23 | 64.92 | m2
|  | 1 | 8.05 | 8.05 | m2
|  | 10 | 3 | 30 | m2
|  | 4 | 11.57 | 46.28 | m2
|  | 1 | 4.32 | 4.32 | m2
|  | 1 | 8.57 | 8.57 | m2
|  | 1 | 6.44 | 6.44 | m2
|  | 4 | 11.49 | 45.96 | m2
|  | 7 | 8.46 | 59.22 | m2
|  |  |  | 385.04 | m2 | total area of curtain walling | 1350 | 519804 |  | As per page 230 of SPONS 2020 (Architects edition)
2.6 | WINDOWS AND EXTERNAL DOORS
2.6.2 | External Doors
Automatic glazed entrance doors
Automatic glazed sliding doors in aluminium; polyester powder coated; linear
sliding doors; inner pivoted pocket screens; glazed with safety units in
accordance with BS. ASSA ABLOY SL510 P RC2 Anti-Burglar Sliding Door
| System complete with 100mm operator providing automated operation of the | [8 empty] | x5 retail units plus 1x entrance for accomodation entrance
| sliding door leaves |  | 6
| Double bi-parting; opening 2.00m× 2.30m nr 9100.00 |  |  | 6 | nr | total number of automatic entrance doors | 11500 | 69000
Shopfront, shutters and grilles
| flat facade; glass in aluminium framing; manual centre doors only | 6 | 7.39 |  | m2 | 6x main entrance doors
|  |  |  | 44.34 | m2 | total area of shop front panels around entrance doors
| grilles or shutters | 6 | 10.88 |  | m2 | 6x main entrance doors |  |  |  | Assumed shutters required to all entrance doors
|  |  |  | 65.28 | m2 | total area of shutters | 520 | 33945.6 |  | As per page 235 of SPONS 2020 (Architects edition)
| fire shutters; powers operated | 3 | 2.86 |  |  | 3x roller shutters to service yard
|  |  |  | 8.58 | m2 | total area of fire rated roller shutters | 560 | 4804.8 |  | Assumed shutters required to all entrance doors
As per page 235 of SPONS 2020 (Architects edition)
2.7 | INTERNAL WALLS AND PARTITIONS
2.7.1 | Frame and panel partitions
Metal stud and board partitions; height range from 2.40m to 3.30m
130mm thick partition; 70mm steel studs at 600mm centres generally; 2
layers 15mm Soundbloc board each side; joints filled with joint filler and joint
| tape; emulsion paint finish; softwood skirtings with gloss finish |  | 23.38
|  | 3 | 23.06
9.93
20.16
21.93
2.15
|  |  | 28.17 | 128.78 | lm
|  | 3 |  | 128.78 | lm |  |  |  |  | 3m high internal walls for Ground floor
|  |  |  | 386.34 | m2 | total meterage of internal stud for GF accomodation area
|  | 42 | 23.71 | 995.82 | lm | total meterage of internal partitions for all flats (1st floor)
|  | 42 | 23.71 | 995.82 | lm | total meterage of internal partitions for all flats (2nd floor)
|  | 2.4 |  | 1991.64 | lm
|  |  |  | 4779.936 | m2 | total area of internal partitions for flats
|  |  | 17.87 |  |  | All other areas (corridors etc) - 1st floor
10.32
35.48
10.18
26.42
31.85
39.45
3
9.54
20.65
5.78
3
3
21.06
3
|  | 2 |  | 240.6 | lm | To allow for 1st and 2nd floor (as mirror image)
|  |  |  | 481.2 | lm
|  | 2.4 |  | 481.2 |  | walls 2.4m high |  |  |  | 2.4 high walls for 1st and 2nd floor
|  |  |  | 1154.88 | m2 | total area of corridor areas (1st and 2nd floor)
|  |  |  | 1154.88 | m2 | total area of corridor areas (1st and 2nd floor)
|  |  |  | 4779.936 | m2 | total area of internal partitions for flats
|  |  |  | 386.34 | m2 | total meterage of internal stud for GF accomodation area
|  |  |  | 6321.156 | m2 | total area for building | 93 | 587867.508 |  | As per page 236 of SPONS 2020 (Architects edition)
Block partitions
dense aggregate block walls
| 140mm thick |  | 38.15 |  | lm |  |  |  |  | Assumed 3m high internal walls
|  |  | 38.15 |  | lm
|  |  | 38.15 |  | lm
|  |  | 40.12 |  | lm
|  |  | 16.5 |  | lm
|  |  | 16.5 |  | lm
|  |  | 12.51 |  | lm
|  |  | 20.89 |  | lm
|  |  | 7.13 |  | lm
|  |  | 17.01 |  | lm
|  |  | 13.38 |  | lm
|  |  |  | 258.49 | lm | total meterage of blockwork partitions required (retail areas - ground floor)
|  | 3 |  | 258.49
|  |  |  | 775.47 | m2 | total area of blockwork partitions required (retail areas - ground floor) | 67 | 51956.49 |  | As per page 237 of SPONS 2020 (Architects edition)
2.7.2 | Balustrades and Handrails
included in stairs (2.4.3)
2.8 | INTERNAL DOORS | [8 empty] | Assumed all doors to be fire doors
The following rates include for the supply and hang of doors, complete with all
frames, architrave, typical medium standard ironmongery set and appropriate
finish
Standard fire doors; cellular core; softwood lining; softwood architrave;
aluminuim ironmongery (lockable, self-closure); painting or polishing;
| double leaf; Oak veneered; 60 min fire resistance; polished | 84 | 2 | 168 | nr | 2x doors per flat
|  | 1 | 17 | 17 | nr | Ground floor - 1 floor
|  | 2 | 18 | 36 | nr | 18x doors in corridors (per floor) - 2 floors
|  |  |  | 221 | nr |  | 1750 | 386750 |  | As per page 239 of SPONS 2020 (Architects edition)
Ironmongery sets
Stainless steel ironmongery; euro locks; push plates; kick plates; signage;
closures; standard sets
| office door; non-locking; fire-rated | 1 | 1 | 1 | nr |  | 400 | 400 |  | Ground floor in accomodation area
| office/store; lockable; fire-rated | 94 | 1 | 94 | nr |  | 455 | 42770 |  | Allowed for in gym/common room/library/2x stores/rear doors in retail units and to all entrance rooms of flats
| standard bathroom door (unisex) | 84 | 1 | 84 | nr |  | 355 | 29820 |  | Bathrooms in flats
| fire escape door | 1 | 1 | 1 | nr |  | 2200 | 2200 |  | Ground floor in accomodation area
3 | INTERNAL FINISHES |  |  | 180 | nr | total nr of specialist ironmongery sets |  |  | 3763245.023 | As per page 239 of SPONS 2020 (Architects edition)
3.1 | WALL FINISHES
Wall finishes included in 2.7.1 Frame and partitions
3.2 | FLOOR FINISHES
Cement and sand (1:3) screeds; steel trowelled
| 100mm thick |  |  | 1488.43 | m2 | total meterage of ground floor area | 31 | 46141.33 |  | As per page 241 of SPONS 2020 (Architects edition)
Rigid tile/slab finishes (includes skirtings; excludes screeds)
| Carpet tiles; including underlay, edge grippers | [8 empty] | Assumed for accomodation areas on GF and corridor areas
| heavy domestic duty; to floors; PC Sum £38/m2 |  | 869 |  | m2 | area of accomodation area (GF)
|  |  | 112.8 |  | m2 | area of accomodation area (GF) - (block 4 lift and stairs access)
|  |  | 66.35 |  | m2 | area of accomodation area (GF) - (block 3 lift and stairs access)
|  |  |  | 1048.15 | m2
157.52
415.27
769.35
|  | 2 |  | 1342.14 | m2 | area of corridor and other areas 1st floor - not including flats
|  |  |  | 2684.28 | m2 | area of corridor and other areas 1st and 2nd floor - not including flats
|  |  |  | 1048.15 | m2
|  |  |  | 2684.28 | m2
|  |  |  | 3732.43 | m2 | total area of carpet tiles required | 75 | 279932.25 |  | As per page 242 of SPONS 2020 (Architects edition)
Flexible tiling; welded sheet or butt joint tiles; adhesive fixing
| vinyl safety flooring; 3.5mm thick heavy duty | 84 | 31.66 |  |  | area of flats
|  |  |  | 2659.44 | m2 | total area of vinyl | 68 | 180841.92 |  | As per page 242 of SPONS 2020 (Architects edition)
3.3 | CEILING FINISHES
3.3.3 | Demountable Suspended Ceilings
Armstrong suspended ceiling;
| wood veneers; perforated; concealed grid |  | 4465.29 |  | m2 |  |  |  |  | To all areas, apart from retail units
|  |  | -1048.2 |  | m2 | Retail units
|  |  | -215.96 |  | m2
|  |  | -293.47 |  | m2
|  |  |  | 2907.66 | m2 | total area of suspended ceiling required | 280 | 814144.8 | 1321060.3 | As per page 243 of SPONS 2020 (Architects edition)
4 | FITTINGS, FURNISHINGS AND EQUIPMENT
4.1 | Office furniture and equipment
Included in Provisional Sums - "loose and fixed furniture)
4.1.2 | Domestic Kitchen Fittings and Equipment
Residential fittings (volume housing)
Kitchen fittings for residential units (not including white goods). NB quality and
quantity of units can varies enormously. Always obtain costs from your preferred
supplier. The following assume medium standard units from a large
manufacturer and includes all units, worktops, stainless steel sink and taps, not
including white goods
| one person flat |  | 60 |  | nr |  | 2900 | 174000 |  | 60x student rooms
| two person flat/house |  | 24 |  | nr |  | 3200 | 76800 |  | 24x family rooms
As per page 244 of SPONS 2020 (Architects edition)
Hotel bathroom pods
Fully fitted out, finished and furnished bathroom pods; installed; suitable for
business class hotels
| accessible pod (4.50m plan area) |  | 84 |  | nr |  | 9500 | 798000 | 1048800 | All rooms accessible for disabled persons
5 | SERVICES | [8 empty] | As per page 244 of SPONS 2020 (Architects edition)
5.1 | SANITARY APPLIANCES
Included in Provisional Sums - "Mechanical and Electrical works (including Air Source Heat Pumps)
5.4 | WATER INSTALLATIONS
5.4.1 | Mains Water Supply
Please refer to Spon’s Mechanical and Electrical Services Price Book for a more
comprehensive range of rates
Hot and cold water installations; mains supply; hot and cold water distribution.
| residential; multi-storey tower |  | 2907.66 |  | m2 | total gross internal floor area of accomodation | 75 | 218074.5 |  | As per page 246 of SPONS 2020 (Architects edition)
5.6 | SPACE HEATING AND AIR CONDITIONING
5.6.1 | Space Heating and Air Conditioning
| residential; multi-storey tower; LTHW to each apartment |  | 2907.66 |  | m2 | total gross internal floor area of accomodation | 95 | 276227.7 |  | As per page 247 of SPONS 2020 (Architects edition)
5.7 | VENTILATION SYSTEMS
5.7.1 | Ventilation Systems
| residential; multi-storey tower |  | 2907.66 |  | m2 | total gross internal floor area of accomodation | 54 | 157013.64 |  | As per page 247 of SPONS 2020 (Architects edition)
5.8 | ELECTRICAL INSTALLATIONS
5.8.1 | Electric Mains and Sub-Mains Distrubition
| residential; multi-storey tower |  | 2907.66 |  | m2 | total gross internal floor area of accomodation | 130 | 377995.8 |  | As per page 247 of SPONS 2020 (Architects edition)
5.101 | LIFT AND CONVEYOR INSTALLATIONS
5.10.1 | Lifts and Enclosed Hoists
| 8-person; 4 stops; 1.6 m/s speed |  | 3 |  | nr | 3x lifts required | 110000 | 330000 |  | As per page 248 of SPONS 2020 (Architects edition)
| extra for enhanced finishes; mirror; carpet |  | 3 |  | nr | 3x lifts required | 5000 | 15000 |  | As per page 248 of SPONS 2020 (Architects edition)
| disabled platform lift single wheelchair; 400 kg; 4 stops; 0.16 m/s |  | 3 |  | nr | disabled access required | 12500 | 37500 |  | As per page 249 of SPONS 2020 (Architects edition)
5.11 | FIRE AND LIGHTNING PROTECTION
5.11.1 | Fire Fighting Systems
| residential; multi-storey tower |  | 2907.66 |  | m2 | total gross internal floor area of accomodation | 81 | 235520.46 |  | As per page 249 of SPONS 2020 (Architects edition)
5.12 | COMMUNICATION AND SECURITY INSTALLATIONS
Communication, Security and Control Systems
| residential; multi-storey tower |  | 2907.66 |  | m2 | total gross internal floor area of accomodation | 83 | 241335.78 |  | As per page 250 of SPONS 2020 (Architects edition)
5.13 | SPECIAL INSTALLATIONS
5.13.4 | Specialist Electrical/Electronic Installations
| Solar PV systems | [8 empty] | Allowed 1 system per block (8 blocks)
Solar power including 4kWp monocrystalline solar modules (12 × 185 Wp) on
roof mounting kit; certified inverter; DC and AC isolation switches and
| connection to the grid and certification |  | 8 |  | nr |  | 11000 | 88000 |  | As per page 250 of SPONS 2020 (Architects edition)
5.14 | BUILDER’S WORK IN CONNECTION WITH SERVICES
5.14.1 | Builder’s Work in Connection with Services
Offices and hotels. Gross internal floor area
| main supplies, lighting and power to landlord areas |  | 4465.29 |  | m2 | all areas | 14.6 | 65193.234 |  | As per page 251 of SPONS 2020 (Architects edition)
| central heating, electrical and lift installation |  | 4465.29 |  | m2 | all areas | 25 | 111632.25 |  | As per page 251 of SPONS 2020 (Architects edition)
| air conditioning, electrical and ventilation installations |  | 4465.29 |  | m2 | all areas | 46.5 | 207635.985 | 2361129.349 | As per page 251 of SPONS 2020 (Architects edition)
8 | SERVICES
8.2 | ROADS, PATHS, PAVINGS AND SURFACINGS
Included in Provisional Sum - "External Works"
Car Parking
Surface parking; include drains, kerbs, lighting
| surface car parking with landscape areas |  | 1243.46 |  | m2 | car park area (on site layout drawing) | 160 | 198953.6 |  | As per page 251 of SPONS 2020 (Architects edition)
| Road Crossings | [8 empty] | Drawings/design uncomplete, so assumed one of each required
| Zebra Crossing |  | 1 |  | nr |  | 27000 | 27000 |  | As per page 252 of SPONS 2020 (Architects edition)
| Pelican Crossing |  | 1 |  | nr |  | 47000 | 47000 |  | As per page 252 of SPONS 2020 (Architects edition)
8.3 | SOFT LANDSCAPING, PLANTING AND IRRIGATION SYSTEMS
8.3.1 | Plant supply, planting, maintenance and 12 months guarantee
| Seeded areas |  | 1172.19 |  | m2 | green spaces area north of site layout | 6.3 | 7384.797 |  | As per page 253 of SPONS 2020 (Architects edition)
| Turfed areas |  | 359.06 |  | m2 | green spaces area east of site layout | 8.2 | 2944.292 |  | As per page 253 of SPONS 2020 (Architects edition)
8.4 | FENCING, RAILINGS AND WALLS
8.4.1 | Chain link fencing; plastic coated
| 1.80m high | 2 | 35 | 70
|  |  | 77 | 77
|  |  |  | 147 | m2 | From rear of building to service yard - to not allow unauthroised people to access the service yard. As per Secure by Design Requirements | 37 | 5439 | 288721.689 | As per page 253 of SPONS 2020 (Architects edition)

## SPONS Regional Variations
TENDER PRICE INDEX
REGIONAL VARIATION

## BCIS Index
Series: | BCIS Materials Cost Index
Base: | 1985 mean = 100
Last Updated: | 2022-01-25
Notes:
Date | Index | Status | Percentage change
|  |  | On year | On quarter | On month
2000-01-01 | 164.5 | Firm | -0.1 | 0.2 | 0.1
2000-02-01 | 164.5 | Firm | 0.4 | 0 | 0
2000-03-01 | 165.4 | Firm | 1 | 0.6 | 0.5
2000-04-01 | 166.6 | Firm | 1.1 | 1.3 | 0.7
2000-05-01 | 167 | Firm | 1.8 | 1.5 | 0.2
2000-06-01 | 167.3 | Firm | 2.1 | 1.1 | 0.2
2000-07-01 | 167.4 | Firm | 2.3 | 0.5 | 0.1
2000-08-01 | 167.8 | Firm | 2.5 | 0.5 | 0.2
2000-09-01 | 167.9 | Firm | 2.6 | 0.4 | 0.1
2000-10-01 | 168.2 | Firm | 2.5 | 0.5 | 0.2
2000-11-01 | 168.3 | Firm | 2.3 | 0.3 | 0.1
2000-12-01 | 168.6 | Firm | 2.6 | 0.4 | 0.2
2001-01-01 | 168.1 | Firm | 2.2 | -0.1 | -0.3
2001-02-01 | 168.6 | Firm | 2.5 | 0.2 | 0.3
2001-03-01 | 168.5 | Firm | 1.9 | -0.1 | -0.1
2001-04-01 | 169.4 | Firm | 1.7 | 0.8 | 0.5
2001-05-01 | 169.8 | Firm | 1.7 | 0.7 | 0.2
2001-06-01 | 170 | Firm | 1.6 | 0.9 | 0.1
2001-07-01 | 169.9 | Firm | 1.5 | 0.3 | -0.1
2001-08-01 | 169.8 | Firm | 1.2 | 0 | -0.1
2001-09-01 | 170.1 | Firm | 1.3 | 0.1 | 0.2
2001-10-01 | 169.8 | Firm | 1 | -0.1 | -0.2
2001-11-01 | 169.5 | Firm | 0.7 | -0.2 | -0.2
2001-12-01 | 169.6 | Firm | 0.6 | -0.3 | 0.1
2002-01-01 | 169.3 | Firm | 0.7 | -0.3 | -0.2
2002-02-01 | 169.4 | Firm | 0.5 | -0.1 | 0.1
2002-03-01 | 169.6 | Firm | 0.7 | 0 | 0.1
2002-04-01 | 170 | Firm | 0.4 | 0.4 | 0.2
2002-05-01 | 173 | Firm | 1.9 | 2.1 | 1.8
2002-06-01 | 174 | Firm | 2.4 | 2.6 | 0.6
2002-07-01 | 174 | Firm | 2.4 | 2.4 | 0
2002-08-01 | 174.6 | Firm | 2.8 | 0.9 | 0.3
2002-09-01 | 175.4 | Firm | 3.1 | 0.8 | 0.5
2002-10-01 | 176 | Firm | 3.7 | 1.1 | 0.3
2002-11-01 | 175.6 | Firm | 3.6 | 0.6 | -0.2
2002-12-01 | 176.2 | Firm | 3.9 | 0.5 | 0.3
2003-01-01 | 176.3 | Firm | 4.1 | 0.2 | 0.1
2003-02-01 | 176.9 | Firm | 4.4 | 0.7 | 0.3
2003-03-01 | 176.9 | Firm | 4.3 | 0.4 | 0
2003-04-01 | 177.6 | Firm | 4.5 | 0.7 | 0.4
2003-05-01 | 178.8 | Firm | 3.4 | 1.1 | 0.7
2003-06-01 | 179.1 | Firm | 2.9 | 1.2 | 0.2
2003-07-01 | 179.4 | Firm | 3.1 | 1 | 0.2
2003-08-01 | 179.7 | Firm | 2.9 | 0.5 | 0.2
2003-09-01 | 179.8 | Firm | 2.5 | 0.4 | 0.1
2003-10-01 | 179.2 | Firm | 1.8 | -0.1 | -0.3
2003-11-01 | 179.2 | Firm | 2.1 | -0.3 | 0
2003-12-01 | 179.5 | Firm | 1.9 | -0.2 | 0.2
2004-01-01 | 179.5 | Firm | 1.8 | 0.2 | 0
2004-02-01 | 179.9 | Firm | 1.7 | 0.4 | 0.2
2004-03-01 | 181.8 | Firm | 2.8 | 1.3 | 1.1
2004-04-01 | 183.5 | Firm | 3.3 | 2.2 | 0.9
2004-05-01 | 186 | Firm | 4 | 3.4 | 1.4
2004-06-01 | 187.6 | Firm | 4.7 | 3.2 | 0.9
2004-07-01 | 189.3 | Firm | 5.5 | 3.2 | 0.9
2004-08-01 | 190.1 | Firm | 5.8 | 2.2 | 0.4
2004-09-01 | 191.1 | Firm | 6.3 | 1.9 | 0.5
2004-10-01 | 191.8 | Firm | 7 | 1.3 | 0.4
2004-11-01 | 192.3 | Firm | 7.3 | 1.2 | 0.3
2004-12-01 | 193.1 | Firm | 7.6 | 1 | 0.4
2005-01-01 | 193.5 | Firm | 7.8 | 0.9 | 0.2
2005-02-01 | 195.5 | Firm | 8.7 | 1.7 | 1
2005-03-01 | 195.9 | Firm | 7.8 | 1.5 | 0.2
2005-04-01 | 196.3 | Firm | 7 | 1.4 | 0.2
2005-05-01 | 197 | Firm | 5.9 | 0.8 | 0.4
2005-06-01 | 197.1 | Firm | 5.1 | 0.6 | 0.1
2005-07-01 | 197.2 | Firm | 4.2 | 0.5 | 0.1
2005-08-01 | 196.3 | Firm | 3.3 | -0.4 | -0.5
2005-09-01 | 195.7 | Firm | 2.4 | -0.7 | -0.3
2005-10-01 | 195.4 | Firm | 1.9 | -0.9 | -0.2
2005-11-01 | 195.8 | Firm | 1.8 | -0.3 | 0.2
2005-12-01 | 196.6 | Firm | 1.8 | 0.5 | 0.4
2006-01-01 | 197.3 | Firm | 2 | 1 | 0.4
2006-02-01 | 199.7 | Firm | 2.1 | 2 | 1.2
2006-03-01 | 201.4 | Firm | 2.8 | 2.4 | 0.9
2006-04-01 | 202.3 | Firm | 3.1 | 2.5 | 0.4
2006-05-01 | 204.6 | Firm | 3.9 | 2.5 | 1.1
2006-06-01 | 207.3 | Firm | 5.2 | 2.9 | 1.3
2006-07-01 | 208.4 | Firm | 5.7 | 3 | 0.5
2006-08-01 | 210.4 | Firm | 7.2 | 2.8 | 1
2006-09-01 | 211 | Firm | 7.8 | 1.8 | 0.3
2006-10-01 | 212 | Firm | 8.5 | 1.7 | 0.5
2006-11-01 | 212.8 | Firm | 8.7 | 1.1 | 0.4
2006-12-01 | 213.3 | Firm | 8.5 | 1.1 | 0.2
2007-01-01 | 212.5 | Firm | 7.7 | 0.2 | -0.4
2007-02-01 | 215.8 | Firm | 8.1 | 1.4 | 1.6
2007-03-01 | 217.2 | Firm | 7.8 | 1.8 | 0.6
2007-04-01 | 216.7 | Firm | 7.1 | 2 | -0.2
2007-05-01 | 219 | Firm | 7 | 1.5 | 1.1
2007-06-01 | 219.6 | Firm | 5.9 | 1.1 | 0.3
2007-07-01 | 220 | Firm | 5.6 | 1.5 | 0.2
2007-08-01 | 221.3 | Firm | 5.2 | 1.1 | 0.6
2007-09-01 | 221.9 | Firm | 5.2 | 1 | 0.3
2007-10-01 | 221.6 | Firm | 4.5 | 0.7 | -0.1
2007-11-01 | 220.9 | Firm | 3.8 | -0.2 | -0.3
2007-12-01 | 220.6 | Firm | 3.4 | -0.6 | -0.1
2008-01-01 | 220.3 | Firm | 3.7 | -0.6 | -0.1
2008-02-01 | 223.7 | Firm | 3.7 | 1.3 | 1.5
2008-03-01 | 225.5 | Firm | 3.8 | 2.2 | 0.8
2008-04-01 | 227.3 | Firm | 4.9 | 3.2 | 0.8
2008-05-01 | 229.6 | Firm | 4.8 | 2.6 | 1
2008-06-01 | 231.6 | Firm | 5.5 | 2.7 | 0.9
2008-07-01 | 234.9 | Firm | 6.8 | 3.3 | 1.4
2008-08-01 | 236.7 | Firm | 7 | 3.1 | 0.8
2008-09-01 | 238.3 | Firm | 7.4 | 2.9 | 0.7
2008-10-01 | 239.6 | Firm | 8.1 | 2 | 0.5
2008-11-01 | 238.2 | Firm | 7.8 | 0.6 | -0.6
2008-12-01 | 235.5 | Firm | 6.8 | -1.2 | -1.1
2009-01-01 | 232.2 | Firm | 5.4 | -3.1 | -1.4
2009-02-01 | 232.1 | Firm | 3.8 | -2.6 | 0
2009-03-01 | 232 | Firm | 2.9 | -1.5 | 0
2009-04-01 | 230.7 | Firm | 1.5 | -0.6 | -0.6
2009-05-01 | 229.8 | Firm | 0.1 | -1 | -0.4
2009-06-01 | 229.3 | Firm | -1 | -1.2 | -0.2
2009-07-01 | 229.3 | Firm | -2.4 | -0.6 | 0
2009-08-01 | 230.9 | Firm | -2.5 | 0.5 | 0.7
2009-09-01 | 232 | Firm | -2.6 | 1.2 | 0.5
2009-10-01 | 232.9 | Firm | -2.8 | 1.6 | 0.4
2009-11-01 | 234.8 | Firm | -1.4 | 1.7 | 0.8
2009-12-01 | 234.5 | Firm | -0.4 | 1.1 | -0.1
2010-01-01 | 235 | Firm | 1.2 | 0.9 | 0.2
2010-02-01 | 235.4 | Firm | 1.4 | 0.3 | 0.2
2010-03-01 | 236.9 | Firm | 2.1 | 1 | 0.6
2010-04-01 | 241.2 | Firm | 4.6 | 2.6 | 1.8
2010-05-01 | 245.8 | Firm | 7 | 4.4 | 1.9
2010-06-01 | 248.1 | Firm | 8.2 | 4.7 | 0.9
2010-07-01 | 249.4 | Firm | 8.8 | 3.4 | 0.5
2010-08-01 | 249.8 | Firm | 8.2 | 1.6 | 0.2
2010-09-01 | 250.4 | Firm | 7.9 | 0.9 | 0.2
2010-10-01 | 250 | Firm | 7.3 | 0.2 | -0.2
2010-11-01 | 250.3 | Firm | 6.6 | 0.2 | 0.1
2010-12-01 | 250.3 | Firm | 6.7 | 0 | 0
2011-01-01 | 251.6 | Firm | 7.1 | 0.6 | 0.5
2011-02-01 | 254.2 | Firm | 8 | 1.6 | 1
2011-03-01 | 255.8 | Firm | 8 | 2.2 | 0.6
2011-04-01 | 257.4 | Firm | 6.7 | 2.3 | 0.6
2011-05-01 | 259.4 | Firm | 5.5 | 2 | 0.8
2011-06-01 | 260.6 | Firm | 5 | 1.9 | 0.5
2011-07-01 | 260.6 | Firm | 4.5 | 1.2 | 0
2011-08-01 | 261.2 | Firm | 4.6 | 0.7 | 0.2
2011-09-01 | 260.8 | Firm | 4.2 | 0.1 | -0.2
2011-10-01 | 260.4 | Firm | 4.2 | -0.1 | -0.2
2011-11-01 | 259.8 | Firm | 3.8 | -0.5 | -0.2
2011-12-01 | 259.4 | Firm | 3.6 | -0.5 | -0.2
2012-01-01 | 258.3 | Firm | 2.7 | -0.8 | -0.4
2012-02-01 | 260.1 | Firm | 2.3 | 0.1 | 0.7
2012-03-01 | 261.6 | Firm | 2.3 | 0.8 | 0.6
2012-04-01 | 262.4 | Firm | 1.9 | 1.6 | 0.3
2012-05-01 | 262.7 | Firm | 1.3 | 1 | 0.1
2012-06-01 | 261.5 | Firm | 0.3 | 0 | -0.5
2012-07-01 | 260.9 | Firm | 0.1 | -0.6 | -0.2
2012-08-01 | 260.2 | Firm | -0.4 | -1 | -0.3
2012-09-01 | 260.3 | Firm | -0.2 | -0.5 | 0
2012-10-01 | 260 | Firm | -0.2 | -0.3 | -0.1
2012-11-01 | 259.7 | Firm | 0 | -0.2 | -0.1
2012-12-01 | 259.1 | Firm | -0.1 | -0.5 | -0.2
2013-01-01 | 259.4 | Firm | 0.4 | -0.2 | 0.1
2013-02-01 | 260.5 | Firm | 0.2 | 0.3 | 0.4
2013-03-01 | 261 | Firm | -0.2 | 0.7 | 0.2
2013-04-01 | 261.8 | Firm | -0.2 | 0.9 | 0.3
2013-05-01 | 261.9 | Firm | -0.3 | 0.5 | 0
2013-06-01 | 261.6 | Firm | 0 | 0.2 | -0.1
2013-07-01 | 260.8 | Firm | 0 | -0.4 | -0.3
2013-08-01 | 260.4 | Firm | 0.1 | -0.6 | -0.2
2013-09-01 | 260.1 | Firm | -0.1 | -0.6 | -0.1
2013-10-01 | 260.5 | Firm | 0.2 | -0.1 | 0.2
2013-11-01 | 260.7 | Firm | 0.4 | 0.1 | 0.1
2013-12-01 | 260.9 | Firm | 0.7 | 0.3 | 0.1
2014-01-01 | 261.2 | Firm | 0.7 | 0.3 | 0.1
2014-02-01 | 262.5 | Firm | 0.8 | 0.7 | 0.5
2014-03-01 | 263.4 | Firm | 0.9 | 1 | 0.3
2014-04-01 | 263.1 | Firm | 0.5 | 0.7 | -0.1
2014-05-01 | 263.4 | Firm | 0.6 | 0.3 | 0.1
2014-06-01 | 263.6 | Firm | 0.8 | 0.1 | 0.1
2014-07-01 | 263.6 | Revised | 1.1 | 0.2 | 0
2014-08-01 | 263.6 | Firm | 1.2 | 0.1 | 0
2014-09-01 | 263.8 | Firm | 1.4 | 0.1 | 0.1
2014-10-01 | 263.5 | Firm | 1.2 | 0 | -0.1
2014-11-01 | 263.6 | Firm | 1.1 | 0 | 0
2014-12-01 | 263.2 | Firm | 0.9 | -0.2 | -0.2
2015-01-01 | 262.2 | Firm | 0.4 | -0.5 | -0.4
2015-02-01 | 262.2 | Firm | -0.1 | -0.5 | 0
2015-03-01 | 261.6 | Firm | -0.7 | -0.6 | -0.2
2015-04-01 | 261.6 | Firm | -0.6 | -0.2 | 0
2015-05-01 | 261.6 | Firm | -0.7 | -0.2 | 0
2015-06-01 | 260.6 | Firm | -1.1 | -0.4 | -0.4
2015-07-01 | 259.4 | Firm | -1.6 | -0.8 | -0.5
2015-08-01 | 258.3 | Firm | -2 | -1.3 | -0.4
2015-09-01 | 257.4 | Firm | -2.4 | -1.2 | -0.3
2015-10-01 | 256.9 | Firm | -2.5 | -1 | -0.2
2015-11-01 | 256 | Firm | -2.9 | -0.9 | -0.4
2015-12-01 | 255 | Firm | -3.1 | -0.9 | -0.4
2016-01-01 | 254.5 | Firm | -2.9 | -0.9 | -0.2
2016-02-01 | 255.7 | Firm | -2.5 | -0.1 | 0.5
2016-03-01 | 255.5 | Firm | -2.3 | 0.2 | -0.1
2016-04-01 | 256.4 | Firm | -2 | 0.7 | 0.4
2016-05-01 | 258.2 | Firm | -1.3 | 1 | 0.7
2016-06-01 | 260.2 | Firm | -0.2 | 1.8 | 0.8
2016-07-01 | 260.4 | Firm | 0.4 | 1.6 | 0.1
2016-08-01 | 261.7 | Firm | 1.3 | 1.4 | 0.5
2016-09-01 | 262.5 | Firm | 2 | 0.9 | 0.3
2016-10-01 | 262.6 | Firm | 2.2 | 0.8 | 0
2016-11-01 | 264.1 | Firm | 3.2 | 0.9 | 0.6
2016-12-01 | 264.9 | Firm | 3.9 | 0.9 | 0.3
2017-01-01 | 267.2 | Firm | 5 | 1.8 | 0.9
2017-02-01 | 269.7 | Firm | 5.5 | 2.1 | 0.9
2017-03-01 | 270.6 | Firm | 5.9 | 2.2 | 0.3
2017-04-01 | 271.3 | Firm | 5.8 | 1.5 | 0.3
2017-05-01 | 272 | Firm | 5.3 | 0.9 | 0.3
2017-06-01 | 272.2 | Firm | 4.6 | 0.6 | 0.1
2017-07-01 | 272.7 | Firm | 4.7 | 0.5 | 0.2
2017-08-01 | 273.6 | Firm | 4.5 | 0.6 | 0.3
2017-09-01 | 275.3 | Firm | 4.9 | 1.1 | 0.6
2017-10-01 | 276.8 | Firm | 5.4 | 1.5 | 0.5
2017-11-01 | 278.2 | Firm | 5.3 | 1.7 | 0.5
2017-12-01 | 279.4 | Firm | 5.5 | 1.5 | 0.4
2018-01-01 | 280.1 | Firm | 4.8 | 1.2 | 0.3
2018-02-01 | 283.3 | Firm | 5 | 1.8 | 1.1
2018-03-01 | 283.4 | Firm | 4.7 | 1.4 | 0
2018-04-01 | 283.8 | Firm | 4.6 | 1.3 | 0.1
2018-05-01 | 285.3 | Firm | 4.9 | 0.7 | 0.5
2018-06-01 | 286.4 | Firm | 5.2 | 1.1 | 0.4
2018-07-01 | 287.3 | Firm | 5.4 | 1.2 | 0.3
2018-08-01 | 287.4 | Firm | 5 | 0.7 | 0
2018-09-01 | 288.6 | Firm | 4.8 | 0.8 | 0.4
2018-10-01 | 287.8 | Firm | 4 | 0.2 | -0.3
2018-11-01 | 288.4 | Firm | 3.7 | 0.3 | 0.2
2018-12-01 | 289.2 | Firm | 3.5 | 0.2 | 0.3
2019-01-01 | 288.4 | Firm | 3 | 0.2 | -0.3
2019-02-01 | 289.7 | Firm | 2.3 | 0.5 | 0.5
2019-03-01 | 292.1 | Firm | 3.1 | 1 | 0.8
2019-04-01 | 292.1 | Firm | 2.9 | 1.3 | 0
2019-05-01 | 291.4 | Firm | 2.1 | 0.6 | -0.2
2019-06-01 | 292.5 | Firm | 2.1 | 0.1 | 0.4
2019-07-01 | 292.3 | Firm | 1.7 | 0.1 | -0.1
2019-08-01 | 291.9 | Firm | 1.6 | 0.2 | -0.1
2019-09-01 | 291.3 | Firm | 0.9 | -0.4 | -0.2
2019-10-01 | 291.6 | Firm | 1.3 | -0.2 | 0.1
2019-11-01 | 289.1 | Firm | 0.2 | -1 | -0.9
2019-12-01 | 287.2 | Firm | -0.7 | -1.4 | -0.7
2020-01-01 | 285.8 | Firm | -0.9 | -2 | -0.5
2020-02-01 | 287.3 | Firm | -0.8 | -0.6 | 0.5
2020-03-01 | 288.9 | Firm | -1.1 | 0.6 | 0.6
2020-04-01 | 288.8 | Firm | -1.1 | 1 | 0
2020-05-01 | 291.2 | Firm | -0.1 | 1.4 | 0.8
2020-06-01 | 289.3 | Firm | -1.1 | 0.1 | -0.7
2020-07-01 | 289.9 | Firm | -0.8 | 0.4 | 0.2
2020-08-01 | 289.9 | Firm | -0.7 | -0.4 | 0
2020-09-01 | 291.1 | Firm | -0.1 | 0.6 | 0.4
2020-10-01 | 292.4 | Firm | 0.3 | 0.9 | 0.4
2020-11-01 | 294.2 | Firm | 1.8 | 1.5 | 0.6
2020-12-01 | 298.2 | Firm | 3.8 | 2.4 | 1.4
2021-01-01 | 299.6 | Firm | 4.8 | 2.5 | 0.5
2021-02-01 | 305.1 | Firm | 6.2 | 3.7 | 1.8
2021-03-01 | 310.2 | Firm | 7.4 | 4 | 1.7
2021-04-01 | 314.3 | Firm | 8.8 | 4.9 | 1.3
2021-05-01 | 318.9 | Firm | 9.5 | 4.5 | 1.5
2021-06-01 | 323.9 | Firm | 12 | 4.4 | 1.6
2021-07-01 | 329.7 | Firm | 13.7 | 4.9 | 1.8
2021-08-01 | 342.8 | Firm | 18.2 | 7.5 | 4
2021-09-01 | 349.3 | Firm | 20 | 7.8 | 1.9
2021-10-01 | 351.8 | Provisional | 20.3 | 6.7 | 0.7
2021-11-01 | 354.1 | Provisional | 20.4 | 3.3 | 0.7
2021-12-01 | 354.7 | Provisional | 18.9 | 1.5 | 0.2
2022-01-01 | 356.4 | Forecast | 19 | 1.3 | 0.5
2022-02-01 | 357.9 | Forecast | 17.3 | 1.1 | 0.4
2022-03-01 | 358.5 | Forecast | 15.6 | 1.1 | 0.2
2022-04-01 | 360.9 | Forecast | 14.8 | 1.3 | 0.7
2022-05-01 | 362 | Forecast | 13.5 | 1.1 | 0.3
2022-06-01 | 361.2 | Forecast | 11.5 | 0.8 | -0.2
2022-07-01 | 358.8 | Forecast | 8.8 | -0.6 | -0.7
2022-08-01 | 357.1 | Forecast | 4.2 | -1.4 | -0.5
2022-09-01 | 355 | Forecast | 1.6 | -1.7 | -0.6
2022-10-01 | 354.6 | Forecast | 0.8 | -1.2 | -0.1
2022-11-01 | 354.2 | Forecast | 0 | -0.8 | -0.1
2022-12-01 | 353.5 | Forecast | -0.3 | -0.4 | -0.2
2023-01-01 | 353.6 | Forecast | -0.8 | -0.3 | 0
2023-02-01 | 355.1 | Forecast | -0.8 | 0.3 | 0.4
2023-03-01 | 355.7 | Forecast | -0.8 | 0.6 | 0.2
2023-04-01 | 358.4 | Forecast | -0.7 | 1.4 | 0.8
2023-05-01 | 359.8 | Forecast | -0.6 | 1.3 | 0.4
2023-06-01 | 359.2 | Forecast | -0.6 | 1 | -0.2
2023-07-01 | 359.3 | Forecast | 0.1 | 0.3 | 0
2023-08-01 | 360 | Forecast | 0.8 | 0.1 | 0.2
2023-09-01 | 360.3 | Forecast | 1.5 | 0.3 | 0.1
2023-10-01 | 361.7 | Forecast | 2 | 0.7 | 0.4
2023-11-01 | 363 | Forecast | 2.5 | 0.8 | 0.4
2023-12-01 | 364 | Forecast | 3 | 1 | 0.3
2024-01-01 | 364.2 | Forecast | 3 | 0.7 | 0.1
2024-02-01 | 365.6 | Forecast | 3 | 0.7 | 0.4
2024-03-01 | 366.3 | Forecast | 3 | 0.6 | 0.2
2024-04-01 | 369.4 | Forecast | 3.1 | 1.4 | 0.8
2024-05-01 | 371.1 | Forecast | 3.1 | 1.5 | 0.5
2024-06-01 | 370.8 | Forecast | 3.2 | 1.2 | -0.1
2024-07-01 | 371.2 | Forecast | 3.3 | 0.5 | 0.1
2024-08-01 | 372.2 | Forecast | 3.4 | 0.3 | 0.3
2024-09-01 | 372.8 | Forecast | 3.5 | 0.5 | 0.2
2024-10-01 | 373.7 | Forecast | 3.3 | 0.7 | 0.2
2024-11-01 | 374.4 | Forecast | 3.1 | 0.6 | 0.2
2024-12-01 | 374.6 | Forecast | 2.9 | 0.5 | 0.1
2025-01-01 | 375.4 | Forecast | 3.1 | 0.5 | 0.2
2025-02-01 | 377.5 | Forecast | 3.3 | 0.8 | 0.6
2025-03-01 | 378.8 | Forecast | 3.4 | 1.1 | 0.3
2025-04-01 | 381.7 | Forecast | 3.3 | 1.7 | 0.8
2025-05-01 | 383.5 | Forecast | 3.3 | 1.6 | 0.5
2025-06-01 | 383.5 | Forecast | 3.4 | 1.2 | 0
2025-07-01 | 383.9 | Forecast | 3.4 | 0.6 | 0.1
2025-08-01 | 385 | Forecast | 3.4 | 0.4 | 0.3
2025-09-01 | 385.4 | Forecast | 3.4 | 0.5 | 0.1
2025-10-01 | 386.1 | Forecast | 3.3 | 0.6 | 0.2
2025-11-01 | 386.7 | Forecast | 3.3 | 0.4 | 0.2
2025-12-01 | 387.1 | Forecast | 3.3 | 0.4 | 0.1
2026-01-01 | 388 | Forecast | 3.4 | 0.5 | 0.2
2026-02-01 | 390.2 | Forecast | 3.4 | 0.9 | 0.6
2026-03-01 | 391.6 | Forecast | 3.4 | 1.2 | 0.4
2026-04-01 | 394.7 | Forecast | 3.4 | 1.7 | 0.8
2026-05-01 | 396.4 | Forecast | 3.4 | 1.6 | 0.4
2026-06-01 | 395.9 | Forecast | 3.2 | 1.1 | -0.1
2026-07-01 | 395.8 | Forecast | 3.1 | 0.3 | 0
2026-08-01 | 396.5 | Forecast | 3 | 0 | 0.2
2026-09-01 | 396.6 | Forecast | 2.9 | 0.2 | 0
2026-10-01 | 397.3 | Forecast | 2.9 | 0.4 | 0.2
2026-11-01 | 398 | Forecast | 2.9 | 0.4 | 0.2
2026-12-01 | 398.3 | Forecast | 2.9 | 0.4 | 0.1