## Draft table of times
Task | Estimated completietion date | Time spent on Task
Acquire brief |  | 1 hour
Create a plan |  | 1 week
Produce a Gant chart |  | 1 day
Identify target market |  | 1 hour
Research into the problem |  | 2 days
Analise a competitors product |  | 1 week
Update brief if needed with additions from research |  | 2 days
Create a design specification |  | 2 days
Create a variety of design ideas |  | 1 week
Choose 1 idea and confirm with peer |  | 1 day
Develop idea to meet user demands |  | 3 days
Break down product to identify each part or sub-assembly |  | 1 week 3 days
Calculate the cost for each component |  | 3 days
Show an assembly diagram of the product |  | 1 week
Develop the idea on a cad model to identify sizes and materials |  | 2 weeks
Develop the final idea and present to peers in a recognized engineering drawing standard |  | 1 week
Create a flow chart for the manufacture of the product |  | 2 days
Order any parts that are needed |  | 2 days
Manufacture the first part and test |  | 3 days
Manufacture the second part and test |  | 3 days per sub assembly
Once all sub-assemblies are manufactured, assemble and test |  | 3 days
Present product to peers for assessment |  | 2 days

## Gant chart
Date | time axis 2019-09-03 to 2020-01-08
Task / Day | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday
Acquire brief of the problem
Create a plan of steps that I will take to create a solution to the problem | bar: 2019-09-04 to 2019-09-05
Produce a Gant chart with suitable deadlines and dates of completion | bar: 2019-09-06
Identify target market that the product will be produced for | bar: 2019-09-09
Carry out research into the cause of the problem, and why it is a problem | bar: 2019-09-10 to 2019-09-11
Analyse a competitors product that is currently on the market to buy. Provide evidence of research into the problems, and an employees experience of the problem | bar: 2019-09-12 to 2019-09-13
Update brief with more detail and better specifications Specifications such as: size, colours, cost, time to build, aesthetics | bar: 2019-09-16
Make a list of any unanswered questions that need to be asked, to assist with the design process. Ensure these are answered before starting the design process | bar: 2019-09-17
Create a design specification, suggesting a list of points that the product must meet and a list that includes desirable factors of the product This list may include some features like: safety factor, compatibility, size, aesthetics, user friendliness | bar: 2019-09-18 to 2019-09-19
Begin brainstorming ideas for a solution to the product. | bar: 2019-09-20
Begin to assess ideas to find 2 - 3 suitable ones that will enter the design process. I will score them against my design specification to see which will be put forward to the design process. | bar: 2019-09-20
Create a variety of design ideas, that meet the design specification (minimum 2, maximum 6) | 2019-09-23: Problems with CAD software; 2019-09-26: Idea 1 Complete; 2019-10-01: Idea 2 complete
Score ideas and evaluate to find the most feasible solution. This may be dine using the specification or with a peer. | bar: 2019-10-02
Choose 1 idea and confirm with peer/mentor This idea will also be reviewed by a technician to see if it is reasonable | 2019-10-03: College; 2019-10-04: Holiday
Develop idea to meet user demands. Acquire the customers views of the product, and ask if it meets their needs | bar: 2019-10-08 to 2019-10-09
Break down product to identify each part or sub-assembly Begin to layout a plan on how each part is going to be made, or where it will be bought from | bar: 2019-10-10
Calculate the cost for each component, and put forward to the finance department, for funding the project | bar: 2019-10-11; 2019-10-14 to 2019-10-15
If any parts cannot be found and an alternative part can be used/has to be used specify what changes this part will cause to the design and product. | bar: 2019-10-16
Show an assembly diagram of the product, with appropriate labels and descriptions | bar: 2019-10-17
Develop the idea on a cad model to identify sizes and materials If needs be perform stress analysis using features of Autodesk | bar: 2019-10-18; 2019-10-21
Specify why I have chosen the materials for the specific parts. If necessary state any other materials that I could use | bar: 2019-10-22 to 2019-10-23
Develop the final idea and present to peers in a recognized engineering drawing standard Also present to finance department, the customer and my project leader, along with technicians | bar: 2019-10-24 to 2019-10-25
Create a flow chart for the manufacture of the product, showing a step by step action for each part Plan in checks along the way, some with peers, a and some on my own | bar: 2019-10-28 to 2019-11-01
Order any parts that are needed for the project. | bar: 2019-11-04 to 2019-11-08
Manufacture the first sub-assembly and test the assembly for any faults | 2019-11-11: No suitable material on site; 2019-11-18: No suitable material on site; 2019-11-25: No material; 2019-12-02: Some material gained, but not all, moved to sub assembly 2
Manufacture the second sub-assembly and test for any imperfections. If needed solve these problems before final assembly. | bar: 2019-12-09 to 2019-12-11; 2019-12-16 to 2019-12-17; 2019-12-20; 2019-12-26 to 2019-12-29
Once all sub-assemblies are manufactured, assemble product, so it is ready for testing | bar: 2019-12-30 to 2019-12-31
Testing of the product and rectifying any problems that occur | bar: 2020-01-01 to 2020-01-02
Apply any solutions to the product | bar: 2020-01-02
Write up build repotty and log, including photographs. Create presentation ready for peers | bar: 2020-01-03 to 2020-01-05
Analysis of my product. It will be compared and rated to the products currently in use, and I will ask the AM workers to rate my product on certain features, then carry a review to see if it suitable to be commissioned for use.
Present product to peers for a final assessment before release to the customers | 2019-09-03: September (Month 1); 2019-10-03: October (Month 2); 2019-11-03: November (Month 3); 2019-12-03: December (Deadline day); 2019-12-04: December (over scheduled); 2020-01-03: January (Over schedule)

## Design Specification
Criteria | Description | Level of importance | Why is this specification important? | How will I ensure the specification has been met?
Safety | The product that I make must be safe to use and repair or maintain if anything is needed from it. My product cannot cause harm to the user or operator. I must also keep safe whilst making the product, and consider helath and safety codes and practices. This will ensure that nobody will get hurt or injured when making and using my product. | Extremely High | To ensure that everyone is safe during the build and when using the product This will ensure there are fewer injuries, and that the product meets the safety requirements to be used in the factory. | I will ensure a risk assessmnet has been carried out for the are I wil be working in. If there is an accident I will report it, and to ensure my product is safe, it will undergo numerous tests.
Quality | The product must be of high quality in order to endure a life in a working factory, where it may be used upto 20 times a day The parts that I use must be of high quality and easy to maintain Overall finish and apperance, along with construction quality must be of high satisfaction, so that it does not fall apart, and also so it looks professional, as guests may see this product. | Significantly High | Quality is important because it needs to be able to withstand daily use therfore the quality of the build and materials need to be of high standards. | I will ask a peer to perfrom a quality assessment on my completed product, and the parts that were used during the assembely.
Performance | My solution must be able to perform to the users expectations, and beyond them if possible. It must perform well enough so that it is a sustainable option for the company, and is not slowing down production time within the factory. | Significantly High | This feature is important because the product needs to better than other products curently on the market This performance will ensure that my target market wil want to buy and use my product as it will be the best performing on the market. | I will test my product against the current way of measuring and cutting wire, to see if its any quicker.
User friendliness | The product should be easy and simple to use. The user must be able to operate the product with very little training, and not spend a lot of time setting the machine up. | High | User friendliness is an important factor, because my product should be easy and simple to use It shouldn’t cause the user frustration trying to use it. If its not user friendly, then the customer will not want to use my product. | To test this I intend to get an employee who has never seen my product, to test it and see if they can use it easily.
Aesthetics | My solution shouldn’t be an "eye sore", yet it doesn’t need to be perfectly shaped, it should be easy enough to look at, yet not look out of place in the environment it is placed in. My design needs to have a proffesional look to it, and not a 'homemade' apperance | Medium | This should be considered, so that it does not look out of place, or so that it is not unwanted due to its apperance. | I will ask for an impartial view from a collegue.
Environment | The design and manufacture of the product should consider and in any way possible try to help the environment, wether that be re-using scrap materials, or turning off my computer after I havce finished designing. The finished product should also not look out of place in the environment it is palced in, the aesthetics should suit where it is being used. | High | The environment is important, as it covers 2 aspects of the product. Firstly my product should fit in the envirnment it is going to be placed in, and other environment sit will be placed in. Secondly my product needs to ensure it attempts to help the environment in any way possible | I will only use sustainable sources to gain my material from and used recycled materials where possible.
Cost | My total cost to research, design and build my product needs to be lower than other competitiors on the market, along with staying reasonable for the companys finance department. | Significantly High | This is important as my product needs to be a reasonable price to buy and also to make. This is so that it can be cheaper than competitors products | I will keep all recipts from purchases to enable me to stay within my budget. I will aslo shop around for the best price on parts
Materials | The materials that I use to build the solution must be approprite so that they can withstand the forces and tasks being carried out. Also the materials should try to consider the environment, so sourcing them from a sustainable souce, and possibly re-using materials from other projects. | Significantly High | Materials is of high importance becaue without using the right materials my product will not be able to withstand the daily use withing the facotry. It may also not be able to perform as expected as that materil will have the wrong properties for that job. My product may also become very expensive if I use the wrong materials, therfore careful and correct material selction is very important. | I will analise each material I plan on using to ensure it is correct for that job. I can also consult a peer on my material choices. However each material will be labelled and shown in my designs, so they can all be approved before I begin manufacturing my product.
Ergonomics | The product should be able to be used by almost anyone, and fit the average standards. Ergonomics could be incoperated into my product in the display size, or any levers or buttons that may need to be used. The position should be easy to reach for everyone. | Medium | My product should be easy to work with for the general population and should fit to average statisitcs. | I will get a number of impartial employees to test my product, to see if they can all use it comfortably.
Function | The soution needs to solve the problem. Therfore my solution should allow workers to measure wire and cable more accurately, and easier, along with cut it to that specific length. | Significantly High | The product needs to function in the way in which it was designed. It should allow workers to measure and cut cable more accurately and quicker. | I will perform various tests to ensure it performs in the wayit was designed to do.
Size | It should not be over the reccomended maximum size that I will ask in my questions, and should either fit on the worktop or fit in the space where the old cable dispensing stand was, however it should be easy to move. | High | My product needs to fit to the specifications I was given, and be able to fit on the worktop bench, or be able to replace the old unit that is currently in use. | To check this specification I will measure my product, and keep the size tolerance in mind during designing and building.
Shape | The apparatus should be a regualr shape, with no acute angles, or strange sides that do not fit inside the reccomended dimensions. | Medium | The product should not have any sharp endges or be of an ireegular shape, that it does not fit securely in the space I am allocated. | I will get my designs checked by a peer before beginning the assesmbly process, therfore they can alert me to any irregularities in the shape.
Target market | My product needs to appeal to the AM250 manufacturing team, as they are my main target market for this product,a nd will be the ones who have to use this product Therfore I need to ensure I make it to their standards and specifications | Significantly High | Target market is an important consideration, as if my design doesn’t appeal to them, then they may not want to use it, or purchase my product. The design and final product need to suit the demands and people in the AM 250 build area. | To do this, I will get a small select of my target market to come and review my product. This will ensure that it is suitable for them and people who would also be interested in my product.
Solves the problem | Is my product a suitable solution to the problem that I was made aware of, and asked to create a solution to? | Extremely high | If my product does not solve the problem, then it will be rendered useless. | My product will be tested and also reviewed by various people to see if it does solve the problem. I will also allow my product to go into use to test it. This will be before the unveilling at the christmas party.
Time to build | The product must suit my timescale and be able to be built within that time frame. | High | If my product cannot be built in the timescale, then the time has been wasted, and the company has been cost money due to it. | I will ensure i assess my project ideas with the build time I have allocated myself.

## Score Sheet
Criteria | Predicted rating | Current rating for product in use | Idea 1 | Idea 2 | Idea 3 | Idea 4 | Idea 5 | Comments | Rating for product 1 Motor driven | Rating for product 2 1m circumference wheel | Comments
Safety | 5 | 5 | 4 | 3 | 4 | 5 | 5 | All use electricity, and have moving parts | 3 | 4
Quality | 4 | 4 | 3 | 4 | 4 | 5 | 5 | Depends on my build quality | 4 | 4
Performance | 4 | 3 | 4 | 4 | 4 | 5 | 3 | All my ideas will perform as required | 4 | 4
User friendliness | 3 | 5 | 3 | 3 | 5 | 4 | 3 | Not all are quicker to set up than a rule | 3 | 5
Aesthetics | 2 | 2 | 3 | 3 | 4 | 3 | 0 | The apperance isnt a key issue | 3 | 4
Environment | 3 | 3 | 2 | 4 | 3 | 3 | 0 | I wil try to use recycled materials | 4 | 3
Cost | 4 | 5 | 2 | 4 | 4 | 1 | 2 | Some products are more complex than others, causing costs to be higher, some higher than my budget allows | 4 | 4
Materials | 4 | 5 | 3 | 4 | 4 | 3 | 0 | My material choices will depend on the component | 4 | 4
Ergonomics | 2 | 5 | 4 | 3 | 3 | 4 | 0 | My product may not suit everyone, but I will build it with the aim to suit most people | 3 | 3
Function | 4 | 5 | 4 | 4 | 4 | 5 | 5 | All my product will do what they are designed to | 4 | 4
Size | 3 | 3 | 2 | 4 | 3 | 3 | 0 | Some ideas are alot bigger than others | 4 | 3
Shape | 2 | 2 | 4 | 3 | 3 | 3 | 0 | Most of the ideas are finished in a cube shape | 3 | 3
Target market | 4 | 5 | 4 | 4 | 4 | 2 | 4 | They are all aimed at the identified target market | 4 | 4
Solves the problem | 5 | 5 | 4 | 5 | 5 | 4 | 5 | I cannot test the idea to see if it solves the problem. | 5 | 5
Total | 49 | 57 | 46 | 52 | 54 | 50 | 32 |  | 52 | 54
| Okay | Excellent | Acceptable | Okay | Good | Okay |  |  | Okay | Good
Ratings are from 1 to 5; 5 being a good feature, and 1 being a very low feature. For example,cost: If the product is expensive it scores 1, if its cheap it scores 5. 1 = poor 2= acceptable 3= okay 4= good 5= excellent
0-45 = poor 45-48 = acceptable 49-52= okay 53-56 = good 57+ = Excellent

## Parts List
Part | Place of Purchase | Quantity | Cost of part | Part number | Required for? | Purchased
Magetic sensor | RS Components | 1 | 2.58 | 765-9337 | Sensor for metre readout | Yes
Sensor readout display | RS Components | 1 | 15.97 | 185-5980 | Tell how many revs have been done | Yes
Magnet to activate sensor | RS Components | 1 | 2.91 | 846-339 | Activate sensor | Yes
50mm ø 50mm Rubber shaft/wheel | Trackside spares | 1 | 3.5 | PD1276 | Grip on Wire | Yes
1m circumference circle | Ebay | 1 | 25 | 221921270967 | Measure metres | Yes
ball bearing 17 x 40 x 17.5 | Ebay | 1 | 8.2 | 190525077325 | Go inside the wheel to allow it roll freely | Yes
Tension springs | RS Components | 1 | 12.62 | 121-359 | Tension wheels to cable | Yes
100mm x 750 mm Aluminium plate(5mmx800x400) | Ebay/Rich McCallum/LC02 | 1 | 16.7 | 161064303572 | Make side plates | Yes
40 mm x 100 mm ø mild steel bar (Integrex Steve Mitchell) | Ebay | 1 | 8 | 271621202226 | Adaptar for rubber wheels onto 10 mm bar | Yes
Handle | RS Components | 1 | 7.71 | 859-149 | Turn the device | Yes
ball bearing 10 x 19 x 5 | RS Components | 2 | 4.94 | 619-0064 | Go in end plates to support bar | Yes
10mm ø x 160mm mild steel bar (Miskin stores) | Ebay | 1 | 3.2 | 271621202226 | Bottom roller drive shaft, has to fit only handle available | Yes
17mm ø x 100 mm mild steel bar (Miskin Ø3/4) | Ebay | 1 | 3.75 | 271621202226 | Top roller driveshaft. Has to fit bearing | Yes
17mm Shaft collar | Simply bearings.co.uk | 5 | 1.55 | ZP171224 | stop bearings from sliding around | Yes
60mm ø x 30mm aluminuim bar (Integrex) |  | 1
|  | Total | 127.77

## Flowchart
Stage | Task | Allocated time | Tools required | Required materials | If checkpoint fails | Comments
1 | Gather materials for subassembly 1 (2 drive shafts) |  | Lathe, knife tool, Medium diamond knurl tool micrometer (0-25mm and 25-50mm), screw cutting tool Pitch gauges, 6 inch steel rule, Centre drill and drill bits | Mild steel bar (50mm ø) Rubber wheels | N/A
2 | Setup bar in lathe, and turn down ends to required diameters |  | Knife tool, Lathe | Mild steel bar (50mm ø) | N/A
3 | Ensure diameters are to the required dimensions |  | Range of Micrometers |  | Turn down diameters to a suitable, or accurate diameter if possible, or return to stage 2 with a new bar.
4 | Option a) drill and tap either end of bar a to the required dimensions for a bolt option b) screw cut/ run a die down the ends so a wing nut can be threaded on |  | Drill bit set, centre drill, tap, Jacobs chuck and tailstock, screw cutting tool, pitch gauge, die |  | N/A
5 | Check the thread is clean, and square |  | nut/bolt depending on option, engineers square |  | return to stage 2 with a new bar, or if possible reduce thread size
6 | apply a medium diamond knurl to centre of bars |  | Knurl tool | Rubber wheel | N/A
7 | Place rubber drive wheels onto the newly knurled surface |  |  | Rubber wheel | N/A
8 | Ensure wheel cannot be easily moved |  |  |  | Apply a new knurl to the diameter, or reduce diameter, apply a new knurl, and make a pressure bushing to sit between the two
N/A
9 | Gather materials for 2 end plates |  | Milling machine | Aluminium plate | N/A
10 | Create datum edges and reduce plate to size. |  |  |  | N/A
11 | Ensure plate is correct dimensions |  | Digital callipers |  | Return to stage 10 with a new plate
12 | Create the slot that will allow the top roller to move freely |  |  |  | N/A
13 | Check slot is the correct dimensions |  | Digital callipers |  | adjust dimensions, or return to stage 10 with a new plate.
14 | Drill and recess the bottom hole for bushing and drive shaft. |  |  |  | N/A
15 | Check that this hole is the correct dimensions |  | Digital callipers |  | adjust dimensions, or remake plate.
16 | Drill and tap the holes onto the bottom and top of the plates, for the base and top plates to bolt into. |  |  |  | N/A
17 | Check that threads are clean and square |  | Engineers square, appropriate bolt |  | Clean threads, or re make plate with square threads.
18 | Repeat steps 10 - 17 for second end plate |  |  |  | N/A
N/A
19 | Assemble the bar drive shafts into the end plates, and fit springs |  |  |  | N/A
20 | Manufacture measure wheel on laser cutter/purchase a trundle wheel |  |  |  | N/A
21 | Mount measuring wheel to the drive shaft |  |  | Measuring wheel | N/A
22 | Ensure all is fitted together securely |  | Check bolts with appropriate spanners/screwdrivers |  | disassemble and reassemble, finding the loose component.
N/A
23 | Mount sensor onto wheel, and briefly connect to output screen |  |  | Sensor, magnet, cables | N/A
24 | Test sensor position and securely mount, remove screen on completion |  | N/A |  | Ask electrician to help determine problem.
25 | Manufacture frame |  |  |  | N/A
26 | Attach wheels, and measuring device |  |  |  | N/A
27 | Mount screen in a suitable location |  |  |  | N/A
28 | Check to see if readout works, and is easily readable |  | Power supply |  | Ask electrician to help determine problem.
29 | Attach appropriate cutters to a suitable location on the frame, with steel cable
30 | Check to see if the whole device works |  | Power supply |  | Fault find and resolve issue
31 | Perform accuracy tests and vigorous testing to ensure all criteria is met |  | Check sheet | Wire | Find defective part and replace with a new component