Method Statement

| Project title: | Tai Tarian Office Build |
| --- | --- |
| Reference: | TT052020 |
| Date: | 31.03.20 |

Description of Works

| Scope: | Steel frame erection |
| --- | --- |
| Method of work: | Transportation to site ready for erection |
| Duration: | 1 week |
| Sequence: | Transportation to site: - Organise storage facility - Coordinate with Site Manager as per erection date/site accessibility - Installation of steel columns - Erection of steel frame Access to site: - Ensure site has a sufficient road build for truck access, transportation of frame and crane loader for installation - Clear location plan for communication between site workers and deliveries On delivery: - Appropriate storage available – clean and dry - Unloading methods to be agreed with Site Manager - Use of appropriate belts for lifting and placing – attention to detail here to avoid damage to frame prior to and during installation - All materials to be inspected by Site Manager and any damaged components replaced Erection - local resource for equipment hire - Site Manager to report on site conditions to ensure it’s ready for major works - Employ specialist contractors for the build – local if possible - Weather conditions must be suitable for erection purposes Transportation to site - Beams should be appropriately arranged on appropriate transport - Unloading to be completed by crane - Access road must be made accessible for the width/length – allow for turning space - Deliver the sections close to the point of erection to limit movement/damage of materials - Ensure I-Beams and rafters are positioned appropriately for ease of build - Consider storage to avoid contamination – dry area, above ground, packaged appropriately and ventilated - Clash detection to have been undertaken prior to manufacture - Positioning of anchor points to be confirmed by Site Manager as per specification - Equipment to be inspected prior to lifting. Staff numbers to be accounted for and recorded. - Temporary anchor points to be set up whilst erection underway to avoid swinging materials - Crane to stay in position until anchor points are secured |
| Location: | Baglan Bay |

Resources required

| Personnel: | Crane driver, labour, Site Manager, Site Engineer |
| --- | --- |
| Supervision: | Site Manager |
| Plant/Equipment | Crane |
| Materials: | Steel frame, anchor bolts |

Assessment of Risks

| Access to site: | Temporary road made accessible |
| --- | --- |
| Area of work: | Baglan Bay |
| Staff at risk: | Whole site |
| Staff competence (sufficient training completed?) | Previously confirmed. |

Control Measures in place

| Permits: | n/a |
| --- | --- |
| Security: | Site security |
| Other: | n/a |