Assignment 1

Project Management

Module : LCBB5005

Student name:  Aurora Catalina Jipa

Student number :1815962

Lecture name : Molly Jack

Table of Contents

Introduction	2

College building project management plan	3

Scope of project	3

Milestone activities	3

Change management plan	3

Communication managing plan	4

Plan for cost management	5

Plan for schedule management	6

Work breakdown structure	11

Plan for Risk management	11

Resources calendar	12

Challenges for project execution	12

Concern of stakeholders	13

Benefit realisation	13

Used project PRINCE 2 approach	13

Conclusion	14

References	15

List of Figures

Figure 1: Project cost planning	6

Figure 2: Project Gantt chart	10

Figure 3: College building construction WBS	11

List of Tables

Table 1:Milestone table	3

Table 2: Communication plan	4

Table 3: Scheduling of project	6

Table 4: Risk plan	11

Table 5: Resources calendar	12

Introduction

This study is based on a project management plan in which various concepts are being studied. This plan shows the study of various strategies, skills, competence, procedure & expertise that are required to achieve the aims of the project. Main & actual project outcomes are limited to its expenditure. This project plan is based on building construction for a college. For simplifying this project PRINCE 2 methodology is being used. With the help of this methodology practical planning realities, planning execution, and planning implementation are taking place most quickly. It also used to provide professional advancement potential within their work. This project is going to be completed within the budget of £50,000. Total time duration which is being taken to complete the project is just nearly about 6 months.

This report is going to indicate the plan for project management that is to make construction of college buildings. All the things are used to be defined in such a way that identification of the project and its feasibility can be understood properly. Within this plan, a communication plan, change plan, cost, schedule, risk management-based plan is shown. Stakeholders concern, benefits realization, resources calendar & its execution challenges are also studied in it.

College building project management plan

Scope of project

Main aim of this project is to construct a building for the college by proper planning, creation, implementation & construction. Through this project construction of this building is going to be completed within defined duration and budget too. Another scope towards this is just to clarify the project specification under which it covers instructions, documents, and facilities that have been implemented within this constructed building. Through this project successful completion of the building construction is going to be made in a very efficient way (Khusain, 2019).

Milestone activities

Within this project, there are many of the milestone activities, which followed to get complete within their definite time. They are defining the completion of this project which follows various tasks and sub-task to completed it. For getting an accurate and successful completion of this construction work within a defined budget and duration these milestones are to be followed (Eik-Andresen, et. al., 2016). Thus, these required milestones for this project are being represented in a following table:

Table 1:Milestone table

| Project Milestones | Description | Duration for its completion |
| --- | --- | --- |
| Project starting | This is the first milestone activity under which project initiation is used to be done through its documentation. | 33 days |
| Project Resources collection | Second milestone activity indicates the gathering of resources like material, machines, equipment, etc. | 24 days |
| Project modelling | This is third milestone under which designing, model, or sketch of a constructed building is to be made. | 17 days |
| Project implementation | Under this milestone activity construction work is going to take place. | 44 days |
| Project closing | This is the last milestone that defines the completion of the project. | 13 days |

Change management plan

For high performance within the construction or building project, it provides some carefully controlled changes. Within this project change management, some terms are included which are used to be like organised approach, documentation inclusion, records, planning, flow, procedure, time table, cost, and also operation of plan. During the construction of this college building, major changes are used to be followed (Halou, et. al., 2019). Such like:

- Construction market standard is must be followed.

- Relocation plan should be implemented from one building to another building transfer.

- Company plan and requirement should be reorganized.

- By using the company brief project planning, its practices are going to be changed.

- Changing or moving from one constructional technology to another one.

Communication managing plan

For making the project completed successfully communication plan is very necessary. This is going to define as the communication strategy or structure by which project stakeholders are completed successfully. This plan is very helpful which provides contact-based references that have been required for this lengthy construction project. Stakeholder which are included within this project provides communication by understanding this communication plan. Within this project communication functions of the stakeholders are defined by this plan only. This plan indicates the contact mapping in which project expectations, stakeholder's behavioural actions, and discussion are being displayed effectively. There are many of the parties which are somewhere related to this college building construction project that is being shown with their communication in a communication management plan (LaPrad, 2018). Thus, a communication plan is going to represent the Knowledge that has to be transmitted which indicates that were to do communication, with whom and when to communicate. Thus, for this project communication plan is being presented as follows:

Table 2: Communication plan

| Mode of communication | Explanation | Format | Participated people | Occurrence | Owner | Deliverable outcomes |
| --- | --- | --- | --- | --- | --- | --- |
| Report status weekly | This is showing a project report progress or status every week. | Through the use of email. | Sponsor of the project, supervisor of project, and manager. | Every week. | Project manager | Project status report |
| Meeting on weekly project progress | This is to make a meeting with all the stakeholders about project progress. | Person to person | Team leader and team members. | Every week. | Team leader | Updating process with project status. |
| Weekly review of project | This is used to indicates the project review every week. | Through calling. | Team leader and team members. | Every month. | Project manager | Project status as per weekly basis presentation |
| Design review of project | This is just to identify the whole status of the project model or the blueprint. | Face to face. | Project manager, project supervisor, and contractors. | Every week. | Project manager | Designing a package for this project. |
| Project closing review | It shows the completion of project with its review. | Face to face. | Project manager, project supervisor, and contractors | On required basis. | Project manager | Closure of project. |

Plan for cost management

Cost management planning is one of the vital parts of the college building project. As it is a very lengthy project in which costing factor within whole project managed by the project manager. A project manager is only the person who is going to manage a certain calculation of the cost or expenses that has been taken place within this completion of the project task. His responsibilities are just to estimate the expenses discrepancies with the help of earned benefits process. For providing the financial adjustment project manager is making his control over the program and task to be completed. Total set or estimated budget for this project is just £50,000. This defined budget is fixed which means in this construction, not more this budget is can be used within this college building construction (Vasista, et. al., 2017). Cost management plan shows in the figure below which is indicating the cost status, distribution of the cost, and also overall costing details. It represents that total costing which has been expended in this project is £49,760. Thus, this all is going to be represented in below figure in the form of project cost overview which defines the overall costing of this project:

Figure 1: Project cost planning

Plan for schedule management

This project is based on the construction of college buildings which is going to be a lengthy project. Thus, for this project, a proper management plan is used to be developed sufficiently by the usage of MS project that is going to be presented with its deadlines. Within this project, various tasks or activities are scheduled within a given time duration. It represents the task with a proper sequence so that the completion of the task is taking place in a fast manner and in a more efficient way. Estimated amount of working is being presented with required cycle for the completion of its project work package. This project is going to be more focused on a defined projection. To distribute the task and resources this schedule is developed that helps to complete the project more efficiently. Within this particular schedule duration, task, and also the required cost for each an individual task is being represented (Li, et. al., 2017). Thus, this particular scheduling is going to be represented in following table 1 and figure of Gantt. Chart:

Table 3: Scheduling of project

| Tasks Names | Durations | Starting time | Finishing time | Predecessor | Resources list with Names | Costing |
| --- | --- | --- | --- | --- | --- | --- |
| College building construction project | 131 days | Fri 31-07-20 | Fri 29-01-21 |  |  | £ 49,760 |
| Project starting | 33 days | Fri 31-07-20 | Tue 15-09-20 |  |  | £ 13,600 |
| Defining scope & objectives | 5 days | Fri 31-07-20 | Thu 06-08-20 |  | Construction manager, Contractor, Sponsor, Supervisor | £ 4,000 |
| Cost constraints | 11 days | Fri 07-08-20 | Fri 21-08-20 | 2 | Working manager, Labour | £ 4,400 |
| Budget setting | 9 days | Mon 24-08-20 | Thu 03-09-20 | 3 | Working manager, Labour | £ 3,600 |
| Project documentation | 8 days | Fri 04-09-20 | Tue 15-09-20 | 4 | Supervisor | £ 1,600 |
| Ending of project starting | 0 days | Tue 15-09-20 | Tue 15-09-20 | 5 |  | £ 0 |
| Project resources collection | 24 days | Wed 16-09-20 | Mon 19-10-20 | 1 |  | £ 7,040 |
| Material selection and gathering | 7 days | Wed 16-09-20 | Thu 24-09-20 |  | Construction manager | £ 1,680 |
| Machine gathering | 6 days | Fri 25-09-20 | Fri 02-10-20 | 8 | Supervisor, Working manager | £ 2,160 |
| Construction site survey | 6 days | Mon 05-10-20 | Mon 12-10-20 | 9 | Supervisor | £ 1,200 |
| Outlining construction details | 5 days | Tue 13-10-20 | Mon 19-10-20 | 10 | Construction manager, Working manager | £ 2,000 |
| Ending of project resource collection | 0 days | Mon 19-10-20 | Mon 19-10-20 | 11 |  | £ 0 |
| Project modelling | 17 days | Tue 20-10-20 | Wed 11-11-20 | 7 |  | £ 6,440 |
| Design of Project | 3 days | Tue 20-10-20 | Thu 22-10-20 |  | Contractor, Labour, Supervisor | £ 1,800 |
| 2D & 3D model | 4 days | Fri 23-10-20 | Wed 28-10-20 | 14 | Labour | £ 960 |
| Sketch documentation | 4 days | Thu 29-10-20 | Tue 03-11-20 | 15 | Construction manager, Contractor, Working manager | £ 2,240 |
| Construction blueprint | 6 days | Wed 04-11-20 | Wed 11-11-20 | 16 | Construction manager | £ 1,440 |
| Ending of project modelling | 0 days | Wed 11-11-20 | Wed 11-11-20 | 17 |  | £ 0 |
| Project implementation | 44 days | Thu 12-11-20 | Tue 12-01-21 | 13 |  | £ 18,640 |
| Foundation work | 8 days | Thu 12-11-20 | Mon 23-11-20 |  | Contractor, Labour | £ 3,200 |
| Wall & framing | 12 days | Tue 24-11-20 | Wed 09-12-20 | 20 | Contractor, Labour | £ 4,800 |
| Lintel & roof construction | 13 days | Thu 10-12-20 | Mon 28-12-20 | 21 | Construction manager, Labour | £ 6,240 |
| Finishing work | 11 days | Tue 29-12-20 | Tue 12-01-21 | 22 | Labour, Working manager | £ 4,400 |
| Ending of Project implementation | 0 days | Tue 12-01-21 | Tue 12-01-21 | 23 |  | £ 0 |
| Project closure | 13 days | Wed 13-01-21 | Fri 29-01-21 | 19 |  | £ 4,040 |
| Construction inspection | 5 days | Wed 13-01-21 | Tue 19-01-21 |  | Contractor, Sponsor | £ 1,800 |
| Review on construction | 4 days | Wed 20-01-21 | Mon 25-01-21 | 26 | Contractor, Supervisor | £ 1,440 |
| Construction handover | 4 days | Tue 26-01-21 | Fri 29-01-21 | 27 | Supervisor | £ 800 |
| Ending of Project | 0 days | Fri 29-01-21 | Fri 29-01-21 | 28 |  | £ 0 |

Gantt chart:

Figure 2: Project Gantt chart

Work breakdown structure

As this project is going to be completed within six months under which different milestone activities are to be followed. Proper suited process of project work is being analysed by the WBS which makes an easy understanding of the work plan. This work is used to be presented in the following WBS form (Sutrina, et. al., 2017).

Figure 3: College building construction WBS

Plan for Risk management

There are a large number of the risk that is taking place within this college building project. These particular risk with its management are being presented in the following table (Bahamid & Doh, 2017):

Table 4: Risk plan

| Name of risks | Explanation | Impact on project | Occurrence | Risk dependency |
| --- | --- | --- | --- | --- |
| Safety risks | Within construction field, there are very high chances of accidents happening. Safety risks are developed due to the unskilled labour which can take false usage of things by which chances of accident increases. These risks are very common and very severe thus they are needed to mitigate or to manage in a very fast manner. | Very severe impact. | More common. | On labours and team members. |
| Budget risks | This risk is can take place, when due to certain reason construction cost get above the defined budget cost. This is mainly taking place when the budget is not planned properly. | High | Least common | Project manager |
| Legal risks | They are taking place when no legal approval has been followed by the government. Thus, every project required legal approval before construction. | Very high | Not so common | Project supervisor or manager |
| Environmental risks | This is taking place due to the bad environment condition that has been due to natural disasters (Chatterjee, et. al., 2018). | Very high | Common | Project supervisor or manager |

Resources calendar

Table 5: Resources calendar

| Resource names | Total working hours | Standard rates | Participation | Initial |
| --- | --- | --- | --- | --- |
| Contractor | 328.0 hours | £ 20.00/ hour | High | C |
| Working manager | 368.0 hours | £ 20.00/ hour | High | WM |
| Sponsor | 80.0 hours | £ 25.00/ hour | High | S |
| Labour | 568.0 hours | £ 30.00/ hour | High | L |
| Construction manager | 320.0 hours | £ 30.00/ hour | High | C |
| Supervisor | 288.0 hours | £ 25.00/hour | High | S |

Challenges for project execution

Few challenges that have been taking place during the implementation of this project are like:

- Conflicts between resources is one of the challenges that has been taking place when different tasks are having need of same resources. Thus, these conflicts hamper the project execution.

- Less accountability provides continued coordination and tracking on this particular project whose working defined as a challenge.

- Difficulty within execution takes place due to draining money, incentives & energy that is going to distract the focused work on completion of project.

- Delay of project is also sometimes taking place by which whole execution is going to be hampered.

Concern of stakeholders

They are be represented as follows:

- Ethics are the main important concern as they must be followed to increase the rational behaviour towards the workers. Under this no worker is going to cheat towards its work thus it is stakeholder concern.

- Governance is another concern which defines as governance policies by which construction is going to be completed successfully. A proper guideline is needed to be followed otherwise project gets down.

- Disclosure of confidential and sensitive detailed answers for the workers is very concerning as it hampers the whole project (De Massis, et. al., 2018).

Benefit realisation

- Collaboration with the contractors provides a structured timetable by which completion of the task is adequately taking place & in a fast way also.

- It provides the completion of the project in a highly accurate manner with proper costing also.

- Another benefit is just to provide very high-quality innovation such that the project is used to be complete in a successful manner.

- Definite resources are used to be completed efficiently.

Used project PRINCE 2 approach

This approach is being used to provide the proper coordination and management of the project efficiently. Under this methodology, various advantages are used to be provided for this particular project (Vaníčková, 2017). These advantages are to be like:

- It provides minimal costing.

- Provides limited efficiency.

- Provides a better point to contact.

- Simplest handling it provides.

- Capital utilization is used to provides.

Conclusion

All of this study indicates the project management plan for building construction projects. From this report, it can be concluded that for increasing the performance of this particular project planning and scheduling of its is necessary. Prince 2 approach is very effective as define the successful completion of this project. This report also concludes that, terms included in this plan like communication planning, cost planning, and scheduling with its scope are very important. Thus, they all represent the deep analysis of the project by following which this building construction project is going to be completed successfully.

References

Bahamid, R.A. and Doh, S.I., 2017, November. A review of risk management process in construction projects of developing countries. In IOP Conference Series: Materials Science and Engineering (Vol. 271, No. 1).

Chatterjee, K., Zavadskas, E.K., Tamošaitienė, J., Adhikary, K. and Kar, S., 2018. A hybrid MCDM technique for risk management in construction projects. Symmetry, 10(2), p.46.

De Massis, A., Audretsch, D., Uhlaner, L. and Kammerlander, N., 2018. Innovation with Limited Resources: Management Lessons from the G erman M ittelstand. Journal of Product Innovation Management, 35(1), pp.125-146.

Eik-Andresen, P., Johansen, A., Landmark, A.D. and Sørensen, A.Ø., 2016. Controlling a multibillion project portfolio-milestones as key performance indicator for project portfolio management. Procedia-Social and Behavioral Sciences, 226, pp.294-301.

Halou, M., Samin, R. and Ahmad, M., 2019. Impacts of change management on risk and cost management of a construction projects. Journal of Project Management, 4(2), pp.157-164.

Khusain, N.M.Y.M., 2019. The role of using value-oriented management in the scope of construction projects.

LaPrad, 2018. How to Create a Project Management Communication Plan | Team Gantt. Available at: https://www.teamgantt.com/blog/project-management-communication-plan (Accessed: 31 July 2020).

Li, X., Xu, J. and Zhang, Q., 2017. Research on construction schedule management based on BIM technology. Procedia engineering, 174, pp.657-667.

Sutrisna, M., Ramanayaka, C.D. and Goulding, J.S., 2018. Developing work breakdown structure matrix for managing offsite construction projects. Architectural engineering and design management, 14(5), pp.381-397.

Vaníčková, R., 2017. Application of PRINCE2 project management methodology. Studia Commercialia Bratislavensia, 10(38), pp.227-238.

Vasista, T.G.K., 2017. strategic cost management for Construction project success: a Systematic study. Civil Engineering and Urban Planning: An International Journal (CiVEJ), 4(1), pp.41-52.