International Hotel Management (BA)

BMIH6007 INTERNATIONAL MEETINGS MANAGEMENT FOR THE HOTEL INDUSTRY

ASSIGNMENT 2: EVENT STRATEGIC PLANNING AND DELIVERY CONSIDERATIONS FOR AN INTERNATIONAL MEETING / EVENT

REPORT

EVENT FOCUS - THEME: VISIT WALES’ - “YEAR OF CROESO 2025

Student Name: Bianca Negreanu

Student ID: 2244613

Level: 6

Module Leader: Kathryn Flynn

Table of Contents

Introduction	3

Event Cycle	3

Event Concept	5

Aim and Objectives of Meeting/Event	6

Event Management	7

Event Budget	8

Industry Trends/Issues/Impacts	9

Situational and Cultural Considerations	11

Conclusions	14

Reference List	15

# Introduction

The Welsh Welcome Experience will be a 5-day encompassing cultural event aimed at commemorating the distinctive culture and language of Wales, history, food, and all the natural scenery. The event coincides with the Year of Croeso 2025 campaign that mainly seeks to make Wales one of the leading international tourism destinations by reflecting on its rich sense of place and celebrated Welsh hospitality (Visitwales, 2025). The festival will be held in the main regions of Wales like Welsh urban culture, Snowdonia National Park, and the scenic Wales, and nature outdoor activities and their locations to capture the various components of Welsh identity.

The cultural tourism orientation of this event is critical, as it has several reasons. First, the world has changed about the tendency to choose experiential tourism approaches when the tourists want to engage in the natural cultural life of the country they are travelling to (Wales.com, 2025). The event will fulfil this need by offering the guests rich experience of Welsh traditions and activities that will include tasting local cuisine, verbal guided heritage tour, and performance of Welsh traditional music. The event will be focused on international tourists along with the professionals of the MICE industry with an emphasis on the appeal to high-value tourists in Europe, North America, and Asia that want to explore tourism opportunities in the cultural and adventure sector.

The event has been selected based on increasing demand of cultural tourism in the world and the possibility of utilising the Year of Croeso program to bring Wales into international limelight. This event will mainly offer both cultural exchange and an economic advantage to the local tourism in Wales because of linking visitors with the true Welsh identity.

# Event Cycle

The Event Cycle is a systematic model that consists of 3 primary phases namely pre-event, event execution, and post-event assessment. All these phases are crucial towards smooth running of the event and support of the objectives (Getz and Page, 2019). It enables one to break down the tasks, duties, and schedules in a systematically identified way, so that every part of the event is taken care of.

Figure 1: Visit Wales’ “Year of Croeso” 2025 Program

(Source: Visitwales, 2025)

Pre-Event Stage

Pre-event stage comprises preliminary planning, which entails establishment of event concept, provision of the venues, budgeting, and marketing. In this event, areas like Cardiff, Snowdonia, and Pembrokeshire will be chosen to have an all-inclusive Welsh experience. One of the tasks within this phase will involve collaborations with the local businesses to sponsor them and to use online marketing platforms to market to the international tourists (Rogers and Wynn-Moylan, 2022). A project management plan will be prepared that will contain schedules of obtaining permits, concluding of the contracts with vendors, and the schedule of the performances and workshops.

Event Execution

The emphasis during the event execution stage will be on accomplishing the scheduled activities. There will be high engagement of the guests and on the logistics of the event. The activities will consist of various performances, interactive lessons, cuisine, and outdoor adventures. The role of the staff management will be key in ensuring that all the activities are made easier and problem-solving in real-time will be introduced to solve unexpected situations, e.g. weather shake-ups or logistical problems (Smith, 2012).

Post-Event Evaluation

The post-event phase will entail assessment of event success within the context of satisfaction of the guests, financial outcomes, and the effect that the event has upon the tourism profile of Wales. Survey and focus groups will be used to collect feedback and the financial audit will be used to determine the revenue generation and cost-effectiveness (Fox et al., 2014). This step will guarantee the event will be successful in the long-term and provide prospective enhancements in chances of repeat performances.

The coverage of the Event Cycle will allow the Welsh Welcome Experience to be coherent, properly conducted, and constantly advanced, which will make it known as a flagship cultural event (O’Toole, 2011).

# Event Concept

Welsh Welcome Experience will give a multi-sensory immersive cultural, landscape, and traditions trip through Wales to delegates and guests. Every day of the festival will be devoted to another aspect of the Welsh heritage, so that visitors could have an exciting and lively experience (Bowdin et al., 2023).

| Day | Focus | Activities and Experiences |
| --- | --- | --- |
| Day 1 | Welsh Heritage | Cardiff Castle Tour, traditional Welsh music and dance performances, and historical exhibitions. |
| Day 2 | Welsh Cuisine and Drinks | Welsh culinary tastings (e.g., Welsh Rarebit, lamb dishes), cooking classes, and whisky/gin tastings. |
| Day 3 | Welsh Arts and Crafts | Local artisans’ exhibitions, hands-on craft workshops, and textile weaving demonstrations. |
| Day 4 | Outdoor Adventures in Wales | Guided hiking tours in Snowdonia, wildlife spotting in Pembrokeshire, and mountain biking. |
| Day 5 | Welsh Language and Community | Welsh language classes, local community performances, and traditional Welsh dance workshops. |

Table 1: Event Concept

(Source: Self-made)

Day 1 will focus on engaging the visitors in Welsh culture by taking them on a historical tour around Cardiff Castle and by holding interactive performances by the local Welsh artists. Day 2 will be dedicated to Welsh food, and guests will get to know such traditional Welsh dishes as Welsh rarebit and take classes on cooking. On Day 3, the event will feature Welsh art and Welsh craftsmanship and the guests will have a chance to experience what it means to make Welsh pottery and a Welsh woven cloth (Gov.wales, 2025).

Day 4 will serve the external people by providing a varied adventure sporting programs in Snowdonia National Park and Brecon Beacons. These will comprise guided ascending, mountain biking, and wildlife viewing. The last day of the festival will be dedicated to the Welsh language, as guests will be engrossed in language classes and the performances of local Welsh choirs and Welsh traditional dancers (Gov.wales, 2025).

This is a multi-faceted itinerary that enables the delegates to get a many-sided view of Wales be it of its historic tradition or in the modern dynamic, stimulating culture so the delegates have a true and interesting experience of Wales (Allen et al., 2022).

# Aim and Objectives of Meeting/Event

| Objectives | SMART Criteria |
| --- | --- |
| Objective 1: Increase international visitor numbers to Wales by 20% by the end of 2025. | - Specific: Increase international visitors. - Measurable: 20% increase. - Achievable: Through targeted marketing and industry partnerships. - Relevant: Aligns with Wales’s tourism goals. - Time-bound: By December 2025. |
| Objective 2: Secure £150,000 in sponsorships for the event by June 2025. | - Specific: Secure sponsorships. - Measurable: £150,000 in sponsorships. - Achievable: Through partnerships with Welsh businesses, tourism boards, and industry players. - Relevant: Supports event funding and operations. - Time-bound: By June 2025. |
| Objective 3: Achieve a minimum of 90% satisfaction rate from attendees, with at least 75% expressing interest in visiting Wales again. | - Specific: Measure satisfaction through surveys. - Measurable: 90% satisfaction. - Achievable: Through post-event feedback. - Relevant: Ensures the event meets its objectives. - Time-bound: Post-event analysis. |

Table 2: SMART Objectives

(Source: Self-developed)

The aim of the event is to heighten the awareness of international tourism in Wales through waving its cultural assets in the Year of Croeso 2025. The SMART goals are consistent with, quantifiable, attainable, applicable, and time-based targets. Objective 1 will aim at enhancing the number of international guests with the use of global marketing campaigns. Objective 2 is centred on achieving organisational sponsorship by local businesses and industry players in Wales, as these are necessary to make the event viable. Objective 3 is to ensure high levels of attendees’ satisfaction, so that the guests can have an enriching experience that will motivate them to come back to the place of Wales in the future (Price, 2021).

# Event Management

The Welsh Welcome Experience will be subject to effective operational logistics management, staffing, and overall guest involvement management. There are various important positions and capabilities necessitating a smooth running of the event (Stielke et al., 2024).

| Role | Required Skills |
| --- | --- |
| Event Manager | Project management, budgeting, risk management, and communication skills. |
| Cultural Experts | In-depth knowledge of Welsh culture, history, language, and traditions. |
| Marketing and PR Team | Digital marketing expertise, partnership management, and event promotion. |
| Customer Service | Multilingual support, guest relations, and problem-solving. |
| Operations Team | Logistics coordination, vendor management, and time management. |

Table 3: Event Management

(Source: Self-created)

The entire event will be supervised by the event managers where all the logistics will be carried out within the budget and on time. The genuine material will be offered by the cultural specialists, starting with the history of Welsh ancestry to the lessons in the traditional language. The marketing team will focus on creating global awareness and it will utilise digital media like social media, email, and influencer partnerships. One of the functions that the operations team will do is the logistics, which is the transportation, feeding, as well as keeping the daily activities well-organised (Groom, 2022).

# Event Budget

| Sources | Amount (£) | Percentage of Total Income |
| --- | --- | --- |
| Ticket Sales | £250,000 | 50% |
| Sponsorships | £150,000 | 30% |
| Merchandise Sales | £45,000 | 10% |
| Government Grants | £45,000 | 10% |
| Total Income | £400,000 | 100% |

Table 4: Income Breakdown

(Source: Self-made)

| Category | Amount (£) | Percentage of Total Expenditure |
| --- | --- | --- |
| Venue Hire | £100,000 | 20% |
| Talent and Performers | £75,000 | 15% |
| Marketing and Promotion | £50,000 | 10% |
| Logistics and Operations | £100,000 | 20% |
| Catering and Hospitality | £75,000 | 15% |
| Staff and Volunteers | £45,000 | 10% |
| Contingency Fund | £45,000 | 10% |
| Total Expenditures | £400,000 | 100% |

Table 4: Expenditure Breakdown

(Source: Self-made)

The projected breakeven is £400,000. These sources of income are diversified with the key sources being the ticket sales and the sponsorships. The spending is widespread between the needed categories and there is no advertisement on the quality and experience of the event. It has also prepared the contingency fund of 10% of the total expenditure to cover unexpected expenses. This budget is in accordance with industry standards of large-scale culture events and will guarantee financial sustainability.

# Industry Trends/Issues/Impacts

The role of knowing the trends within the industry is critical to the success of the Welsh Welcome Experience program.

Figure 2: Wales Natural Beauty

(Source: Wales.com, 2025)

Rise in Experiential Tourism

Holiday makers are demanding more realistic and intensive experiences. As explained by the world tourism organisation, cultural tourism has expanded and destinations where tourists get local experience have increased tourists visiting such destinations (Ifans, 2022). The Year of Croeso mainly conforms to this trend by putting great focus on the rich culture and traditions of Wales.

Sustainability Focus

Sustainable tourism practices are gaining more demand. To follow this trend, the event will also adopt environmentally-friendly practices, including minimization of waste, development of local products, as well as the use of transport among others properly (Tan and Zhu, 2022).

Digital Transformation

Online marketing and engagement are necessary. The event will capitalize on social media, virtual reality previews, and mobile applications that will help to deliver a better experience to the attendees and reach a wider audience (Dillette and Ponting, 2021).

Economic Impact

Cultural events are a huge contribution to the local economies. For example, the National Eisteddfod, which will take place in Wrexham is anticipated to bring in 150,000 visitors and results of up to £16 million into the local economy (Ponting, 2021). This mainly highlights the economic gains that may also accrue by the Welsh Welcome Experience.

Post-Pandemic Travel Behaviour

There has been a change in the travel behaviour after the pandemic, where safety and wellness are the central focus. To address these issues, the event will mainly be inclusive of health measures and wellness programs (Kitchen, 2022).

Technological Integration

The use of advanced innovation options and technology can mainly improve the overall experiences of events. Touring historical locations as well as live-streaming performances using augmented reality are some of the areas that will also be examined to attract technology-conscious eventgoers (Kitchen, 2022).

Cultural Preservation

It is more focused on preservation and the encouragement of local cultures. Traditional Welsh music and dance and crafts will be presented in the event, so that no part of the cultural heritage is ignored or lost (Kitchen, 2022).

Global Competition

Wales is competing with other destinations that have the same culture. The Year of Croeso campaign is one chance to outshine Wales due to its unique culture and hospitality (Kitchen, 2022).

# Situational and Cultural Considerations

It is crucial to deal with cultural and situational factors to achieve success in the event.

SWOT Analysis

| Strengths | Weaknesses |
| --- | --- |
| Strong cultural heritage and traditions | Limited international awareness of Wales |
| Government support through the Year of Croeso campaign | Seasonal weather variability affecting outdoor events |
| Established tourism infrastructure and transport network seamlessly | Potential language barriers for non-Welsh speakers |
| Diverse landscapes and attractions attracting huge numbers of visitors globally | Limited direct international flight connections |

| Opportunities | Threats |
| --- | --- |
| Growing interest in cultural and sustainable tourism | Economic downturns affecting travel budgets and system |
| Collaboration with international travel partners | Competition from other European destinations |
| Development of year-round tourism initiatives | Environmental challenges impacting outdoor events |

Table 5: SWOT Analysis

(Source: Self-made)

The SWOT analysis has shown that Wales has the following strengths that may serve as an opportunity to make the event more attractive; the cultural heritage and government support. There should be issues like poor international publicity and fluctuation of the weather season, which should be settled by determining the marketing strategies and contingency plan. The opportunities comprise the increasing trend in cultural tourism and possible cooperation with other partners and the threats are recession and environmental concerns (AlWaer et al., 2021). Through taking into consideration these factors, the event can be made to reach its full potential success.

PESTLE Analysis

| Factors | Description | Impact on the Event |
| --- | --- | --- |
| Political | Welsh Government's commitment to boosting tourism through campaigns like Year of Croeso and policies promoting local economic development. | The event benefits from strong governmental support, facilitating funding and promotion through government channels. |
| Economic | Economic factors like inflation, travel costs, and consumer spending patterns affect travel decisions (Kamariotou et al., 2021). | Economic downturns could reduce disposable income for tourism, but government-backed initiatives like Year of Croeso can mitigate this impact (Kamariotou et al., 2021). |
| Social | There is a growing preference for experiential and cultural tourism, with millennials and Generation Z driving demand for authentic experiences. | The event taps into the demand for cultural experiences, offering immersive activities that appeal to socially conscious travellers. |
| Technological | Rapid advancements in digital marketing, social media platforms, and virtual event technologies. | The event will leverage social media and virtual tours to attract international audiences and engage them before and during the event. |
| Legal | UK and European regulations on health and safety, data protection (GDPR), and event licensing. | The event must adhere to strict safety standards and legal requirements, ensuring compliance with local regulations for crowd control and data management. |
| Environmental | Growing focus on sustainability and eco-friendly practices in tourism, including carbon footprint reduction and waste management. | The event will incorporate sustainable practices, such as sourcing local produce, reducing plastic usage, and minimizing event waste to align with industry standards. |

Table 6: PESTLE Analysis

(Source: Self-made)

The PESTLE analysis brings several external factors that will affect the Welsh Welcome Experience. Politically, the Welsh Government had been firmly supportive of the Year of Croeso 2025, which gives a firm basis to work upon advertising the event. Economically, global uncertainties may have a negative impact on tourism spending (Bradbury and Bhattacharya, 2022). However, the high cultural nature of the event countermeasures such uncertainty. Socially, due to the increasing popularity of experiential tourism, the event will be well-placed and technological progress will allow conducting successful marketing locally and online. Enforcement of safety and data protection laws is vital about the legal and sustainability of the event location in terms of environmental factors to ensure that the occasion is in tandem with global sustainability forces (Evans, 2024). It is necessary to take these factors into consideration to maximise the success and sustainability of the event.

# Conclusions

Welsh Welcome Experience involves a strategic plane of displaying the culture and hospitality that exists in Wales to the world. The event taps into the trends in tourism coupled with authenticity and immersion into tradition by falling within the Year of Croeso 2025 program. The event will advertise the image of the Welsh international tourism, will enhance the local economies, and will aid in cultural exchange between nations given that it was well planned, that there was involvement of stakeholders involved in the process and good financial plan. The combination of the environmental practises with technological development viability will also ensure the experience of the attendant is even better and will play a role in supporting the sustainability of the event over time to facilitate the objectives of tourism in Wales.

# Reference List

Allen, J., Harris, R. and Jago, L., (2022). Festival & special event management. John Wiley & Sons.

AlWaer, H., Rintoul, S. and Cooper, I., (2021). Design-led events in collaborative planning: improving post-event planning and delivery. Archnet-IJAR: International Journal of Architectural Research, 15(3), pp.774-799.

Bowdin, G.A., Allen, J., Harris, R., Jago, L., O'Toole, W. and McDonnell, I., (2023). Events management. Routledge.

Bradbury, T. and Bhattacharya, S., (2022). Employing multiple delivery partners: demonstrating success through an event case study. International Journal of Event and Festival Management, 13(3), pp.351-368.

Dillette, A. and Ponting, S.S.A., (2021, June). Diffusing innovation in times of disasters: considerations for event management professionals. In Journal of Convention & Event Tourism (Vol. 22, No. 3, pp. 197-220). Routledge.

Evans, N.G., (2024). Strategic management for tourism, hospitality and events. Routledge.

Fox, D. et al. (2014) Doing events research: from theory to practice. Routledge: Oxford

Getz, D. and Page, S. (2019) Event studies: theory, research and policy for planned events. 3rd Edition. Routledge: Oxford

Gov.wales, (2025), Visit Wales invites world to feel the 'hwyl' in 2025, [Online], Available at: https://www.gov.wales/visit-wales-invites-world-feel-hwyl-2025 [Accessed on 30th October 2025]

Groom, D., (2022). Research Framework for the Archaeology of Wales 2021-2026: Maritime Chapter.

Ifans, R., (2022). Stars and Ribbons: Winter Wassailing in Wales. University of Wales Press.

Kamariotou, V., Kamariotou, M. and Kitsios, F., (2021). Strategic planning for virtual exhibitions and visitors’ experience: A multidisciplinary approach for museums in the digital age. Digital Applications in Archaeology and Cultural Heritage, 21, p.e00183.

Kitchen, E., (2022). Strategic event planning. In The Routledge Handbook of Business Events (pp. 32-42). Routledge.

O’Toole, W. (2011) Events feasibility and development: from strategy to operations. Elsevier: Oxford

Ponting, S.S.A., (2021). “I am not a party planner!”: setting a baseline for event planners' professional identity construction before and during COVID-19. Journal of Hospitality and Tourism Insights, 4(2), pp.205-223.

Price, W.R., (2021). Mining for tourists: An analysis of industrial tourism and government policy in Wales. Tourism Planning & Development, 18(4), pp.435-456.

Rogers, T. Wynn-Moylan, P (2022) Conferences and conventions: a global industry. 4th Edition. Routledge: Oxford

Smith, A. (2012) Events and urban regeneration: the strategic use of events to revitalise cities. Routledge: Oxford

Stielke, A., Pastorino, G., Heimburg, D.V., Ness, O. and Prilleltensky, I., (2024). Country deep dive on the well-being economy: Wales.

Tan, Y. and Zhu, Z., (2022). The effect of ESG rating events on corporate green innovation in China: The mediating role of financial constraints and managers' environmental awareness. Technology in Society, 68, p.101906.

Visitwales, (2025), Year of Croeso in Wales, [Online], Available at” https://traveltrade.visitwales.com/ [Accessed on 30th October 2025]

Wales.com, (2025), You’re invited to feel the “hwyl” in Wales during 2025, [Online], Available at: https://www.wales.com/news/united-kingdom/year-croeso-campaign-wants-welsh-visitors-feel-hwyl [Accessed on 30th October 2025]