## Slide 1: Theory of Change and Logical Framework: Principles and Examples The Digital Professional for Health and Care
Dr Taiwo Adedeji BSc MSc MRes PhD

## Slide 2: Learning outcomes
Understand the frameworks and models for planning and evaluating change
Apply the Theory of Change to digital health implementation

## Slide 3: Outline
Logical framework (Logframe)
Theory of Change (ToC)
ToC case study

## Slide 4: Logical Framework (Logframe)
Logframes involve designing, monitoring, and evaluating inputs, activities, outputs, and outcomes logically to achieve desired results
Logframes are linear and easier to model with less difficulty
Notes: A logic model is a theory-based framework used in evaluating and summarising how an intervention works by identifying pathways from inputs/activities to intended outcomes (Rogers, 2008). Logic models are usually graphical representations that outline the inputs, activities, outputs, outcomes and impact of complex interventions (Maden et al., 2017).

## Slide 5: Logframe Matrix
(Bullen, 2021)

## Slide 6: Logframe components
Goal
Outcome
Output
Activity
(Bullen, 2021)

## Slide 7: Logframe Matrix
Example
(Bullen, 2021)

## Slide 8: Theory of Change (ToC)
Origins in Theory-Based Evaluation (TBE)
Similar to Logframe but complex
Start with long-term goal(s) and map backwards
Revision of maps (1st, 2nd, 3rd…nth versions)
Stakeholder engagement

## Slide 9: ToC definitions
Weiss popularised the term and modestly defined a ‘theory of change’ as:
a theory of how and why an initiative will work (Weiss, 1995).
UK’s Department for International Development (DFID) defined ToC as:
“an outcomes-based approach which applies critical thinking to the design, implementation and evaluation of initiatives and programmes intended to support change in their contexts” (Vogel, 2012).
Notes: This definition seems simplistic, yet it is foundational.
ToC has evolved over the years, considering the ever-changing complexities in international development programmes.

## Slide 10: ToC map
Long-term change
Assumptions
Measurable outcomes
Interventions
Outputs
Inputs
Notes: Despite not having a single way of designing ToCs, good quality ToCs should entail specific components such as long-term goals, assumptions, interventions, measurable outcomes, inputs and outputs (Connell & Kubisch, 1998).

## Slide 11: ToC Components
Component | Definition
Long-term change | The desired goal the stakeholders want to achieve.
Problems | The challenges facing the current paper-based health records workflow as highlighted by the stakeholders.
Stakeholders | The people directly or indirectly involved or affected by the success or failure of the EHR implementation.
Assumptions | The beliefs that specify the underlying reasons for the logical connections that exist between the ToC elements.
Inputs | The activities/tasks carried out around the intervention.
Interventions | The initiatives or programmes embarked on to influence the desired outcomes; in this study, the EHR implementation and sustainability arrangements.
Outputs | The tangibles resulting from the inputs and the intervention.
Measurable effects | The immediate indicators that could be traced to the implementation process and are readily usable for evaluation. These measures can be quantitative or qualitative.
Wider benefits | The generalisable pointers that could guide the stakeholders as to how possible is the long-term change.
Notes: In the context of this study, the ToC components have the following definitions

## Slide 12: ToC as a process and product
A process that articulates the mechanisms of change
The process involves setting out a long-term goal and go in a reverse direction to specify assumptions and identify preconditions to bring about the desired outcomes (Taplin et al., 2013)
The process leads to the product (ToC map), usually in versions
Notes: ToC process articulates the mechanisms of change. The process begins when stakeholders set out a long-term goal and go in a reverse direction to specify assumptions and identify preconditions to bring about the desired outcomes (Taplin, Clark, Collins, & Colby, 2013)
The process leads to the product (ToC map), which is usually developed in versions before, during and after programme implementations.

## Slide 13: ToC vs Logframe
ToC | Logframe
Messy and complex | Neat and tidy
Shows all pathways | Shows programme-specific pathways
Gives the big picture | Gives a detailed description of the programme
Flexible map | Linear diagram
Detailed assumptions | Basic assumptions
Tool for planning, design and evaluation | Tool for mainly monitoring

## Slide 14: ToC Case Study
Move from paper to electronic records
Electronic Health Record (EHR) implementation @ Festac Primary Health Centre, Lagos
Theory of Change (ToC) approach
  Interviews
  EHR system selection and evaluation
  Workshop

## Slide 15: Initial ToC
Pre-Implementation
An initial version of the Theory of Change for the scheduled EHR implementation in Festac PHC (Adedeji, 2021).

## Slide 16: Revised ToC
Actual Implementation
A revised version of the Theory of Change for EHR implementation in Festac PHC, including a workshop at MedInfo Conference 2019 (Adedeji, 2021).
Notes: A revised version of the Theory of Change for Electronic Health Records implementation in Festac PHC, including a workshop at MedInfo Conference 2019.

## Slide 17: Long-term change
Assumption | Source
EHR system is sustainable | Policymakers, Practitioners, Programme designer

## Slide 18: Wider benefits
Assumption | Source
EHR is used regularly | Policymakers, Practitioners, Programme designer
Clinicians are maintaining supportive attitude towards digital transformation | Policymakers, Practitioners, Programme designer

## Slide 19: Measurable effects
Assumption | Source
Hardware equipment and EHR software remain intact and is maintained regularly | Policymakers, Practitioners, Programme designer
Clinicians are making use of EHR regularly for delivering health services to patients | Practitioners, Policymakers
Stakeholders are learning from EHR usage and data | Policymakers, Practitioners, Programme designer, Health informatics experts

## Slide 20: Outputs
Assumption | Source
Implementer and technicians possess the relevant skills for installing the equipment | Policymakers, Programme designer
Staff are available to complete a feedback form | Practitioners
EHR is designed with the relevant system attributes | Practitioners, Programme designer
Health informatics experts contribute to workshop questions | Health informatics experts, Programme designer

## Slide 21: Intervention
Assumption | Source
Procured items are delivered in time to the health facility | EHR implementation
Stakeholders streamline requirements for EHR system | Practitioners, Programme designer
EHR users key in patient data correctly | 
Implementer provides training and support | …Policymakers
Questions relating to the EHR implementation are being asked by workshop participants | Health informatics experts, Programme designer

## Slide 22: Inputs
Assumption | Source
Arrangements are made with the relevant vendors | Programme designer
Items with their specifications and costs are listed in a spreadsheet | EHR implementation
Stakeholders have flexible schedules | Practitioners
Staff give consent to participate in the EHR system evaluation | 
ANC and immunisation records are tracked manually (paper) | 
Workshop paper is accepted | Programme designer

## Slide 23: Stakeholders & Problems

## Slide 24: Generic ToC
Future Implementation
A generic version of Theory of Change for Electronic Health Records implementation, without context-specific details (Adedeji, 2021)

## Slide 25: Findings
ToC maps
  Initial
  Revised
  Generic
Interview themes
  Readiness
  Expectations
  Sustainability
Technical implementation
Workshop

## Slide 26: Study conclusions
Impact summary
  Research dissemination
  Benefits realisation through the case study
  Collaboration with global community.
What was previously known
  ToC approach is effective in engaging stakeholders
  ToC is both a process and a product
  ToC has little public use in health informatics projects.

## Slide 27: Study contributions
ToC is useful in formulating the preconditions to achieve the long-term goal to improve the delivery of MCH.
ToC is a powerful tool to guide the implementation of health informatics projects.
Development of ToC maps to guide new EHR implementations in LMICs.

## Slide 28: Summary
Logframes are useful frameworks to design and monitor change projects
ToC approach is helpful in understanding the bigger picture of digital health interventions

## Slide 29: References
Adedeji, T. A. (2021) Realising the benefits of digital health implementation in a middle-income country: Applying Theory of Change in Nigerian primary care. University of Portsmouth. Available at: https://researchportal.port.ac.uk/en/persons/taiwo-adedeji/studentTheses/
Bullen, P. B. (2021) How to write a logical framework (logframe). Available at: https://tools4dev.org/resources/how-to-write-a-logical-framework-logframe/ (Accessed: 24 November 2021).
Taplin, D. H. et al. (2013) Theory of Change Technical Papers: A series of papers to support development of theories of change based on practice in the field. New York: ActKnowledge. Available at: http://www.theoryofchange.org/wp-content/uploads/toco_library/pdf/ToC-Tech-Papers.pdf.
Vogel, I. (2012) Review of the use of ‘Theory of Change’ in international development. London: GOV.UK. Available at: https://www.gov.uk/government/news/dfid-research-review-of-the-use-of-theory-of-change-in-international-development.
Weiss, C. H. (1995) ‘Nothing as Practical as Good Theory: Exploring Theory-Based Evaluation for Comprehensive Community Initiatives for Children and Families’, New Approaches to Evaluating Community Initiatives: Concepts, Methods, and Contexts. doi: 10.1177/1356389003094007.