## Sheet1
Option Group B |  |  |  |  | Assessor | IV | Alternate IV
|  | PD15 | Project Management |  |  | Graham Orr | Ged Edwards
Learning Outcome - The learner will: |  | Assessment Criterion - The learner can: |  |  | Demonstrated by
1.1 | Understand the core project standards and characteristics within the business and commercial context | 1.1.1 | Define a project’s characteristics and environment | Task 1 Report 2,500 words | Prepare a report seeking authority to undertake a project within a setting with which you are familiar such as your place of work. The report is to cover: 1. What the project sets out to achieve and how it affects the rest of the organisation or setting in which it is found (Assessment criteria 1.1.1 and 1.2.1). 2. The structure (numbers of people and their skills) of the project team (Assessment criteria 1.3.1, 1.4.1 and 2.1.3). 3. The tasks and roles of the people forming the project team (Assessment criterion 3.1.1).
1.2 | Understand the various controlled project styles, approaches, triggers, products and processes | 1.2.1 | Define the processes and activities that comprise a project
1.3 | Understand the factors comprising a successful project organisation | 1.3.1 | Select a typical project organisational structure
1.4 | Understand the circumstances that bring about the need for project programme management and how project programmes can be managed effectively | 1.4.1 | Define an appropriate structure for project programme management
2.1 | Understand the process of project start-up and the components of a project’s terms of reference (TOR) | 2.1.1 | Define the processes involved within project start-up, terms of reference and effective project management | Task 2 Report 2,500 words | Prepare a Project Initiation Document (PID) for project proposal in Task 1. The PID is to cover: 1. The Terms of Reference (TOR) for the Project (Assessment criteria 2.1.1 and 2.1.2). 2. The work packages that make up the stages and the stages that make up the project (Assessment criteria 2.2.1, 3.5.1 , 4.1.1, 4.1.2 and 4.2.1 ). 3. The sequence of events in the form of a PERT diagram and accompanying analysis of probability of completion (Assessment criteria 2.2.1 and 2.2.2.
|  | 2.1.2 | Plan and prepare a project brief
|  | 2.1.3 | Appoint an appropriate project management team |  | Prepare a report seeking authority to undertake a project within a setting with which you are familiar such as your place of work. The report is to cover: 1. What the project sets out to achieve and how it affects the rest of the organisation or setting in which it is found (Assessment criteria 1.1.1 and 1.2.1). 2. The structure (numbers of people and their skills) of the project team (Assessment criteria 1.3.1, 1.4.1 and 2.1.3). 3. The tasks and roles of the people forming the project team (Assessment criterion 3.1.1).
2.1 | Understand the various tools used to initiate, plan, control and monitor project progress | 2.2.1 | Define the tools needed to plan, control and monitor a given project | Task 2 Report 2,500 words | Prepare a Project Initiation Document (PID) for project proposal in Task 1. The PID is to cover: 1. The Terms of Reference (TOR) for the Project (Assessment criteria 2.1.1 and 2.1.2). 2. The work packages that make up the stages and the stages that make up the project (Assessment criteria 2.2.1, 3.5.1 , 4.1.1, 4.1.2 and 4.2.1 ). 3. The sequence of events in the form of a PERT diagram and accompanying analysis of probability of completion (Assessment criteria 2.2.1 and 2.2.2.
2.3 | Know the typical methods and steps involved in project planning and flow | 2.3.1 | Define the methods and steps involved in the planning and flow of a given project
2.4 | Understand the processes, activities and dependencies within a project | 2.4.1 | Define the planning sequences, processes, activities and dependencies of a given project
2.5 | Understand the risks associated with projects and the action to be taken | 2.5.1 | Implement a project risk analysis | Task 3 Report 2000 words | Prepare a Standing Operating Procedure (SOP) that details how the project is to be controlled and any how risks that may affect the successful completion are to be monitored and their effects eliminated or minimised (Assessment criteria 2.5.1, 3.2.1, 3.3.1, 3.4.1, 3.6.1 and 4.2.1).
3.1 | Understand the scope of responsibility and associated tasks when directing a project | 3.1.1 | Define the processes and issues that arise when directing a given project | Task 1 Report 2,000 words | Prepare a report seeking authority to undertake a project within a setting with which you are familiar such as your place of work. The report is to cover: 1. What the project sets out to achieve and how it affects the rest of the organisation or setting in which it is found (Assessment criteria 1.1.1 and 1.2.1). 2. The structure (numbers of people and their skills) of the project team (Assessment criteria 1.3.1, 1.4.1 and 2.1.3). 3. The tasks and roles of the people forming the project team (Assessment criterion 3.1.1).
3.2 | Know the procedures to be followed to maintain quality standards within a project | 3,2,1 | Define authorisation and acceptance procedures and their associated inputs and outputs for a given project | Task 3 Report 2,000 words | Prepare a Standing Operating Procedure (SOP) that details how the project is to be controlled and any how risks that may affect the successful completion are to be monitored and their effects eliminated or minimised (Assessment criteria 2.5.1, 3.2.1, 3.3.1, 3.4.1, 3.6.1 and 4.2.1).
3.3 | Understand what needs to be controlled and monitored during the life of a project | 3.3.1 | Define the processes that need to be controlled and monitored during the life of a given project
3.4 | Understand project assessment and monitoring techniques | 3.4.1 | Identify the risk triggers, progress, tolerances and need for re-evaluation of a given project
3.5 | Know how to manage the stages of a project and maintain stage criteria | 3.5.1 | Define the stage control, stage boundaries, boundary control and reports for a given project | Task 2 Report 2,500 words | Prepare a Project Initiation Document (PID) for project proposal in Task 1. The PID is to cover: 1. The Terms of Reference (TOR) for the Project (Assessment criteria 2.1.1 and 2.1.2). 2. The work packages that make up the stages and the stages that make up the project (Assessment criteria 2.2.1, 3.5.1 , 4.1.1, 4.1.2 and 4.2.1 ). 3. The sequence of events in the form of a PERT diagram and accompanying analysis of probability of completion (Assessment criteria 2.2.1 and 2.2.2.
3.6 | Understand the techniques used to analyse project risk and the actions aimed at risk minimisation | 3.6.1 | Analyse the risks associated with a given project and implement risk minimisation techniques | Task 3 Report 2000 words | Prepare a Standing Operating Procedure (SOP) that details how the project is to be controlled and any how risks that may affect the successful completion are to be monitored and their effects eliminated or minimised (Assessment criteria 2.5.1, 3.2.1, 3.3.1, 3.4.1, 3.6.1 and 4.2.1).
4.1 | Understand project control and configuration management techniques | 4.1.1 | Identify and implement appropriate change control techniques | Task 2 Report 2,500 words | Prepare a Project Initiation Document (PID) for project proposal in Task 1. The PID is to cover: 1. The Terms of Reference (TOR) for the Project (Assessment criteria 2.1.1 and 2.1.2). 2. The work packages that make up the stages and the stages that make up the project (Assessment criteria 2.2.1, 3.5.1 , 4.1.1, 4.1.2 and 4.2.1 ). 3. The sequence of events in the form of a PERT diagram and accompanying analysis of probability of completion (Assessment criteria 2.2.1 and 2.2.2.
|  | 4.1.2 | Implement effective configuration management
4.2 | Understand product and work package delivery and their associated activities | 4.2.1 | Define the processes and activities needed to ensure project product delivery
4.3 | Know how to deliver effective project quality management | 4.2.1 | Implement effective quality management for a given project | Task 3 Report 2000 words | Prepare a Standing Operating Procedure (SOP) that details how the project is to be controlled and any how risks that may affect the successful completion are to be monitored and their effects eliminated or minimised (Assessment criteria 2.5.1, 3.2.1, 3.3.1, 3.4.1, 3.6.1 and 4.2.1).
4.4 | Understand the process of project closure | 4.4.1 | Implement an effective process of closure for a given project | Task 4 Report 2000 words | Prepare a Standing Operating Procedure (SOP) that identifies and defines how the closure report is to be structured. As a minimum the structure of a closure report is to include: how the completed work packages and stages were controlled; how the Risk register was used to control the project Assessment critieriion 4.4.1)