Mobile App Development for Task Management

Component 1: Project Plan Essay

Student name: Andrei-Florin Zaharia

Student ID: 2311195

LCBB6006 Project Management

Contents

1.	Brief Introduction of the Project	3

2.	Project scope	3

2.1.	Project scope	3

2.2.	Project Aim	3

2.3.	Project Objectives	3

3.	Project Assumptions and Constraints	4

3.1.	Budget Assumptions	5

3.2.	General Assumptions	5

4.	Project Constraints	6

4.1.	Constraints	6

4.2.	Exclusion	6

4.3.	Project Risk Management	6

4.3.1.      Risk Register	7

5.	Stakeholder Management Plan	8

5.1.	Stakeholder Power-Interest Grid	8

6.	Project Organization Structure	9

6.1.	Organization Structure	11

6.2.	Roles and Responsibilities	11

7.	Project Control Mechanism	12

8.	Project Communication Plan	12

9.	Project Planning with Milestones	14

9.1.	Work Breakdown Structure (WBS) of the Project activities	14

Reference List	16

# Brief Introduction of the Project

Task management apps are vital for organizing daily responsibilities, allowing users to create, assign, and arrange tasks flawlessly. This project focuses on developing a mobile application enabling users to manage their tasks to enhance individual and organizational productivity (Bruce and Pederson, 2002). Our task management mobile app will contain vital features and functionalities to help users manage their work effectively.

# Project scope

## Project scope

Project scope describes the work that must be undertaken to deliver the project outcome on time and within the allocated budget (Hamilton, 2008). This project section covers the project's objectives, the parameters, the expected quality, cost, and time. The project will cover market research to understand stakeholders' needs, define functional requirements, design user interface and experience, and develop backend systems. It will also cover the implementation of frontend functionality, system testing, and app deployment and testing. Also, the project will provide ongoing support and maintenance and conduct a review. The estimated project costs are $35,000, covering the costs of materials, personnel, and other expenses.

## Project Aim

This project aims to deliver an easy-to-use and effective mobile app that improves task organization and enables people and teams to perform their roles well.

## Project Objectives

- To develop a mobile app compatible with both Android and iOS platforms.

- To create an easy-to-use interface enabling operators to interact with the app seamlessly.

- To enable mobile app operators to create and organize tasks, prioritize tasks, and allocate due dates.

- To integrate reminder alerts and notifications to guarantee the timely completion of tasks.

- To integrate task collaboration functionalities to ease team coordination and cooperation.

- To integrate task progress tracking and reporting features to offer operators an understanding of their output.

- To implement appropriate security measures to guarantee data privacy and the security of users' information.

- To perform thorough testing and quality guarantee to offer a steady and bug-free app

- To offer consistent testing updates to solve problems and present new functionalities.

- To deliver the mobile app within the specified budget and timeline.

# Project Assumptions and Constraints

Project assumptions refer to beliefs that are likely to occur or to be true during the project but are not certain. Therefore, project assumptions are based on expectations, knowledge, or experience and can affect the project's quality, budget, risk, schedule, or scope (Hamilton, 2008). For instance, resource availability, market demand for the mobile app, customer satisfaction, and stakeholders are some of the general assumptions of this project.

Project constraints are the limitations or restrictions that the project team must observe during the project. They are usually defined by the project client, stakeholders, or sponsor, and can affect the project schedule, quality, scope, or resources (Hamilton, 2008). For instance, fixed timeline, regulatory requirements, tight budget, availability of the required skills, and specific deliverables can affect the project's quality, scope, or schedule.

## Budget Assumptions

- The project has a fixed budget of $35,000

- The organization's marketing cost will not be included in this budget.

- Customer service for the finished mobile app will not be included in the budget for this project.

## General Assumptions

- The identified mobile application's functionalities and features are consistent with the target users' preferences and needs.

- The mobile app will be compatible with the Android and iOS platforms.

- The relevant stakeholders will provide the team with all the required support throughout the project lifecycle.

- The required resources will be available whenever needed to help the team meet project requirements.

- The development of this mobile application will comply with the applicable legal regulatory requirements, including security regulations and data privacy.

# Project Constraints

## Constraints

- The project team must deliver the project within the allocated budget of $35,000

- The project team must complete the project within three months

- Budget estimates may be inaccurate

- Compatibility issues

- Additional costs may require approval.

## Exclusion

- Mobile app's marketing and promotion

- Customer service for the finished mobile app

## Project Risk Management

Project risk management will help to identify, evaluate, and control the potential risks throughout the project. This will help the project manager to ensure the project is on track and achieves its goals. Project risks will likely impact on the project's budget, performance, or timeline if not managed well (Tereso et al., 2018). The project team will utilize a risk register document to track possible risks affecting the project. This risk log is the main source for the project to detect, evaluate, and control all the potential risks throughout the project lifespan (Tereso et al., 2018). Keeping this risk register will enable the project manager to proactively detect possible opportunities and threats, assess their importance, and develop appropriate risk response plans to lessen their impact on the project (Onyeyiri and Wilson, 2025). Furthermore, this project register will help to promote openness among key stakeholders, ensuring everyone understands possible risks and the suitable solutions.

### Risk Register

| Risk Description | Risk category | Probability | Impact | Risk score | Risk Response Strategy | Mitigation |
| --- | --- | --- | --- | --- | --- | --- |
| Lack of hardware infrastructure | Technical | Medium | High | 5 | Acceptance | Utilize cloud-based infrastructure or rent hardware |
| Lack of technical expertise | Technical | High | High | 9 | Mitigation | Recruit experienced mobile app developers or outsource them |
| Lack of adequate software infrastructure | Technical | Medium | High | 5 | Mitigation | Purchase new software or upgrade existing software |
| Delays in the delivery of required software components | Project | Medium | High | 5 | Mitigation | Build strong relationships with software vendors to speed up supply or find alternative solutions. |
| Changes in customer requirements | Project | High | High | 9 | Avoidance | Involve customers in project planning when reviewing requirements |
| Budget overruns | Project | Medium | High | 5 | Mitigation | Track spending carefully and alter the project plan accordingly |
| Delays in regulatory approvals | External | Low | High | 4 | Mitigation | Initiate the approval process early and collaborate with regulators. |
| Security breach | Technical | Low | High | 4 | Transfer | Hire a security consultant |

Table 1: Risk Register

Source: Self-generated

# Stakeholder Management Plan

This stakeholder management plan will help define the procedures used to identify stakeholders who are likely to be impacted or affect the project and understand their expectations and interests in this project (Chigona et al., 2010). Therefore, this plan will enable the project team to develop suitable management strategies for engaging all key stakeholders throughout the lifespan (Chigona et al., 2010). This plan will help the project team to identify and manage stakeholder expectations and needs to gain their buy-in and achieve project success.

## Stakeholder Power-Interest Grid

The project team will use the Power-Interest Grid tool to classify stakeholders based on their level of interest and power in the project (Chigona et al., 2010). This tool will enable the team to visualize and classify stakeholders based on their level of interest and power in the project. Therefore, this tool will help offer vital information regarding the expectations and interests of different stakeholders and how the team can engage each of them to prevent conflicts and misunderstandings. Key stakeholders in this project include the project sponsor, the project manager, the project team, the sales and market department, the finance department, the mobile app users, the quality assurance team, the user experience designer, the App store review team, the technical support team, and the legal team.

| Keep Satisfied (high power, high interest) - the quality assurance team - quality assurance team - App review team - The legal team | Manage closely (high power, high interest) - project sponsor - Project manager - Project team - User experience designer - Mobile app developer |
| --- | --- |
| Monitor (low power, low interest) - the sales and market department - vendors/suppliers | Keep Informed (Low power, high interest) - the finance department - the mobile app users - Technical support team - the mobile app users |

Table 2: The Stakeholders' Power-Interest Grid

Source: Self-generated

# Project Organization Structure

A project organization entails an organizational structure that facilitates the coordination and execution of project activities (Chawla et al., 2018). Organization structure helps to create a working condition that promotes coordination among the team members with minimal disruptions, conflicts and overlaps. This structure will help the project team to reduce the misunderstandings and indecision that typically arise during the project opening stage. The team will create a structure that defines connections among the team members and their links to the outside environment (Cristóbal, Fernández, and Diaz, 2018). It represents authority through an organizational chart. This project adopted a functional project structure where the hierarchy of the project structure is organized around conventionally functioning departments. The project manager will oversee the project's general operations (Ika et al., 2020). The project manager will also hire a team with the right functional expertise to enhance the project's success.

## Organization Structure

Project Manager

Technical writer

Compliance Officer

Risk Manager

UI/UX Designer

QA/In-house testers

Database specialist

Mobile app developer

IT/DevOps Specialist

Quality control

Security specialist

Performance testing specialist

Risk management team

Figure 1: Project Organization Structure

Source: Self-generated

## Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | -The project manager is tasked with overseeing the overall project planning, coordination, and management |
| UI/UX Designer | -Responsible for designing the user interface and guaranteeing a seamless user experience. |
| Mobile App Developers | -Responsible for developing the core functionality, implementing the app features, and handling coding |
| Database specialist | -Responsible for designing and managing the database structure and guaranteeing efficient data storage and retrieval |
| Quality assurance/testers | Responsible for performing functional testing, security testing, and compatibility testing. |
| Performance Testing Specialist | Responsible for undertaking performance testing to guarantee the mobile app's performance under load. |
| IT/DevOps Specialist | Responsible for creating a development atmosphere, preparing deployment packages, and handling app store submissions |
| Risk manager | Tasked with identifying, assessing, and mitigating risks. |
| Security specialist | Responsible for creating user guides and documentation |
| Compliance officer | Will ensure the mobile app adheres to the relevant laws and regulations. |
| Security specialist | Responsible for undertaking security testing and guaranteeing the app's security measures. |

# Project Control Mechanism

Project managers strive to track their projects' progress to ensure they are completed on time, within the projected budget, and meet all the user requirements (Chow et al., 2021). Therefore, the project control mechanism entails project managers' actions to ensure the project remains on track. One of the fundamental project control mechanisms adopted for this project is to define key objectives, identify risks, and set up a schedule and cost baseline to avert scope creep (Lawrence and Scanlan, 2007). Furthermore, the project team will establish key performance indicators, define reporting structures, and detail resource allocation to ensure efficient utilization (Bruce and Pederson, 2002). Moreover, the project manager will conduct team meetings daily to track and compare the project's progress.

# Project Communication Plan

| Audience | Information | Communication frequency | Method | Owner |
| --- | --- | --- | --- | --- |
| Project sponsor | -Project status -Budget -Milestones achieved | Weekly | -In-person meetings -Monthly progress reports -email | Project manager |
| Vendors/ service providers | -Project progress -changes in requirements | When required | Regular meetings and email updates | Project manager |
| Project Team | Daily project tasks | Daily | On-site meeting and WhatsApp group | Project manager |
| Regulatory authority | Project status report | Monthly | Newsletters and email communication | Mobile app developer |
| Quality assurance team | General progress of the project | At every milestone | Face-to-face meeting and email update | Mobile app developer |

Table 3: Communication plan

Source: self-generated

# Project Planning with Milestones

## Work Breakdown Structure (WBS) of the Project activities

| WBS |  | Activity | Milestones | Owners | Duration |
| --- | --- | --- | --- | --- | --- |
| Task 1 | Mobile Development Project Plan |  | N/A |  |  |
| 1.1. | Project Planning and Initiation |  | N/A |  |  |
|  |  | Defining project scope and Objectives | Clear project scope and objectives | Project manager | 2 days |
|  |  | Identifying stakeholders and their roles | Identified stakeholders | Project manager | 1 day |
|  | 1.1.3. | Conducting risk assessment | Identified potential risks | Risk manager | 2 days |
|  |  | Identify project assumptions and constraints | Identified project assumptions and constraints | Project manager | 2 days |
|  | Requirements gathering and analysis |  | N/A |  |  |
|  |  | Conducting stakeholder interviews | Interviews conducted | Business Analyst | 1 week |
|  |  | Analyzing user requirements and needs | Documented stakeholder requirements and needs | Business Analyst | 3 days |
|  |  | Defining functional and non-functional requirements | Documented functional and non-functional requirements | Business Analyst | 3 days |
|  | Mobile app Design Phase |  |  |  |  |
|  |  | User Interface (UI) Design | Designed user interface | UI/UX Designer | 1 Week |
|  |  | Information Architecture Design | Designed information architecture | UI/UX Designer | 4 days |
|  |  | Database Design | Designed database | UI/UX Designer | 3 days |
|  | Development Phase |  | N/A |  |  |
|  |  | Implementing core functionality | Implemented core functionality | Development Team | 2 weeks |
|  |  | Creating task creation and assignment | Task creation and assignment feature | Development Team | 1 week |
|  |  | Implementing task progress tracking | Task progress tracking feature | Development Team | 3 days |
|  |  | Incorporating collaboration features | Collaboration feature | Development Team | 1 week |
|  |  | Integrating reminder alerts and notifications | Functioning reminder alerts and notifications | Development Team | 4 days |
|  |  | Implementing data storage and retrieval | Implemented data storage and retrieval | Development Team | 1 week |
|  | Testing and quality assurance |  | N/A |  |  |
|  | 1.5.1. | Developing test plans and test cases | Developed Test plans and test cases | QA Team | 3 days |
|  | 1.5.2. | Performing functional testing | Functional testing completed | QA Team | 1 week |
|  | 1.5.3. | Undertaking performance testing | Performance testing conducted | QA Team | 1 week |
|  | 1.5.4. | Testing compatibility across platforms and devices | Compatibility testing performed | QA Team | 3 days |
|  | 1.5.5. | Performing security testing | Security testing conducted | QA Team | 4 days |
|  | 1.5.6. | Conducting user acceptance testing | User acceptance testing conducted | QA Team | 1 week |
|  | Documentation and Deployment |  | N/A |  |  |
|  |  | Creating user documentation | User guide and documentation created | Technical Writer | 3 days |
|  |  | Preparing deployment package | Deployment package completed | Technical Writer | 3 days |
|  |  | Applying to mobile app stores | Application to app stores submitted | Technical Writer | 1 day |

Table 4: Work Breakdown Structure (WBS) of the Project activities

Source: Self-generated

# Reference List

Bruce, P. and Pederson, S.M. (2002). The Software Development Project: Planning and Management. New York: Wiley. Available at: 978-0471062691 (Accessed: 13 October 2025).

Chawla, V. K., Chanda, A. K., Angra, S., and Chawla, G. R. (2018) 'The Sustainable Project Management: A review and future possibilities', Journal of Project Management, pp. 157–170. Available at: 10.5267/j.jpm.2018.2.001 (Accessed: 13 October 2025).

Chigona, W., Roode, D., Nazeer, N., and Pinnock, B. (2010) 'Investigating the impact of stakeholder management on the implementation of a public access project: The case of smart cape', South African Journal of Business Management, 41(2), pp. 39–50. Available at: 10.4102/sajbm.v41i2.517 (Accessed: 13 October 2025).

Chow, T. C., Zailani, S., Rahman, M. K., Qiannan, Z., Bhuiyan, M. A., and Patwary, A. K. (2021) 'Impact of sustainable project management on project PLAN and project success of the manufacturing firm: Structural Model Assessment', PLOS ONE, 16(11). Available at: 10.1371/journal.pone.0259819 (Accessed: 13 October 2025).

Cristóbal, J.R.S., Fernández, V. and Diaz, E. (2018) 'An analysis of the main project organizational structures: Advantages, disadvantages, and factors affecting their selection', Procedia Computer Science, 138, pp. 791–798. Available at: 10.1016/j.procs.2018.10.103 (Accessed: 13 October 2025).

Hamilton, A. (2008). Handbook of Project Management Procedures. London: Thomas Telford, Online : Institution of Civil Engineers. Available at: 978-0727732583 (Accessed: 13 October 2025).

Ika, L. A., Söderlund, J., Munro, L. T., and Landoni, P. (2020) 'Cross-learning between Project Management and International Development: Analysis and Research Agenda', International Journal of Project Management, 38(8), pp. 548–558. Available at: 10.1016/j.ijproman.2020.10.005 (Accessed: 13 October 2025).

Lawrence, P. and Scanlan, J. (2007) 'Planning in the dark: Why major engineering projects fail to achieve key goals', Technology Analysis &amp; Strategic Management, 19(4), pp. 509–525. Available at: 10.1080/09537320701403508 (Accessed: 13 October 2025).

Onyeyiri, A. and Wilson, G. (2025) 'Evaluation of the impact of effective project management techniques on the success of steel development projects in Nigeria.', International Journal of Scientific Research and Management (IJSRM), 13(05), pp. 2174–2201. Available at: 10.18535/ijsrm/v13i05.ec05 (Accessed: 13 October 2025).

Tereso, A., Ribeiro, P., Fernandes, G., Loureiro, I., and Ferreira, M. (2018) 'Project Management Practices in private organizations', Project Management Journal, 50(1), pp. 6–22. Available at: 10.1177/8756972818810966 (Accessed: 13 October 2025).