| Why | Who | Where | How | When | Cost |
| --- | --- | --- | --- | --- | --- |
| Recommendation 1: Train in-house level 4 workplace assessors |  |  |  |  |  |
| Internal assessors would provide more bespoke adjustments depending on role. Implementation would be quicker than going through Access to work (Scope, 2024). | Volunteers would undertake this responsibility. | Assessors would be available across the force but the project would fall under either HR to Estates Access to Work team. | - Article on the intranet asking for volunteers. - Training sessions with provider. - Inform force how to arrange assessments. - Ensure quality of assessments through dip-sampling. | The first cohort could receive training early 2025. Further cohorts could be arranged throughout 2025/26. | Training provided by British Dyslexia Association (no date) is £1340 per person. We should have at least 10 assessors throughout the force, total would be £13,400. |
| Recommendation 2: Mandatory neurodiversity training for all SWP employees |  |  |  |  |  |
| CIPD (2024) advise organisational training provides understanding, knowledge and appreciation for neurodiversity. Feedback from the survey suggests line manager training is needed. | Learning and Development lead. All SWP employees attend. | Remote learning can be facilitated quicker and is more cost effective but can feel impersonal and not engaging (Corporate Learning Network, 2023). Use a blended approach. | - L&D to develop training package. - Comms to advertise it. - Senior manager buy-in to make the training mandatory. | Allowing time to prepare the training alongside other on-going work, the training could take place throughout 2025. | Cost estimated against time to develop training (3 weeks) - £1961 Time to provide training to full force (18 weeks) - £11,769 Total - £13,730 (based on salary) As comparison, an external provider (The Brain Charity, no date) would cost £392,000 for full force. |
| Recommendation 3: advertise reasonable adjustments at recruitment stage and standardise adjustments into recruitment processes. |  |  |  |  |  |
| Most respondents to survey felt there was not enough information available at recruitment and feedback details ideal adjustments which could be made standard. | HR lead. Force-wide comms on allowable reasonable adjustments. | Reasonable adjustments listed on all SWP recruitment adverts. Video sent out as part of interview package. | - Comms develop video. - HR develop list of reasonable adjustments. - Senior leader buy-in for reasonable adjustments. - Add list onto job adverts. - Add video to interview package. | Time to compile list of reasonable adjustments and include on adverts, and time to develop video estimated at 1 week each. | To compile a list of available reasonable adjustments would take a day – estimated cost is £93 based on salary. Sending video of building for interview – cost of time estimated at £373. |

References:

British Dyslexia Association (no date) Accredited level 4 – workplace assessors programme (elearning/online). Available at: https://www.bdadyslexia.org.uk/services/training/accredited-level-4---workplace-assessors-programme-online-or-virtual (Accessed: 23 September 2024).

CIPD (2024) Neuroinclusion at work. Available at: https://www.cipd.org/uk/knowledge/guides/neuroinclusion-work/ (Accessed: 6 September 2024).

Corporate Leanring Network (2023) The pros and cons of online vs in-person training. Available at: https://www.corporatelearningnetwork.com/learning-design/articles/the-pros-and-cons-of-online-vs-in-person-training (Accessed: 23 September 2024).

The Brain Charity (no date) Workplace neurodiversity training. Available at: https://www.thebraincharity.org.uk/other-ways-to-support-the-brain-charity/neurodiversity-training/#:~:text=The%20Brain%20Charity's%20neurodiversity%20training%20supports%20organisations%20to%20understand%20what,recruitment%2C%20onboarding%20and%20retention%20processes (Accessed: 23 September 2024).

Scope (2024) Access to work grant scheme. Available at: https://www.scope.org.uk/advice-and-support/access-to-work-grant-scheme#:~:text=How%20long%20it%20takes,weeks%20to%20get%20an%20assessment (Accessed: 23 September 2024).