## Cover
0
ELEMENTAL COST PLAN
STAGE COACH THEARTRE SCHOOL – MERTHYR TYDFIL
(PHASE 1 OF MASTERPLAN CONCEPT)
Client: Ace Capital Projects Ltd
M.E.S.S Construction Services Ref: SCT001
Version: 1
Date: May 2025

## QA
Quality Information
Prepared by |  |  | Checked by |  | Verified by |  |  | Approved by
Max James |  |  | Project Team |  | Project Team |  |  | Project Team
Revision History
Revision | Date |  | Details | Authorised |  | Name |  | Position
1 | 2025-05-08 |  |  | MJ |  | Max James | Commercial Manager
Distribution List
# Hard Copies |  | PDF Required |  | Association / Company Name
1 |  | Yes |  | ACE Capital Projects Ltd
P

## Contents
Table of Contents
1 | Basis for Estimate
2 | Take Off Sheet
3 | Cost Plan Summary
4 | Cost Plan Elements
PROJECT NAME Stage Coach Theartre

## Basis for Estimate
1. Basis For Estimate
1.01 | This estimate is based on SPONS 202 figures and indicies for the construction of a theartre within Merthyr Tydfil, on the Glebeland site as per the brief provided by the client
1.03 | The contractor ihas been appointed
1.04 | Specifications and security standards are assumed and to be confirmed.
2. Assumptions and Exclusions
2.01 | VAT is excluded, unless stated otherwise
2.02 | The estimate has been prepared as an assessment of the potential final cost of the intended Works, based on the information noted, and will be subject to change as the design develops and more information becomes available as to the condition of the existing site and buildings
2.03 | Allowances for Design Team fees & surveys are included in the Summary
2.04 | Allowance included for upgrading the existing electrical supply to the site
2.05 | Assumed water and gas supplies have sufficient capacity for the proposed development.
2.06 | An allowance of 15% has been included as part of a contigency to form part of the overall works, this could potentially be reduced upon issue of information provided by the client
2.07 | Where provisional allowances have been made, they have been stated as provisional items. Costs will be firmed up upon recipet of information from the client
2.08 | No allowance for upgrade of district network operator infrastructure
2.09 | Assumed start on site of 3Q2025
2.1 | This estimate is for estimation purposes only and only includes Phase 1 of the developtment. An allowance has also been made for a provisional car park as the car park provided within the basement does not seem sufficient. This could be valued engineered if the spaces required were to decrease.
3. Areas (SOA)
#REF!
3.1 | Areas (GIFA) |  | m2 | sq. ft
|  | Reception | - | -
|  | Waiting | 59.2 | 637
|  | Café | 138.2 | 1488
|  | Kitchen | 35.5 | 382
|  | Dance Studios | 394.8 | 4250
|  | Offices | 146 | 1572
|  | Theatre | 379 | 4080
|  | Toilets | 78.9 | 849
|  | Storage | 197.6 | 2127
|  | Breakout Spaces | 189.5 | 2040
|  | Dressing Rooms | - | -
|  | Control Room | 31.6 | 340
|  | Bar | 118.4 | 1274
|  | Circulation | 1342.3 | 14449
|  | Atrium | Not Included | Not Included
|  | Plant | 592.2 | 6374
|  | Parking | 244.8 | 2635
|  |  | 3948 | 42497
PROJECT NAME: Stage Coach Theartre

## Take Off Sheet
Project Name: Stage Coach Theartre
Estimate Title: Elemental Cost Plan
Date of issue: 2025
TIM | DIM | SQ | Description
Calculation of Wall Thickness
Half Brick Wall 102.5
Cavity 75
Steel Frame 200 (assumed column thickness)
377.5
Trench Width (Pile Diameter) 500
Less Wall 377.5
122.5
Outer Edge of Pile Foundations
W B
64 64
Removal of Topsoil (Average 150mm Thick)
64
64
4096
Material Arising from Pile Foundations
Pile Diameter: 500mm
Pile Depth: 15m
πr2h = r= pile h = height
π0.25 x 15 = 11.78
11.78
250
2945
Element 3.1 Wall Finishes
Internal wall finishes to be
taped and jointed
Take off room area and x (room number)
Window Schedule
Elevation
3 x rows of 4 = 12
3 x rows of 5 = 15
27
Elevation
3 x rows of 4 = 12
12
Elevation
2 x rows of 4 = 8
2 x rows of 3 = 6
14
Elevation to Plaza
5 x rows of 4
20
TOTAL
73
Door Schedule (External)
Elevation
2 x single leaf
1 x double leaf
Elevation
1 x Glazed Entrance
1 x Glazed Front
Elevation
1 x Glazed Rear
Elevation
TOTAL
2 x Single Leaf
1 x Double Leaf
1 x Glazed Front
1 x Glazed Rear
2 x Rolling Shutter Garage Doors
8
Door Schedule (Internal) - As per scanned in drawings
Basement
2 x Single Leaf
10 x Double Leaf
Ground Floor
11 x Single Leaf
8 x Double Leaf
First Floor
7 x Single Leaf
6 x Double Leaf
Second Floor
7 x Single Leaf
8 x Double Leaf
Third Floor
4 x Single Leaf
1 x Double Leaf
31 x Single Leaf
33 x Double Leaf
SFS System
Average 38 linear metres of stud work per room
16 x 12 = 456m
SFS System o&a
Assume 150m
Break Out Areas, Lobbies Etc
Extra Over allowance for above - 100m
860
Note on B34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Number of Piles

## Cost Plan Summary
Cost Plan Summary
PROJECT: | Stage Coach | Theartre
DESCRIPTION: | New Theartre as part of Phase 1 of Materplan
GIFA: | 3948
BUILDING WORKS ESTIMATE
GROUP ELEMENT | ELEMENT DESCRIPTION |  |  | COSTS | £/m2
GROUP ELEMENT 0 | FACILITATING WORKS |  |  | 3285000 | 832.0669
(Inc in Risk Register)
GROUP ELEMENT 1 | SUBSTRUCTURE |  |  | 2690224.9 | 681.4146
GROUP ELEMENT 2 | SUPERSTUCTURE |  |  | 6315693.2 | 1599.7197
GROUP ELEMENT 3 | INTERNAL FINISHES |  |  | 1399090 | 354.3794
GROUP ELEMENT 4 | FITTINGS & FURNISHINGS |  |  | 1000000 | 253.2928
GROUP ELEMENT 5 | SERVICES |  |  | 1500000 | 379.9392
GROUP ELEMENT 6 | PREFABRICATED & BUILDING UNITS |  |  | 0 | 0
GROUP ELEMENT 7 | WORKS TO EXISTING BUILDINGS |  |  | 0 | 0
GROUP ELEMENT 8 | EXTERNAL WORKS |  |  | 2132405 | 540.1228
GROUP ELEMENT 9 | MAIN CONTRACTORS PRELIMS |  |  | 2198689.572 | 556.9123
GROUP ELEMENT 10 | MAIN CONTRACTORS OHP |  |  | 615633.0802 | 155.9354
GROUP ELEMENT 11 | PROJECT DESIGN TEAM FEES |  |  | 634102.0726 | 160.6135
GROUP ELEMENT 12 | OTHER PROJECT COSTS |  |  | 0 | 0
(Inc in Risk Register)
GROUP ELEMENT 13 | PROJECT RISKS |  |  | 0 | 0
(Inc in Risk Register)
WORKS ESTIMATE TOTAL (SUB TOTAL A) |  |  |  | 21770837.8247 | 5514.3966
FACTORS
CURRENT TPI (SPONS 2022 USED) |  |  | 320
CURRENT TPI FORECASTED Q3 2023 (Assumed) TPI |  |  | 412
28029953.6993
FACTORED COSTS (Outer London Factor) |  |  | 0.9%
CURRENT COSTS (Wales Factor) |  |  | 1%
31144392.9993
FACTOR TOTAL (SUB TOTAL B) |  |  |  | 9373555.1745
PROVISIONAL SUMS (ACCOUNTED FOR)
FITTINGS & FURNISHINGS (FIXED FURNITURE) |  |  |  | 850000
FITTINGS & FURNISHINGS (SIGNAGE) |  |  |  | 150000
SERVICES |  |  |  | 1500000
EXTERNAL DRAINAGE |  |  |  | 250000
EXTERNAL SERVICES |  |  |  | 150000
PROVISIONAL SUM (SUB TOTAL C) |  |  |  | 2900000
DESIGN FEES
PROJECT DESIGN TEAM FEES @ 12% OF CONSTRUCTION VALUE
DESIGN FEES (SUB TOTAL D) |  |  |  | As above
RISK ALLOWANCES
DESIGN CONTIGENCY - RISK ALLOWANCE @ 2.5% |  |  |  | 778609.825
CONSTRUCTION RISK - RISK ALLOWANCE @ 2.5% |  |  |  | 275926.3226
EMPLOYERS CHANGE RISK - RISK ALLOWANCE @ 2.5% |  |  |  | 275926.3226
OTHER ASSOCIATED RISK - RISK ALLOWANCE @ 2.5% |  |  |  | 275926.3226
DESIGN FEES (SUB TOTAL E) |  |  |  | 1606388.7927
TOTAL ESTIMATE
SUB TOTAL (A+B+C+E) |  |  |  | 32750781.792
SUB TOTAL M2 (A+B+C+E) |  |  |  | 8295.5374

## 0 Facilitating Works
Project Name: Stage Coach Theartre
Estimate Title: Elemental Cost Plan
Date of issue: 2025
Ref | Description | Quantity | Unit | Rate £ | Total £
Element 0.1 Toxic / Hazadous
material treatment
0.111 A | Allowance for asbestos found | 1 | Item | Inc in RR | 0
within ground
0.112 B | Allowance for contaminated | 1 | Item | Inc in RR | 0
land (disposal of material). Based
on historic information on ground
conditions / surveys.
| Sub-total |  |  |  | 0
Element 0.4 Specialist
Groundworks
0.431 A | Ground gas venting for radon gas | 1 | Item | Inc in RR | 0
due to area - allowance for gas venting
0
Sub-total
Element 0.6 Extraordinary Site
Investigation Works
0.621 A | Allowance for ecology mitigation | 1 | Item | Inc in RR | 0
methods - desktop study
0.631 B | Allowance for UXO Survey due to | 1 | Item | Inc in RR | 0
area of build
| Sub-total |  |  |  | 0
| Total |  |  |  | 3285000

## 1 Substructure
Project Name: Stage Coach Theartre
Estimate Title: Elemental Cost Plan
Date of issue: 2025
Ref | Description | Quantity | Unit | Rate £ | Total £
Element 1.1 Substructure
A | Removal of topsoil - assumed | 4096 | m2 | 22.55 | 92364.8
150mm deep
| Sub-total |  |  |  | 92364.8
Element 1.2 Specialist Foundations
1.21 A | Piling mat - assumed 150mm | 4000 | m2 | 13.7 | 54800
thick
1.22 B | Piling Plant - assumed 1 rig | 1 | Item | 23000 | 23000
1.24 C | Supply and install piles including | 250 | nr | 4100 | 1025000
carting away of soil - assumed
600mm diameter reinforced
concrete piles
1.25 D | Pile Casings - Assumed | 250 | nr | 11.2 | 2800
ground survey data)
1.27 E | Material arising from pile foundations | 4096 | m3 | 75.6 | 309657.6
including disposal of material
1.28 F | Allowance for breaking through | 1 | Item | 25000 | 25000
tarmac
1.29 G | Cutting off tops of concrete piles & | 250 | nr | 910 | 227500
preparing heads (Nr of piles)
1.210 H | Pile tests - using tension piles as reaction: | 12.5 | Item | 9500 | 118750
typical loading test 1000KN to 2000KN
integrity testing (per 20 piles)
1.212 I | Pile caps - 2100mm x 2100mm x 1000mm; | 85 | nr | 910 | 77350
2-3 piles
| Sub-total |  |  |  | 1863857.6
Element 1.3 Lowest Floor
Construction
1.31 A | Ground Floor Slab - 200mm thick concrete | 3948 | m2 | 125 | 493500
slab with 1 layer of A252 fabric reinforcement
1.33 B | Extra over for forming of lift pit | 150 | m2 | 37 | 5550
1.37 C | Drainage below ground - allowance | 1 | Item | 150000 | 150000
1.38 D | Gullies / Floor outlets - allowance | 1 | Item | 50000 | 50000
1.310/311 | Testing / comissioning of drainage | 5 | % | Above | 34952.5
| Sub-total |  |  |  | 734002.5
2690224.9
Note on C39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Cost is per 20 piles - 250/20
Note on C43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Cost per 3 piles - 250/3 then rounded
Note on C51: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: GIFA
Note on C54: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Allowance

## 2 Superstructure
Project Name: Stage Coach Theartre
Estimate Title: Elemental Cost Plan
Date of issue: 2025
Ref | Description | Quantity | Unit | Rate £ | Total £
Element 2.1 Frame
2.11 A | Structural steel frame | 550 | tonne | 2500 | 1375000
inclusive of fittings and fixtures
2.12 B | Fire protection to steel frame - | 3948 | m2 | 37.5 | 148050
allowance for intermesent paint
| Sub-total |  |  |  | 1523050
Element 2.2 Upper Floors
2.21 A | Suspended floor slabs - assumed | 19740 | m2 | 48 | 947520
200mm thick 6.0m span: 8.50kN/m2
2.22 B | Formwork details to suspended | 5 | nr | 35000 | 175000
floors - allowance per floor
2.23 C | Joints / Details between concrete | 5 | nr | 15000 | 75000
suspended floor & steel frame -
allowance per floor
2.24 D | Surface treatment to suspended | 1 | Item | 25000 | 25000
floor - allowance
| Sub-total |  |  |  | 1222520
Element 2.3 Roof
2.34 A | Flat roof detail - specification to | 3948 | m2 | 125 | 493500
be determined - assumption made
for a warm deck detail
2.34 B | Allowance for plant deck - including | 150 | m2 | 113 | 16950
area for water storage, air handling
unit, mechanical riser and external
chiller zone (as per roof detail on
drawing)
2.311 C | Roof covering - allowance made for | 3948 | m2 | 83 | 327684
warm roof detail inclusive of;
waterproofing layer, ridgid
insulation, vapour control layer,
structural deck, ceiling & support
structure - roof detail listed within
cost report
2.322 D | Extra over roof covering - allowance | 250 | m2 | 47 | 11750
for walkways for maintance
2.322 E | Extra over roof covering - allowance | 100 | m2 | 47 | 4700
for re-inforced roof covering for
plant deck area
2.324 F | Edge protection to roof - allowance | 250 | m2 | 65 | 16250
2.341G | Channel gutters - allowance for | 250 | m2 | 94 | 23500
perimetre of building
2.342 H | Rainwater downpipes / outlets - | 250 | m2 | 83 | 20750
allowance
2.345 I | Comissioning / testing of outlets | 5 | % | Above | 45754.2
| Sub-total |  |  |  | 960838.2
Element 2.4 Stairs & Ramps
2.411 A | Stairs to floors (inclusive of staircase | 20 | nr | 6800 | 136000
up to roof deck) - assumed
precast concrete
2.421 B | Stair finish detail - finishes to | 36 | m | 105 | 3780
landings between floor levels
2.431 C | Balustrades & handrails to stairs - | 36 | m | 190 | 6840
allowance
2.441 D | Access ladder - allowance for | 1 | Item | 1000 | 1000
ladder to roof deck
| Sub-total |  |  |  | 147620
Element 2.5 External Walls (Lower Level)
2.511 A | External walls - brick external skin | 1000 | m2 | 150 | 150000
2.514 B | Extra over allowance for forming | 15 | nr | 266 | 3990
of openings (windows) - assumption
2.514 C | Extra over allowance for forming | 5 | nr | 266 | 1330
of openings (doors) - assumption
2.5111 D | Allowance for pointing to external | 1 | Item | 20000 | 20000
walls
2.5111 E | Allowance for stone arch opeing | 1 | Item | 10000 | 10000
to front façade
2.541 F | External soffits - allowance | 1 | Item | 150000 | 150000
2.544 G | Access hatch - allowance for | 1 | Item | 15000 | 15000
hatch to roof deck
| Sub-total |  |  |  | 350320
Element 2.5 External Walls (Lower Level)
2.511 A | External walls - Cladding System | 1 | Item | 1525000 | 1525000
| Sub-total |  |  |  | 1525000
Element 2.6 Windows & External
Doors
2.611 A | Window details as follows;
| UPVC 1400 x 900 mm | 7 | nr | 565 | 3955
| UPVC 1600 x 1400 mm | 5 | nr | 685 | 3425
| UPVC 1100 x 400 mm | 30 | nr | 925 | 27750
2.613 B | Glazed Entrance / Opening | 1 | Item | 25000 | 25000
2.621 C | External Door details as follows;
2.623 D | Glazed enterance door - twin leaf | 4 | nr | 12500 | 50000
glazed automatic sliding door
2.621 E | Steel door to roof deck, twin leaf | 1 | nr | 2125 | 2125
2.621 F | Back of House entrance door, | 1 | nr | 260 | 260
1.5 leaf aluminum
2.621 G | External fire exits, aluminium | 6 | nr | 2700 | 16200
twin leaf with push openings
| Sub-total |  |  |  | 128715
Element 2.7 Internal walls and
partitions
2.711 A | 140mm block load bearing wall | 250 | m2 | 168 | 42000
2.711 B | Extra over for plaster board allowance | 1 | Item | 15000 | 15000
2.711 C | New internal metal stud parititions (SFS | 2280 | lm | 98 | 223440
system)
2.711 D | Extra over for skim & plaster to both | 2280 | lm | 23 | 52440
sides
2.721 E | Internal baulstrade to staircase | 36 | m | 190 | 6840
2.741 | Toilet cublicles in sections of 4 | 66 | nr | 1125 | 74250
(per 2 rooms - due to layout)
| Sub-total |  |  |  | 413970
Element 2.8 Internal Doors
partitions
2.811 A | Fire rated doors single leaf, veneer | 31 | nr | 610 | 18910
with vision panel
2.811 C | Double leaf internal doors (corridoors) | 33 | nr | 750 | 24750
| Sub-total |  |  |  | 43660
6315693.2
Note on C10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assumed - based on building with similar GIFA
Note on C20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: *5 for all floors
Note on C41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Allowance based on similar sized building and consideration of application of building
Note on C80: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assumed staircases 1.8*no of staircases
Note on C83: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assumed staircases 1.8*no of staircases
Note on E116: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Based on project of similar GIFA
Note on C151: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Span of building - basement walls
Note on C161: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assumed staircases 1.8*no of staircases

## 3 Internal Finishes
Project Name: Stage Coach Theartre
Estimate Title: Elemental Cost Plan
Date of issue: 2025
Ref | Description | Quantity | Unit | Rate £ | Total £
Client to Determine Spec - Based on Assumptions
Element 3.1 Wall Finishes
3.11 A | Internal wall finishes to be | 5050 | m2 | 16 | 80800
taped and jointed
3.11 B | Emulsion paint - base coat & | 5050 | m2 | 23 | 116150
second coat allowance
3.11 C | Internal walls to be finished | 5050 | m2 | 12.8 | 64640
with paint
| Sub-total |  |  |  | 261590
Element 3.2 Floor Finishes
3.21 A | Floors to be finished with | 5050 | m2 | 36 | 181800
laminate throughout
3.21 B | MDF Skirtings with one coat | 5050 | m2 | 20 | 101000
of gloss paint
| Sub-total |  |  |  | 282800
Element 3.3 Ceiling Finishes
3.31 A | Taped and jointed plasterboard | 5050 | m2 | 16 | 80800
ceiling
3.31 B | Emulsion paint - base coat & | 5050 | m2 | 23 | 116150
second coat allowance
3.31 C | Ceiling grid system & tiles to | 5050 | m2 | 43 | 217150
underside of plasterboard ceiling
| Sub-total |  |  |  | 414100
Higher Spec Areas - Hall Space / Studio
Element 3.1 Wall Finishes
3.11 A | Internal wall finishes to be | 1500 | m2 | 45 | 67500
taped and jointed & plastered
3.11 B | Emulsion paint - base coat & | 1500 | m2 | 23 | 34500
second coat allowance
3.11 C | Internal walls to be finished | 1500 | m2 | 18.6 | 27900
with matt paint
| Sub-total |  |  |  | 129900
Element 3.2 Floor Finishes
3.21 A | Floors to be finished with | 1500 | m2 | 112 | 168000
bespoke dance hall floooring
3.21 B | Hardwood Skirtings with one coat | 1500 | m2 | 45 | 67500
of gloss paint
| Sub-total |  |  |  | 235500
Element 3.3 Ceiling Finishes
3.31 A | Taped and jointed plasterboard | 800 | m2 | 28 | 22400
ceiling - suspended ceiling for studio lights
3.31 B | Emulsion paint - base coat & | 800 | m2 | 23 | 18400
second coat allowance
3.31 C | Ceiling grid system & tiles to | 800 | m2 | 43 | 34400
underside of plasterboard ceiling
| Sub-total |  |  |  | 75200
1399090
Note on C12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: GIFA Allowance and Internal Studs
Note on C15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: GIFA Allowance and Internal Studs
Note on C18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: GIFA Allowance and Internal Studs
Note on C25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: GIFA Allowance and Internal Studs
Note on C28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: GIFA Allowance and Internal Studs
Note on C35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: GIFA Allowance and Internal Studs
Note on C38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: GIFA Allowance and Internal Studs
Note on C41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: GIFA Allowance and Internal Studs

## 4 FF&E
Project Name: Stage Coach Theartre
Estimate Title: Elemental Cost Plan
Date of issue: 2025
Ref | Description | Quantity | Unit | Rate £ | Total £
Client to Inform Costs
Element 4.1 Fittings, furnishings
and equiptment
4.11 A | Allowance for FF&E (Provsional | 1 | Item | 850000 | 850000
sum for fixed furniture)
4.41 B | Allowance for signs & notices | 1 | Item | 150000 | 150000
(Provisional sum for signage)
| Sub-total |  |  |  | 1000000
1000000

## 5 Sevices
Project Name: Stage Coach Theartre
Estimate Title: Elemental Cost Plan
Date of issue: 2025
Ref | Description | Quantity | Unit | Rate £ | Total £
Element 5.1 Sanitary Installations
| Provisional Sum allowance | 1 | Item | Listed Below
for services
Element 5.2 Service Equipment
| Provisional Sum allowance | 1 | Item | Listed Below
for services
| Element 5.3 Disposal Installations | 1 | Item | Listed Below
| Provisional Sum allowance | 1 | Item | Listed Below
for services
Element 5.4 Water Installations
| Provisional Sum allowance | 1 | Item | Listed Below
for services
Element 5.5 Heat Source
| Provisional Sum allowance | 1 | Item | Listed Below
for services
Element 5.6 Space Heating & A/C
| Provisional Sum allowance | 1 | Item | Listed Below
for services
Element 5.7 Ventillation
| Provisional Sum allowance | 1 | Item | Listed Below
for services
Element 5.8 Electrical Installation
| Provisional Sum allowance | 1 | Item | Listed Below
for services
Element 5.9 Fuel Installations
| Provisional Sum allowance | 1 | Item | Listed Below
for services
Element 5.10 Lift & Conveyor
| Provisional Sum allowance | 1 | Item | Listed Below
for services
Element 5.11 Fire & Lighting
| Provisional Sum allowance | 1 | Item | Listed Below
for services
Element 5.12 Comms Systems
| Provisional Sum allowance | 1 | Item | Listed Below
for services
Element 5.13 Specialist Installations
| Provisional Sum allowance | 1 | Item | Listed Below
for services
Element 5.14 BWIC
| Provisional Sum allowance | 1 | Item | Listed Below
for services
1500000

## 6 Prefab & Building Units
Project Name: Stage Coach Theartre
Estimate Title: Elemental Cost Plan
Date of issue: 2025
Ref | Description | Quantity | Unit | Rate £ | Total £
Element 6.1 Prefabricated Buildings
& Units
Not Applicable to Project

## 7 Works to Existing Buildings
Project Name: Stage Coach Theartre
Estimate Title: Elemental Cost Plan
Date of issue: 2025
Ref | Description | Quantity | Unit | Rate £ | Total £
Element 7.1 Minor Demolition Works
& Alteration Works
Not Applicable to Project
Element 7.2 Repairs to Existing
Services
Not Applicable to Project
Element 7.3 Damp Proof Courses /
Fungus & beetle eradication
Not Applicable to Project
Element 7.4 Façade Retention
Not Applicable to Project
Element 7.5 Cleaning Existing Surfaces
Not Applicable to Project
Element 7.6 Renovation Works
Not Applicable to Project

## 8 External Works
Project Name: Stage Coach Theartre
Estimate Title: Elemental Cost Plan
Date of issue: 2025
Ref | Description | Quantity | Unit | Rate £ | Total £
Element 8.1 Site Preparation Works
8.11 A | Clearance of vegitation | 5 | nr | 2475 | 12375
(m2 allowance - site survey
to inform)
8.21 B | Formation of new site contours | 2500 | m2 | 62 | 155000
site to be leveled (m2 allowance -
site survey to inform)
8.22 C | Breaking out of concrete (m2 | 500 | m2 | 49 | 24500
allownce - site survey to inform)
8.24 D | Grubbing up old drainage pipelines | 300 | m2 | 195 | 58500
(m2 allowance - site survey
to inform)
| Sub-total |  |  |  | 250375
Element 8.2 Roads, Paths, Pavings
and Surfacing
8.21 A | Road to car park | 250 | m2 | 295 | 73750
Road width 3.5m
8.22 B | Paved areas - (m2 allowance - | 500 | m2 | 98 | 49000
further developed drawings to
inform)
8.25 C | Allowance for two road crossings | 2 | nr | 47000 | 94000
8.26 D | Public Realm / Car Park Element | 1 | Item | 1158530 | 1158530
Informed by Feasibility Cost Plan
| Sub-total |  |  |  | 1375280
Element 8.3 Soft landscaping,
planting and irrigation systems
8.321 A | Allowance for nr planters to be | 10 | nr | 1000 | 10000
placed on new incoming road
8.324 B | Allowance for nr trees planted adjacent | 5 | nr | 150 | 750
to new incoming road
| Sub-total |  |  |  | 10750
Element 8.4 Fencing, Railings and
Walls
8.41 A | Allowance for fencing around the | 350 | m2 | 240 | 84000
permeter of whole site (block boundary
wall)
8.44 B | Allowance for control barriers to | 10 | nr | 1200 | 12000
car park for out of hours traffic control
| Sub-total |  |  |  | 96000
Element 8.6 External Drainage
8.6 A | Provisonal Sum Allowance for External | 1 | Item | 250000 | 250000
Drainage - To be specified in developed
drawings
| Sub-total |  |  |  | 250000
Element 8.7 External Services
8.7 A | Provisonal Sum Allowance for External | 1 | Item | 150000 | 150000
Services - To be specified in developed
drawings
| Sub-total |  |  |  | 150000
2132405

## 9 Main Contractors Prelims
Project Name: Stage Coach Theartre
Estimate Title: Elemental Cost Plan
Date of issue: 2025
Ref | Description | Quantity | Unit | Rate £ | Total £
A | Main Contractors Preliminaries | 12 | % | 18322413.1 | 2198689.572
at 12% of works cost
| Sub-total |  |  |  | 2198689.572
2198689.572

## 10 Main Contractors OHP
Project Name: Stage Coach Theartre
Estimate Title: Elemental Cost Plan
Date of issue: 2025
Ref | Description | Quantity | Unit | Rate £ | Total £
A | Main Contractors over heads | 3 | % | 20521102.672 | 615633.0802
and profit (OHP) at 3% of works
cost
| Sub-total |  |  |  | 615633.0802
615633.0802
Note on E8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Works costs & Preliminaries

## 11 Project Team Design Fees
Project Name: Stage Coach Theartre
Estimate Title: Elemental Cost Plan
Date of issue: 2025
Ref | Description | Quantity | Unit | Rate £ | Total £
A | Project Design Team Fees | 3 | % | 21136735.7522 | 634102.0726
and profit (OHP) at 3% of works
cost (Assumption of traditional
procurement design method)
| Sub-total |  |  |  | 634102.0726
634102.0726
Note on E8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Works Cost, OHP & Preliminaries

## 12 Other Project Costs
Project Name: Stage Coach Theartre
Estimate Title: Elemental Cost Plan
Date of issue: 2025
Ref | Description | Quantity | Unit | Rate £ | Total £
A | Itemised in Risk Register

## 13 Project Risks
Project Name: Stage Coach Theartre
Estimate Title: Elemental Cost Plan
Date of issue: 2025
Ref | Description | Quantity | Unit | Rate £ | Total £
A | Itemised in Risk Register

## Indicies
Series: | BCIS All-in TPI
Series number: | 101 |  | quarterly
Base: | 1985 mean = 100
Last updated: | 07-Mar-2025
Downloaded: | 04-Apr-2025 14:09
Date | Index | Status | Equivalent sample | Percentage change
|  |  |  | On year | On quarter | TPI Cost | 320
2023-05-01 | 383 | Provisional |  | 4.9 | 1.1 | Forecatsed TPI | 412
2023-08-01 | 386 | Provisional |  | 4.0 | 0.8
2023-11-01 | 388 | Provisional |  | 3.5 | 0.5 |  | 28.75%
2024-02-01 | 390 | Provisional |  | 2.9 | 0.5
2024-05-01 | 392 | Provisional |  | 2.3 | 0.5
2024-08-01 | 394 | Provisional |  | 2.1 | 0.5
2024-11-01 | 397 | Provisional |  | 2.3 | 0.8
2025-02-01 | 399 | Provisional |  | 2.3 | 0.5
2025-05-01 | 401 | Forecast |  | 2.3 | 0.5
2025-08-01 | 403 | Forecast |  | 2.3 | 0.5
2025-11-01 | 406 | Forecast |  | 2.3 | 0.7
2026-02-01 | 410 | Forecast |  | 2.8 | 1.0
2026-05-01 | 412 | Forecast |  | 2.7 | 0.5
2026-08-01 | 414 | Forecast |  | 2.7 | 0.5
2026-11-01 | 417 | Forecast |  | 2.7 | 0.7
2027-02-01 | 421 | Forecast |  | 2.7 | 1.0
2027-05-01 | 423 | Forecast |  | 2.7 | 0.5
2027-08-01 | 425 | Forecast |  | 2.7 | 0.5
2027-11-01 | 429 | Forecast |  | 2.9 | 0.9
2028-02-01 | 434 | Forecast |  | 3.1 | 1.2
2028-05-01 | 435 | Forecast |  | 2.8 | 0.2
2028-08-01 | 438 | Forecast |  | 3.1 | 0.7
2028-11-01 | 442 | Forecast |  | 3.0 | 0.9
2029-02-01 | 447 | Forecast |  | 3.0 | 1.1
2029-05-01 | 448 | Forecast |  | 3.0 | 0.2
2029-08-01 | 451 | Forecast |  | 3.0 | 0.7
2029-11-01 | 455 | Forecast |  | 2.9 | 0.9
2030-02-01 | 457 | Forecast |  | 2.2 | 0.4
1Q 2030 | 478

## Back
0