kftkLV6 Contemporary Themes

– Conference Learning Log

| Student Name: Student Number: | SANDRA SENENKO 1815103 |
| --- | --- |

| Week 1 | Monday April 27th, 2020 |
| --- | --- |
| Planning: We have assigned tasks to the staff during our first week, and we have selected site and location, speakers, publicity, presenters, venue selections. We have described the intent of the meeting (team decided to release a new product). General discussion about projectors, speakers, wi-fi, flip charts, life broadcasting cameras. We addressed choices for pre-packaged foods, snacks, disposables, consumables, cups, coffee and tea. |  |
| Organising: tasks share needed to ensure the quality and the success of the event/venue. Tasks: Events involves the organisation of people with a variety of skills that are appropriate to the form and size of the planned operation, with clear responsibilities, decision taking and control. Emoke Gego- Event Manager- Event overlooking, public participation and engagement, timetable, budget, event protection plan, temporary venue notice Sandra Senenko-Sekara- Marketing Manager- Build web accounts, ads, product logo/post, product details, Instagram, Facebook account, email Kissary Valdez- PR Manager- Attendees, invites, business emails, thank you email Domenico Comte- Quality Control Manager- controlling plus Logo, flyers, enquiries, contract Riccardo Russo- Operation Manager- contract, premises |  |
| Managing: Provide insight, build a common document. |  |
| Marketing: We discussed what programs and facilities we would like to offer for events. We did market research, marketing manager did on-line competition analysis. |  |
| Problems/Resolution Action Plan : There were no problems during our first week meeting |  |
| Focus for the Week: Stay Proactive, Communicate in a efficient way |  |

Student Signature: _______Sandra Senenko-Sekara___________________________ Date: 06/07/2020 _________________________________

| Week 2 | Monday May 4th, 2020 |
| --- | --- |
| Planning: We set our goals, planning budgets, accounts, display hangers, model exhibition tables. Our members also addressed funding- deposit, final compensation, packages, final confirmation and full information to be given one week before, scheduling the event time at 11:30 am till 1.30 pm. We have decided to provide on-site sanitisation, temperature monitoring. Hiring service for report broadcasting |  |
| Organising: Participants to conduct SWOT |  |
| Managing: share information, data protection policies, credit card details |  |
| Marketing: We came up with name and logo of the event service. We have discussed newsletters, advertising materials, Instagram posts and more – All together, it will articulate the theme and purpose of that business/venue |  |
| Problems/Resolution Action Plan : unpredictable rising prices |  |
| Focus for the Week: |  |

Student Signature: Sandra Senenko-Sekara __________________________________ Date: 04/05/2020 _________________________________

| Week 3 | Monday May 11th, 2020 |
| --- | --- |
| Planning: During our second week of the event planning we have made sure that we had enough confirmations (we draw letters). We have also contacted food and beverage company to discuss the price wise. We have discussed budget and targeting, and we have decided to create possibly three different price packages. Venue to be organised for 150-200 attendees. |  |
| Organising: We summarized the establishment of the company name, ads covered, time line set, budget set. At the moment we are working on fliers and Domenico, who is Quality Control Manager, is taking care of that. We also need to adjust contracts with rental agencies for tools we need to contact them in terms of prices. We do need to focus on privacy policies. We have also focused on marketing and promotions. |  |
| Managing: We have decided to work on a questionnaire, thank you messages to be created and we must decide how many people we would like to invite. |  |
| Marketing: We have been working on promotional film video, spending significant time and effort in creating an event pages which are well-designed in terms of both presentation and user experience. Follow up based on what we have done before. |  |
| Problems/Resolution Action Plan : Rental company for the projector. |  |
| Focus for the Week: Review your notes! |  |

Student Signature: ____________________________Sandra Senenko-Sekara______ Date: ____________11th May 2020_____________________

| Week 4 | Monday May 18th, 2020 |
| --- | --- |
| Planning: During week four we have also approached establishments to organize deliveries for pre-made drinks and snacks. During the webinar we agreed to have notebooks with business pens on our desks. Kissary to improve referral promotions and send them over. |  |
| Organising: Dominic- Quality Control Manager to video himself with and sent movie to marketing manager, Broadcasting has been discussed |  |
| Managing: |  |
| Marketing: Marketing posts and movies on social media accounts are on-going and updates are made on a regular basic. We keep customer/guests updated about what is happening. More communicating with customers following promotions and new sales. |  |
| Problems/Resolution Action Plan : Get the quote from the company – Dominic- QC Manager to call the company and communicate about pricing |  |
| Focus for the Week: Be more productive |  |

Student Signature: _________________________Sandra Senenko-Sekara_________ Date: 18/05/2020 _________________________________

| Week 5 | Monday May 25th, 2020 |
| --- | --- |
| Planning: Quality Control manager has contacted the company- unfortunately, quotes were not available. Company introduction movie to be optimised, Check audio speakers and communication checks on the day before to make sure that everything is running perfectly. Complete and exchange banners, newsletters with the team. We must communicate with the on-site tech technicians and to be sent them messaging. Arrangements to be optimised for food and drink supplies and business. Set menu with catering business / manage foods and drinks delivery time |  |
| Organising: We have decided that drinks and appetisers should be on schedule for a 10-minute rest at 12, menu to be planned, client wishes to be on site for ease and avoidance and further travel. Marketing manager to contact photographer for the requested date. |  |
| Managing: We have decided to nominate Emoke to take the pay-out as deposit must be collected 2 weeks in advance, so it is 7th September. Relationship building with potential costumers |  |
| Marketing: Team has received excellent feedbacks on social media. Video still must be refined. Lots of interactions and responses to customers through social media. Planning and publishing the right posts and the right time and frequency. Making conversation about our brand with customers. Increasing our brand awareness |  |
| Problems/Resolution Action Plan : No issues |  |
| Focus for the Week: Get promotional video |  |

Student Signature: Sandra Senenko-Sekara __________________________________ Date: 25/05/2020 _________________________________

| Week 6 – Final Week | Monday June 1st, 2020 |
| --- | --- |
| Planning: During the sixth week Videos still must be posted on youtube and a social page / Fliers and banners posted on Saturday. Audio speakers to be checked and scheduled for Saturday 19 September 2020 (room layout will be carried out the same day). |  |
| Organising: We have decided to organize food from the local Deli/Brasserie called Di Lieto Italian Restaurant, located close to the campus. Uber Eats will deliver food and beverage at the chosen timing. That has been already pre-paid. Delivery has been scheduled at 12 p.m. Speakers will enjoy lunch at 1.30 pm which will be paid individually. Freelancer PH priced at £ 500 to support youtube clip and newsletter pictures. Public relation manager (Kissary) has been allocated to monitor all deposit and credit card forms. Public relations manager (Kissaary) to send email remainders to attendees. |  |
| Managing: During our meeting we have summarized all important informations and timings, |  |
| Marketing: Social media posts are on-going and we are doing well. Our team has attracted around 30 different events through referral promotion. Marketing manager still engages the network and exceeding customer expectations through social media interaction is essential to understanding habits and patterns. |  |
| Focus for the Week: Track more customers in the future conference |  |

Student Signature: Sandra Senenko-Sekara __________________________________ Date: 18/08/2020 _________________________________

| Conference Review | Planning; Organisation; Management; Marketing of the Event and Conference Delivery |
| --- | --- |

Planning of the event went well, we have found it a little challenging to have virtual conference organized. We allocated specific responsibilities to team members that provided a management structure, as well as stopped tasks from slipping to the side of the way. It allowed us to delegate and was useful in our routine preparation for weekly management meetings. Unexpected additional costs has been coming up, hence we have done accounting very carefully. When we got a good understanding of all the expenses and time frame related to the event, we started planning. Creation of our event plan helped us to maintain that every element remained on track, as well as encouraging communication with participants of the event team. We ensured that, before we started marketing, we had a date and place finalised, and that task must have been completed as fast as possible in the planning. When we had branding and logo, people were aware of the company in all of the promotional materials used. Our team performed very well, we all have been very engaged in every aspect of the planning, organizing, and marketing. Marketing activities like Facebook advertisements have provided the biggest Return on Investments. After the event we have got very positive feedbacks from attendees.

APPENDIX: