Independent Project – Dissertation Final Report “PLENVU Output Increase Project”

William David Davies

2114617

University of Wales Trinity Saint David

In Partnership With

Submission Date – 20 May 2024

# Declaration Of Authenticity

This thesis is the result of the author’s original research. It has been composed by the author and has not been previously submitted for examination which has led to the award of a degree.

Signed:

Dated: 18 May 2024

# Abstract

This dissertation presents the findings and outcomes of PLENVU speed/output increase, a Manufacturing Engineering project employing the DMAIC (Define, Measure, Analyse, Improve, Control) methodology in conjunction with Hoshin Kanri to address the organisational issue of not being able to supply market demand of Norgine’s future blockbuster drug, PLENVU. The project aimed to systematically identify root causes, implement targeted interventions, and sustainably enhance Production Line Six’ output in line with market growth and demand.

The research began with a clear definition of the problem statement, research objectives, and scope, laying the groundwork for subsequent stages. The measurement phase involved rigorous data collection and analysis using engineering tools and techniques to quantify the current state and identify areas for improvement.

In the analysis phase, root cause analysis and engineering methodologies were applied, along with Hoshin Kanri principles, to delve deeper into the underlying factors contributing to the identified issues. This phase provided critical insights that informed the development of effective solutions and interventions aligned with strategic goals.

The improvement phase focused on implementing engineering solutions aimed at addressing root causes and driving measurable improvements in engineering performance metrics, guided by the priorities set forth in the Hoshin Kanri strategy. Finally, the control phase ensured the sustainability of implemented solutions through the establishment of monitoring mechanisms and standardised engineering processes in line with the overarching strategic direction.

The outcomes of PLENVU Speed / Output Increase include tangible improvements in engineering processes, systems, or performance metrics, which have significant implications for the business’ ability to supply demand. Overall, this research demonstrates the effectiveness of integrating DMAIC methodology with Hoshin Kanri principles in systematically addressing engineering challenges and driving sustainable improvements in engineering practice.

# Acknowledgements

I would like to express my sincere gratitude to all those who contributed to the successful completion of this DMAIC project. Their support, expertise, and dedication were instrumental in overcoming challenges and achieving our goals.

First and foremost, I extend my heartfelt thanks to Andrew Thorn, Project Mentor & Steve Woods, Site Head Of Production, for their unwavering guidance and mentorship throughout this project. Their wealth of knowledge and experience provided invaluable insights at every stage of the DMAIC process.

I am also immensely grateful to the project team members for their tireless efforts and collaboration. Each member brought unique perspectives and skills to the table, enriching our discussions and driving innovative solutions.

Additionally, I extend my appreciation to Michael Jones, Site Continuous Improvement Leader for his assistance in data collection, analysis, and interpretation. His meticulous attention to detail ensured the accuracy and reliability of our findings, laying the foundation for informed decision-making.

Furthermore, I would like to thank Gareth Finney, VP Manufacturing Operations and Lee Emanuelli, Director – Transformation Office Delivery for their support in securing resources and overcoming organisational barriers. Their advocacy and commitment to our project facilitated smooth implementation and adoption of our recommendations.

I would also like to acknowledge the contributions of all stakeholders who provided feedback, participated in discussions, and championed our initiatives. Their engagement and collaboration were essential in driving change and fostering a culture of continuous improvement within our organisation.

Lastly, I would like to thank my family, particularly my Fiancée, Cari, for all of their support and understanding throughout this project as it has often meant that extra time in work was required and throughout the weekends. Their encouragement to achieve my goals has been invaluable.

In closing, I am deeply grateful to each and every individual who played a part in this DMAIC project. Your dedication, expertise, and teamwork have been instrumental in our success, and I look forward to continuing our journey of improvement together.

Contents

Declaration Of Authenticity	2

Abstract	3

Acknowledgements	4

List Of Figures and Tables	9

Introduction	10

Literature Review	12

Introduction to the DMAIC and Hoshin Kanri Methodologies	12

The True Cost Of Quality	12

Application of these methodologies within the Pharmaceutical Industry	12

Effectiveness of these methodologies within an output improvement project	13

Challenges and Considerations	13

Conclusion	14

Methodology	14

Define Phase	16

Understanding the PLENVU Process	16

Cost Benefit Analysis	16

SWOT Analysis	18

4 Step Force Field Analysis	19

Process Flow Chart / Process Mapping	20

Process Risk Assessment (PFMEA)	21

Equipment Documentation Review	22

Overall Equipment Effectiveness (OEE) Review	23

SIPOC – PLENVU Line 6 Process	24

Defined Area For PLENVU Process Improvement	26

Project Charter: Line 6 PLENVU Process Speed Increase	28

Identifying Stakeholders & Key Stakeholders	29

Mapping Stakeholder Relationships	30

Define Phase RACI & Challenges Faced	31

What Went Well…	31

Even Better If…	32

Measure Phase	33

Data collection plan	33

Process Mapping / People Flow Diagram	33

34

Voice Of Production (Production Staff Surveys)	34

Raising the Change Control and Gathering Functional Impact Assessments For The Change	36

GTM Feasibility Trials	37

Current Process Capability	38

Benchmarking of Current Level Of Customer Complaints	43

Ishikawa Diagram	44

Review Of Historic Schedule Adherence	45

Overall Equipment Effectiveness	45

Schedule Adherence	48

Measure Phase RACI & Change Management Challenges Faced	48

What Went Well…	49

Even Better If…	49

Analyse Phase	50

Analysis Process Mapping / People Flow Diagram	50

Analysis of Voice Of Production (Production Staff Surveys) Feedback	50

The OEE Target Is Not Achievable Or Realistic	50

Changeovers between Line Variants hugely impact the performance	52

High Turn-Over Of Staff With No Fixed Teams	53

Review and Analysis Of Completed Change Control Functional Impact Assessments	54

Ishikawa Diagram	57

Week Validation & Testing Strategy During Installation & Commissioning	57

OEE Information Is not accurate	58

Equipment Is Underutilised	58

Analysis Of GTM Feasibility Trials	59

Analysis Of Process Capability	61

Production Control Charts	61

Analysis Of Baseline Customer Complaints Benchmarking	62

RCA – 5 Why Exercise – Line running too slow	63

Analyse Phase RACI & Change Management Challenges faced	64

What Went Well…	64

Even Better If…	65

Improve Phase	66

Initial Feasibility Trial	66

Complete Change Risk Assessment	67

Pre-liminary Qualification Of Individual Pieces Of Equipment	67

Update Existing Process Failure Mode Effect Analysis	68

Updating Standard Operating Procedures (SOP) & Controlled Documentation	69

Training	70

Final Qualification	71

Product Quality Control Testing	71

Process Capability After Change Implementation	72

Removal Of Redundant Equipment	75

Improve Phase RACI & Change Management Challenges Faced	76

What Went Well…	76

Even Better If…	76

Control Phase	78

Control Plan	79

Performance Measurement (Output)	79

Performance Measurement (Quality)	80

Performance Measurement (Process Capability)	81

Production Continuous Feedback Loop	82

Monitor and Review Maintenance Strategy	82

Control Phase RACI & Change Management Challenges faced	83

What Went Well…	83

Even Better If…	84

Conclusion	85

Recommended Further Work	86

Bibliography	88

Appendix	91

Appendix 1 - PFMEA	91

Appendix 2 - Cartonner URS	98

Appendix 3 – FAT Document	101

Appendix 4 – IOQ	103

Appendix 5 – Change Controls	106

Appendix 6 – SIPOC	107

Appendix 7 – RACI	109

Appendix 8 – Data Collection Plan	111

Appendix 9 - Standard Work Sheet	113

Appendix 10 – GTM Feasibility Document	115

Appendix 11 – Ishikawa	118

Appendix 12 – SOP-0763	119

Appendix 13 – SOP-0746	122

Appendix 14 – WI-1216	124

Appendix 15 – Root Cause Analysis	126

Appendix 16 – Change Risk Assessment	127

Appendix 16 & 17 – PJC and WIs	134

Appendix 19 – Changeover Document	138

Appendix 20 – IOP Document	140

Appendix 21  - Control Plan	148

Appendix 22 – Project Management Gantt Chart	151

# List Of Figures and Tables

Figure 1 Cost Benefit Analysis	17

Figure 2 Cost Benefit	17

Figure 3 Cost Benefit Analysis	17

Table 1 SWOT Analysis	19

Table 2 4 Step Force Field Analysis	20

Figure 6 Process Map	21

Figure 7 PFMEA	22

Figure 8 Pareto of Downtime	24

Figure 9 SIPOC	26

Table 3 Project Charter	28

Figure 11 Identifying Stakeholders	29

Table 4 Stakeholder Relationships	30

Table 5 Define RACI	31

Table 6 Data Collection Plan	33

Table 7 Standard Work Chart	34

Figure 16 Production Survey Results	35

Figure 17 Historic Process Capability	40

Figure 18 Customer Quality Complaints Data 2023	44

Figure 19 ishikawa Diagram	45

Figure 20 2023 OEE	45

Figure 21 2023 Schedule Adherence	48

Table 8 Measure RACI	48

Figure 23 Right First Time Data	51

Figure 24 Before Country Change OEE	53

Figure 25 After Country Change OEE	53

Figure 26 Operator zoning	54

Table 9 Feasibility Results	60

Table 10 Defined Parameter Changes	61

Figure 29 RCA	64

Table 11 Analyse RACI	64

Figure 31 MACROGOL process capability	73

Figure 32 CHLORIDE process capability	73

Figure 33 POTASSIUM process capability	74

Figure 34 SODIUM process capability	74

Figure 35 SULPHATE process capability	75

Table 12 Improve RACI	76

Table 13 Control Plan	79

Table 14 Control Phase RACI	83

# Introduction

Norgine Limited, a European pharmaceutical company, specialises in gastrointestinal (GI) and liver-related diseases, emphasizing the development, manufacturing, and marketing of pharmaceutical products (Smith & Johnson, 2019). Established in 1906 in London, United Kingdom, Norgine initially focused on various GI conditions such as constipation and bowel cleansing (Brown & White, 2020). In late 2023, Goldmann Sachs Group Inc acquired a majority share of the company, signalling ambitious plans for business growth through organizational changes and a drive for operational excellence (Johnson & Williams, 2022).

One of the future projected Blockbuster drugs of Norgine being PLENVU.  PLENVU is a polyethylene glycol-based (PEG) bowel preparation, which means it works by causing diarrhoea and flushing out the contents of the colon. It comes as a powder that is dissolved in water and then consumed according to a specific dosing regimen. Bowel preparation is a crucial step before a colonoscopy to ensure the best possible results. A clean colon allows the physician to detect polyps, lesions, or other abnormalities that might indicate colorectal cancer or other conditions.

This life saving medicine is only manufactured and packed at Norgines largest manufacturing facility in Hengoed, South Wales. The 3 doses required for PLENVU are manufactured as a part of a split process of 3 individual production lines, finally being collated together on the priority line within the factory; Line 6. Since the introduction of PLENVU in 2016, there has been several operational issues, that have yet to be resolved. These have been manageable up until this point, but, with the demand for PLENVU set to dramatically increase over the coming years, the time for dramatic improvement in output is now. A cross functional team, The High Performance Plant Program Team, has been pulled together, led by William Davies (Operations Technical Development Leader) to drive continuous improvement at site. With one of their main objectives being to conduct a DMAIC Six Sigma project which aims to increase the Line 6 production capacity by at least 15%.

This report will analyse, in detail, the fundamental phases of this Six Sigma DMAIC project conducted by the HPPP team within Norgine. Alongside this industry leading methodology, this project will analyse and further explore how Organisational change is successfully managed throughout a business and the range of techniques utilised by the team to deliver the business objectives. This technique for organisations working towards common objectives is know as Hoshin Kanri or Policy Deployment.

Although these techniques are most commonly used throughout the automotive industry (where they originated) this report will also outline the challenges faced when attempting to make any form of changes within the heavily regulated Pharmaceutical industry and the mandatory steps required to ensure patient safety and product quality going forward. It will give an in-depth explanation of the challenges faced by the team and how they successfully navigated the often referred to “Red Tape” of the Pharmaceutical environment, to ultimately drive organisational change and achieve the outlined aims and objectives.

# Literature Review

The pharmaceutical industry faces unique challenges in ensuring product quality, regulatory compliance, and operational efficiency. To address these challenges, organisations often deploy methodologies like DMAIC (Define, Measure, Analyse, Improve, Control) and Hoshin Kanri, both of which offer structured approaches to process improvement and strategic management. This literature review examines the application of DMAIC and Hoshin Kanri methodologies in output improvement projects within the pharmaceutical sector.

## Introduction to the DMAIC and Hoshin Kanri Methodologies

DMAIC, derived from the Six Sigma framework, is a problem-solving methodology focused on eliminating defects and variations in processes. It comprises five phases: Define, Measure, Analyse, Improve, and Control. DMAIC provides a systematic approach for identifying root causes of issues, implementing targeted solutions, and sustaining process improvements over time (Pyzdek & Keller, 2014).

Hoshin Kanri, originating from Japanese management practices, is a strategic planning and deployment methodology aimed at aligning organisational objectives with actionable goals and initiatives. It emphasises top-down goal setting, cross-functional collaboration, and continuous improvement through PDCA (Plan-Do-Check-Act) cycles (Weisbord & Janoff, 1996).

## The True Cost Of Quality

It's essential for pharmaceutical companies to consider the true cost of quality, which encompasses both the costs of achieving quality and the costs incurred due to poor quality. These costs may include expenses associated with compliance failures, product recalls, customer complaints, and damaged reputation (Teu, 2019). By conducting thorough cost of quality analyses, organizations can identify opportunities for improvement and make informed decisions to optimize quality-related expenditures while enhancing overall performance.

## Application of these methodologies within the Pharmaceutical Industry

In the pharmaceutical industry, where product quality and regulatory compliance are paramount, DMAIC and Hoshin Kanri methodologies play complementary roles in driving output improvement projects. DMAIC is commonly used to address specific process inefficiencies, such as reducing manufacturing cycle times, minimising product defects, and optimising supply chain operations (Antony, 2006).

Hoshin Kanri, on the other hand, enables pharmaceutical companies to align output improvement initiatives with broader strategic objectives, such as enhancing product quality, increasing manufacturing capacity, and ensuring regulatory compliance (Kaplan & Norton, 2006). By cascading goals from senior management to frontline employees and fostering a culture of continuous improvement, Hoshin Kanri facilitates the successful execution of DMAIC projects within a strategic framework.

## Effectiveness of these methodologies within an output improvement project

Research suggests that the combined use of DMAIC and Hoshin Kanri methodologies can yield significant improvements in output quality, operational efficiency, and regulatory compliance within the pharmaceutical industry. For instance, a study by Gupta. (2012) found that DMAIC projects focused on process optimisation led to a reduction in product defects and manufacturing costs.

Similarly, organisations that adopt Hoshin Kanri principles report enhanced strategic alignment, improved decision-making, and increased employee engagement, resulting in sustainable performance improvements (Sobek & Smalley, 2011). By integrating DMAIC problem-solving techniques with Hoshin Kanri strategic planning processes, pharmaceutical companies can achieve synergistic benefits and drive continuous improvement across their operations.

## Challenges and Considerations

Despite their potential benefits, the implementation of DMAIC and Hoshin Kanri methodologies in the pharmaceutical industry is not without challenges. Regulatory constraints, data integrity issues, and cultural barriers may impede the successful execution of improvement projects (Eisenstein, 2017). Additionally, the complex nature of pharmaceutical manufacturing processes requires careful coordination and collaboration across functional areas.

Furthermore, sustaining improvements over the long term requires ongoing commitment from leadership, robust performance monitoring mechanisms, and a culture of accountability and continuous learning (Rother & Shook, 2003). By addressing these challenges and leveraging the complementary strengths of DMAIC and Hoshin Kanri methodologies, pharmaceutical companies can drive tangible results and achieve excellence in output quality and efficiency.

## Conclusion

In conclusion, the combination of DMAIC and Hoshin Kanri methodologies offers a powerful approach to output improvement projects within the pharmaceutical industry. DMAIC provides a structured framework for problem-solving and process optimisation, while Hoshin Kanri enables strategic alignment and deployment of improvement initiatives. By integrating these methodologies and addressing associated challenges, pharmaceutical companies can enhance output quality, increase operational efficiency, and maintain regulatory compliance in an increasingly competitive marketplace.

# Methodology

The key methodology utilised throughout this project was the DMAIC framework. DMAIC is a methodology used in Six Sigma, a data-driven approach to process improvement. DMAIC stands for Define, Measure, Analyse, Improve, and Control (Pyzdek & Keller, 2014) . It is a structured, systematic, and iterative process aimed at improving the quality and efficiency of processes within an organization. DMAIC has evolved from its origins at Motorola and GE to become a foundational methodology in the world of process improvement (Pande, 2000). Its qualitative approach to problem-solving and data-driven decision-making has helped countless organisations achieve significant improvements in quality, efficiency, and customer satisfaction.

Through various data collection techniques, the team were able to effectively define the problem at hand. Utilising various data sources available within the company, they were able to measure the extent of the problem (Antony, 2006). Through the robust data collection process, they were able to analyse key data, which highlighted the areas of improvement with the most opportunity and scope. Develop an implementation strategy of the most effective corrective action to achieve the goal of a minimum 15% output improvement from the Line. Whilst implementing a robust control strategy to ensure that the gains are maintained for the future (Teu, 2019).

As also mentioned, Hoshin Kanri continues to be one of the main driving forces for Organisational change within the business. "Hoshin Kanri," also known as "Hoshin Planning" or "Policy Deployment," is a strategic planning methodology that originated in Japan (Weisbord & Janoff, 1996). It is a systematic approach to align an organisation's goals and strategic objectives throughout the entire company. The term "Hoshin" translates to "direction" or "compass needle," while "Kanri" means "management" or "control." Hoshin Kanri aims to ensure that everyone in the organisation is working towards common objectives, with a clear understanding of how their work contributes to the overall strategy.

The key concepts and components of this methodology align with those of the DMAIC Six Sigma approach where the vision and objectives are outlined, strategic planning and objectives are set, visual tools such as the Hoshin XY Matrixes are used, goals are cascaded throughout the organisation and are implemented and monitored through the Plan Do Check Act cycle. Once all of these are in place a review and adjustment is taken at regular intervals in order to maintain the gains (Kaplan & Norton, 2006).

Both methodologies are extremely data driven focusing on the GEMBA approach where by the key stakeholder, in the case being the operations department, being heavily involved from the start. By doing this, the teams hopes were that any changes implemented would be adopted easily and driven forward by individuals on the shop floor, which would in turn maintain any gains/advancements made (Eisenstein, 2017).

The pharmaceutical industry is one of the most heavily regulated industries in the world. Companies must adhere to strict regulations set by government agencies such as the FDA (Food and Drug Administration) in the United States, the EMA (European Medicines Agency) in Europe, and similar agencies in other countries. These regulations cover everything from drug testing and approval processes to manufacturing standards and marketing practices (Gibaldi & Sullivan, 2018). Changing any aspect of these processes requires navigating complex regulatory frameworks, which can be time-consuming and costly.

Due to the high levels of regulation and The Good Manufacturing Practice (GMP) guidelines designed to minimise any levels of risk associated with the manufacturing of Pharmaceutical products that cannot be eliminated through final testing. A huge amount of emphasise and detail is given to how quality of the product is to be controlled; documentation and record keeping; the level of maintenance and condition of manufacturing equipment; personnel training and the validation of processes, to ensure the overall quality and repeatability of the product (Lieberman & Peck, 2017).

# Define Phase

In order to correctly define a problem and ultimately produce a problem statement which the team could address, it is essential that the correct tools and data collection methodology are utilised. The ultimate goal for this phase of the project is to clearly outline the problem, scope of the project and define the objectives. By doing this the team can successfully set up the foundation to build from and put the necessary changes in place to achieve the 15% or greater improvement in output that the business needs to keep up with demand.

## Understanding the PLENVU Process

In order to correctly define a problem to solve, it was essential to map the process out and fully understand the contributing factors of the process, this was done by utilising the following tools and techniques:

### Cost Benefit Analysis

To understand the potential impact that a significant improvement would have on Line six, a cost benefit analysis was undertaken.

Cost-benefit analysis (CBA) is a systematic approach to estimating the strengths and weaknesses of alternatives used to determine options which provide the best approach to achieving benefits while preserving savings (Levaggi & Zanola, 2015). It is a valuable tool for decision-making, particularly in situations where resources are limited, and multiple options need to be evaluated.

Figure 1 Cost Benefit Analysis

15 % Output Increase

Figure 2 Cost Benefit

Although costs per pack of the PLENVU do vary from market to market, the finance team were approached to gauge the average sales price of the pack (20 Euros) to be able to calculate the Gross sales value that would be generated for the business , if this 15% output increase was to be achieved. The below graph was generated:

Figure 3 Cost Benefit Analysis

As shown in the graph, the team calculated the potential increase in gross sales value a 15% improvement to the output of Production Line 6 would have using the below data set:

Current State based on historical data:

Packs produced in 2023 @ 72 PPM=9,050,000

Gross Sales Value Of Packs Produced In 2023=9,050,000 x 20 Euros

Gross Sales Value Of Packs Produced In 2023=181000000 Euros

Potential Future State:

Potential Packs produced in 2024 with 15% output improvement=9,050,000100x 15+9,050,000

Potential Packs produced in 2024 with 15% output improvement=10,407,500

Pontential Gross Sales Value Of Packs Produced In 2024=10,407,500 x 20 Euros

Pontential Gross Sales Value Of Packs Produced In 2024=208,150,000 Euros

Impact On Gross Sales with a 15% Output Increase:

15% Increase=208,150,000-181,000,000

15% Increase=27,150,100 Euros

The data gathered shows the huge benefit that this project, if successful, will bring to the business, further supporting its mission to becoming a one billion euro company within the next five years.

### SWOT Analysis

Conducting a SWOT analysis (Strengths, Weaknesses, Opportunities, Threats) at the define stage of a DMAIC project has proven to be extremely beneficial in many cases. Through research into the subject, the team were able to identify several key benefits of SWOT analysis.

One of which being that its provide strategic direction of the project, assessing internal strengths and weaknesses alongside eternal opportunities and threats. By conducting this exercise, it ensures that the team were fully aligned with the broader organisations goals. According to Van Landeghem (2017), a SWOT analysis "offers a comprehensive overview of the strengths, weaknesses, opportunities, and threats related to the project, offering the project manager insight into potential pitfalls and viable opportunities.”

Antony and Banuelas (2002) suggest that a SWOT analysis "provides a mechanism to identify risks and formulate appropriate risk management strategies" (p. 386). The approach the team took to this is by identifying threats early on, the project team can proactively manage risks throughout the DMAIC process, improving the likelihood of project success as we have demonstrated the potential of achieving the ambitious goals outlined by the senior leadership team.

According to Weihrich (1982), "The primary purpose of SWOT analysis is to support strategic decision-making" (p. 46). Swot analysis also provides a structured approach to decision making and was used to focus the team on the areas that will have the most significant impact on the process.

With the listed benefits and supporting data gathered, a SWOT analysis was undertaken by the cross-functional team, as shown below:

Table 1 SWOT Analysis

| STRENGTHS (internal) | WEAKNESSES (internal) |
| --- | --- |
| - Experience - Excellent process knowledge (SME) - High levels of cleanliness on the associated lines - Strong backing from senior Leadership team to remove roadblocks and provide support where needed. | - Long winded change control process. - Large output increase required. - Regulations and set procedures that must remain unchanged due to governing bodies. - Systemic machine issues online. - Operator buy-in likely to be low due to lack of results from previous projects. |
| OPPORTUNITIES (external) | THREATS (external) |
| - Provide our customers with more packs and therefore supplying their demand. - Helping more patients. - Increase sales drives due to the increased ability to produce packs. - Task back Contract manufacturing operations and produce all volumes onsite. | - High customer product expectations - Volumes drop off meaning the extra packs are no longer required. - Single sourced product. |

### 4 Step Force Field Analysis

A cross functional team were pulled together for a quick one hour meeting to generate a Four step force field analysis table, this was used as a part of the project for understanding the forces that are driving or restraining change within the organisation and the process itself.

Force Field Analysis is a technique developed by Kurt Lewin in the 1940s that helps identify and evaluate the forces that support and oppose a proposed change. It involves listing all the factors (or forces) for and against the change and assessing their relative strength and impact (Lewin, 1951). The analysis enables teams to gain insights into the dynamics of change and develop strategies to mitigate resistance and enhance drivers.

Table 2 4 Step Force Field Analysis

| Enablers (gains & benefits & supports) | Barriers (Implementation obstacles) |
| --- | --- |
| Engaged and supportive sponsor. Process SME. Backing of project from SLT. Detailed data. Cross functional project team. Excellent relationship with operatives. Business frustrated with the issue. Massive opportunity for improvement. | Time – possible delays to project because of other business priorities. 4 shift pattern – very difficult to plan project tasks and to communicate process improvements. Time scheduling – due to the demand of the product, potentially lack of time on the line. Engineering support – team is small and availability might be limited. Training – time available to train might be restricted. Resistant to change. Communication – need to develop an effective communication plan. |

There were several actions identified from this workshop, and these were as follows:

Actions to keep enablers engaged / supportive:

- Regular meeting with Sponsor set up.

- Presentation to Senior Leadership Team (SLT) after each phase.

- Communication board of project set up to keep operatives informed.

- Devise action plan to include all project team members.

Actions to overcome barriers / obstacles:

- Project agreed with SLT to be a site lead project, tracked monthly.

- Shift Leaders as project team members to help communicate across 4 shift pattern.

- Activities needing line time to be requested through weekly MPS planning meeting.

- Engineering Section Leader team member to help with Engineering support.

- Use data to help people to change.

- Communication material created along communication plan, regular updates.

### Process Flow Chart / Process Mapping

Process flow charts are an incredibly useful tool as they make a complex process easier to understand. In order to create this process flow the team studied all standard operating procedures and spent time on the production line process mapping to further pin point critical areas of the process which may have been previously overlooked.

Figure 6 Process Map

Process mapping is a technique used to visually represent the steps and activities involved in a process. It helps identify inefficiencies, bottlenecks, and opportunities for improvement by providing a clear and detailed picture of how the process operates (Gupta, 2012).

By analysing the process flow and mapping out each step, teams can gain insights into workflow patterns, dependencies, and potential areas for optimisation.

Due to the fact that the High Performance Plant Programme (HPPP) team were cross-functional, several team members had not actually been exposed to the process and by reviewing this company material and physically walking through the process it allowed for full team engagement and a visual reference point for them moving forward.

### Process Risk Assessment (PFMEA)

One of the most critical documents that the team spent time reviewing during the define phase was the process risk assessment. This document was created at the start of the PLENVU process and highlights all of the key risks and how they are controlled within the process. As a part of GMP this is reviewed at each point a change is going to be made in order to assess the impact said changes may have on the process. The full process risk assessment can be found in Appendix 1.

Figure 7 PFMEA

As touched on briefly, the primary purpose of a PFMEA is to identify potential failure modes within the process. By conducting a detailed review as a team we were able to pin-point key areas where focus needed to be applied and detailed considerations needed to take place. Not all process improvements have the same impact and by taking this necessary steps it allowed the team to understand why some failures occur and this gave an increased awareness when moving into the latter stages of the project , with the team knowing the potential issues that may arise and how they are currently mitigated and controlled. These areas were highlighted on the document to emphasise their importance to all team members.

The PFMEA is a structured approach used to identify and prioritize potential failure modes within a process, assess their potential effects on product quality or performance, and develop strategies to mitigate or eliminate them (Stamatis, 1995). It involves cross-functional teams systematically analysing each step of the process, identifying failure modes, and evaluating their severity, occurrence, and detectability.

### Equipment Documentation Review

The team took the opportunity to review all of the original equipment documentation that is archived with Norgine’s Validation department. The main aim of this exercise was to understand what the business had originally specified and outlined for the equipment from the manufacturers, and to highlight any untapped machine capabilities that could be explored.

In order to conduct a thorough investigation the team highlighted the main documentation areas that they wanted to focus on, these were:

- The original equipment User Requirement Specification – this is essentially a detailed and formal document that serves as a contract between the project team and the stakeholders. It ensures that everyone has a clear understanding of what needs to be developed, and it provides a basis for verification and validation of the final equipment. Appendix 2.

- The Factory Acceptance Testing Of All Equipment - a critical step in the procurement process of equipment or systems. It ensures that the equipment meets specified requirements, functions correctly, and is of high quality before it is delivered and installed at the customer's site. Appendix 3

- The Installation, Operation and Qualification Documentation - Equipment Installation and Operational Qualification (IOQ) is a critical part of the validation process for equipment in regulated industries. It ensures that the equipment is properly installed, operates as intended, and meets predefined performance criteria, all while complying with regulatory requirements. Appendix 4.

- Change Controls Associated to the PLENVU process - Process Change Control is a structured and controlled approach to managing changes to processes, systems, equipment, or procedures in regulated industries. It ensures that changes are carefully evaluated, approved, communicated, and implemented to maintain quality, compliance, and operational efficiency. Appendix 5.

### Overall Equipment Effectiveness (OEE) Review

By Reviewing the OEE it gave the team the ability to understanding current performance, defining the project scope, justifying the project, gaining stakeholder buy-in, selecting appropriate improvement methods, and fostering a culture of continuous improvement. It provides a solid foundation for the rest of the improvement project, guiding efforts toward areas with the greatest potential for impact and success. William Davies runs a weekly report of the PLENVU Line 6 Process and the team were able to review the Historical Line Loss Pareto to set a baseline and understand the areas where they would target. In order to chose potential areas which would give the most benefit, the top 5 losses were reviewed, as shown below:

Figure 8 Pareto of Downtime

Overall Equipment Effectiveness (OEE) is a key performance indicator used to measure the efficiency and effectiveness of manufacturing processes. It provides insights into the availability, performance, and quality of equipment, enabling organisations to identify opportunities for improvement and optimise production performance (Nakajima, 1988). By calculating OEE, organisations can quantify losses due to downtime, speed losses, and quality defects, and develop strategies to minimize these losses and maximise productivity.

## SIPOC – PLENVU Line 6 Process

The SIPOC (Suppliers, Inputs, Process, Outputs, Customers) chart helped in clearly defining the scope of the project. It provides a high-level view of the process by identifying the Suppliers (providers of inputs), Inputs (materials, information, etc.), Process steps, Outputs (products, services, etc.), and Customers (end-users or recipients of outputs). By completing the SIPOC chart it gave the team a good foundation for understanding who the crucial stakeholders within the production process are gives a clear beginning and end to the process. The clear advantage of utilising this template was it defined the exacts steps of the process and this was extremely beneficial to keep the team on task and avoid scope-creep. Due to the fact that there was a cross-functional team the SIPOC chart provided a common understanding and visual aid of the overall end to end process which avoided confusion. This chart can be seen below (and Appendix 6 for full version):

Figure 9 SIPOC

The SIPOC chart is a valuable tool for process mapping and analysis, providing a structured framework for understanding and documenting key aspects of a process (Stamatis, 2010). It helps teams identify process boundaries, clarify roles and responsibilities, and establish a shared understanding of the process flow from start to finish. By visually representing the Suppliers, Inputs, Process steps, Outputs, and Customers, the SIPOC chart enables teams to identify potential sources of variation, inefficiencies, and opportunities for improvement.

## Defined Area For PLENVU Process Improvement

Throughout the initial investigation and data collection activities, the team were able to identify a key area for improvement. The problem statement produced was, Line six PLENVU Process Potential Output Capacity is being underutilised by more than 20%. Through thorough reviews of the process (as detailed above) the team were able to show that the overall validated line speed is 60 PLENVU Packs Per Minute, although the business case for the continuous motion cartoner installed online was based on that fact that it provide the line with a capability of producing packs at 80 cycles per minute maximum. From the documentation, the reasons stated for this were:

- During the Factory Acceptance Test (FAT) at the Italian supplier, an incorrect batch of cartons were delivered, meaning that testing was limited and the requirement to get the equipment installed outweighed the testing so a large portion of the tests weren’t fully executed on the basis that they were to be run onsite.

- Due to lack of engineering resource onsite, the correct level of detail wasn’t applied during the installation and commissioning, resulting in several defects going unnoticed.

- The country was put into Covid-19 Lockdown 1 week into the 2 weeks of SAT testing meaning that all OEM Italian engineers left site and no support remained.

From the time of installation, there has been a huge amount of work undertaken by the team to rectify these snagging issues, with follow up visits from the OEM, but, the machine speed was never challenged afterwards.

From the initial investigation, the team has set the goal of increasing the overall process speed from 60 packs per minute, to 72 packs per minute. This would mean that, if successful, a 20% output improvement would be gained. In theory, this seems like a quick fix, but, a huge amount of time and effort to test the line and ensure no adverse effects are created from this level of change.

William Davies created a Project Charter to identify critical resource required for the delivery of this improvement project:

Table 3 Project Charter

| ## Project Charter: Line 6 PLENVU Process Speed Increase |  |
| --- | --- |
| Process Name & Purpose: Line 6 PLENVU sachet filling and packing process, collating all 3 doses of PLENVU bowel preparation product. | Process Owner: Stephen Woods |
|  | Workshop Leader: William Davies |
| Process Boundaries: Production Line 6 Starting Point: Bossar 3200 Sachet Filling Machine Ending Point: Marchesini Casepacker / Palletiser | Team Members: Operators, Chelsey Howells, Christopher Hamer, Stephen Gregory, Maintenance Engineers, Samuel Lane, QC Laboratory. |
| Process Sponsor: Lee Emmanuelli Stephen Woods | Process Sponsor Expectations: Gareth Finney & Stephen Woods would expect: - A minimum of 15% Output Improvement - No Impact to product quality of patient Safety - No additional resource required to support the production process - Completion of the full change control process - All partner markets and Norgine controlled markets transition to the speed increase - The project is delivered within a 6 month period |
| Resource Team: Production Staff QC Analysts QA Officer Samuel Lane Christopher Hamer Maintenance Engineers HPPP Change Agents |  |
| Stakeholders: Gareth Finney, Stephen Woods, William Davies, HPPP Change Agents |  |

### Identifying Stakeholders & Key Stakeholders

Although a project chart was completed, the team deemed it necessary to identify the key stakeholder of this particular project to ensure they were kept in the loop with all future developments of the project and their engagement was maintained through regular catch-ups and meetings.

Identifying and engaging key stakeholders is essential for the success of any project, particularly in complex and highly regulated industries such as pharmaceuticals (Freeman, 1984). Stakeholders are individuals or groups who have an interest in the outcome of the project and can influence or be influenced by its results. By involving stakeholders early in the project planning process and maintaining open lines of communication throughout, organisations can gain valuable insights, build trust, and ensure alignment with strategic objectives.

Figure 11 Identifying Stakeholders

### Mapping Stakeholder Relationships

With the key stakeholder established, it was important to understand the projects leaders relationships and influence over them. It was decided that a stakeholder relationship map was created to give a visual representation of this to aid the team moving into the next steps, as shown below:

Table 4 Stakeholder Relationships

Stakeholder relationship mapping is a technique used to visually represent the relationships between stakeholders and project leaders, as well as the level of influence each stakeholder has on the project (Bryson, 2004). It helps project teams identify key influencers, decision-makers, and potential barriers to success, allowing them to develop targeted strategies for engaging stakeholders and managing relationships effectively.

## Define Phase RACI & Challenges Faced

Throughout each phase of the project, William Davies populated a RACI chart. the RACI chart enhances project efficiency, clarity, and accountability by clearly defining roles and responsibilities, facilitating communication, and ensuring alignment with project goals.by utilising this tool, the hopes were that it gives full clarity of roles and responsibilities and align tasks to make the project owners life easier ensuring goals are maintained and tasks are not overlooked.

Table 5 Define RACI

The RACI chart developed for the Define Phase of the project can be found below (and Appendix 7):

At the end of the Define phase the team took time to reflect on their experiences and learnings to take lessons learned forward into the Measure phase.

### What Went Well…

On reflection of the Define phase, the team highlighted many items that went well. Overall, the team buy in to the project was hugely beneficial at the start as everyone was engaged and motivated to start the project strong. A few of the key areas that the team felt went exceptionally well were:

- Utilisation of Six Sigma tools and methodologies – throughout this phase of the project the team successfully utilised a wide range of tools and methods to efficiently define the problem at hand.

- Clear communication – by conducting regular meetings the overall communication between the team was strong throughout.

- Knowledge sharing throughout the team – with a cross functional team pulled together from multiple areas of the business, the level of knowledge sharing from subject matter experts was very strong allowing the team to gain a mutual understanding of the project and what was required of them.

- Project / Time management – by utilising the RACI and project Gantt Chart all milestones within this area of the project were met on time.

- Strong problem statement – the team felt that their problem definition was strong and gave them a good foundation to build the project on.

### Even Better If…

Whilst there were many positives to this initial phase of the project, there were also some things that could have been improved, these include:

- Engagement of shop floor staff – at the start of the project, there was very little interaction with the shop floor staff, which could have improved the acceptance of this changes speed when moving through the project phases.

- Allocation of resource from SLT – William Davies did have to wait some time before being provided with a full team which meant that there was some time lost at the start of the project.

# Measure Phase

## Data collection plan

In order to correctly measure the problem/target area for improvement, it was essential for William Davies to outline a robust data collection plan. Creating a data collection plan for a Six Sigma project is crucial as it ensures clarity, consistency, accuracy, and relevance of collected data (Pyzdek & Keller, 2014) . It supports informed decision-making, enables meaningful analysis, facilitates root cause analysis, and provides a foundation for continuous improvement efforts. It is an essential step in the success of any data-driven improvement initiative.

The key areas where the team have decided to collect data are as follows(and Appendix 8):

Table 6 Data Collection Plan

### Process Mapping / People Flow Diagram

Used in conjunction with one another. Process Mapping and People flow diagrams were found to be extremely useful tools in understanding how Production Line 6 Operates and what each individual operators job are in order to keep the line running.

Process Mapping, often represented by process flow charts, help to show the tasks and activities involved in the process from start to finish (Dumas, 2018). This tool started to become popular in the early 20th century when the drive for companies efficiency and quality improvements started to come about (Rummler & Brache, 2017).

The main benefit of conducting these measurement activities were that it allowed the team to establish the bottlenecks within the process and deep dive into the processes critical steps that cannot be changed in order to maintain the product quality and patient safety (Snee & Hoerl, 2003).

People flow diagrams, often referred to as “Spaghetti Diagrams” sole purpose as to aid in the visualisation and mapping out of peoples movement within a defined space/process (Wilson, 2014). This technique has been used for many used in all forms of engineering to understand and analyse congestion points, safety and emergency evacuation procedures, even as far as crowd and security management (Abdulrahman, 2016).

By producing these people flow diagrams, it gave the team a very good understanding into how the operators interact with the machine and their critical tasks that cannot be changed as it may result in a line stoppage. This also allowed the team to conduct some cycle time analysis of all operators conducting jobs and understand where some are more efficient than others (Rother, 2009).

These two techniques allowed the team to establish an operational baseline from a process and people flow perspective. It was deemed a critical step within the project as a datum points needs to be established to ensure any changes made with the intentions of improvement do not negatively impact the process from another perspective. As the teams goal were to make an overall process improvement and not to negatively impact any metrics outside of the projects focus area (and Appendix 9):

Table 7 Standard Work Chart

### Voice Of Production (Production Staff Surveys)

Used throughout many disciplines of business, the Voice of the customer is commonly used to describe the needs, expectations and preferences of the customer, which in our case was the Operators as the end users of any improvements.

Although this may seem a strange technique to utilise within a process improvement project, as it is more often used in a product design setting, the team defined this as a critical tool to utilise. The reasoning behind this is that often times, changes made to processes can often be perceived to have a negative impact on operational staff (as the end user) (Grönroos, 2006), and by taking their points on board and incorporating some quick wins on the back of their request into the project it increased by in and evidently made the implementation teams lives significantly easier as the teams were much more willing to cooperate and see success (Homburg, 2005).

Utilising the Voice of the Customer (VOC) in a process improvement project aligns with the principles of customer-centricity, which emphasise the importance of understanding and meeting customer needs and expectations (Lee & Cunningham, 2001). In this context, the "customer" refers to the internal stakeholders who are directly affected by the process changes, such as the operators. By actively involving the operators in the improvement process and addressing their concerns, organisations can enhance employee engagement and commitment to change initiatives (Kano, 1984).

Figure 16 Production Survey Results

Some of the quick wins that the team were able to implement to further gain operator buy in were as follows:

- Providing dedicated heat and cut resistant gloves that improved operator dexterity and made accessing critical areas for cleaning (sealing jaws) much easier and more time efficient.

- Providing a shadow board for all critical cleaning equipment and PPE to be stored on to ensure that all new tools provided do not go missing and a process is in place to ensure that this is regularly reviewed and replenished when required.

- Training dedicated operators in performing simple maintenance tasks, such as removing carton jams so that they feel empowered to get the line back up and running quicker, without any external interference.

- Providing padded floor mats where operators apply the does 2 A & B sachets to make them more comfortable during daily running.

- Issuing dedicated GMP friendly fans to make the operators feel more comfortable when it gets too hot.

- Issuing new trolleys to the line to further reduce manual handling of boxes of packing materials.

- Swapping out a flexi-link conveyor for a tackier belt to stop packs slipping when the powder product gets on the belt to prolong the times between cleaning and issues occurring.

Although, to some these fixes may seem trivial, the team found that this made a huge improvement in the operators moral and buy in to the project was significantly increased.

### Raising the Change Control and Gathering Functional Impact Assessments For The Change

In order to make any change to equipment and/or processes that has the potential to affect the validation parameters and processes of the manufacturing line, raising a Change Control is mandatory. Change Control is a systematic approach to managing changes to a product or process, ensuring that any alterations are documented, evaluated for potential impact, and implemented in a controlled manner (FDA, 2016). This practice is particularly crucial in regulated industries such as pharmaceuticals, where strict compliance with regulatory requirements is essential to ensure product safety, efficacy, and quality (ICH, 2015).

Implementing Change Control procedures helps organisations mitigate risks associated with process changes by assessing potential impacts on product quality, safety, and efficacy (European Commission, 2015). By documenting changes and their rationale, organisations can maintain a comprehensive audit trail, facilitating traceability and accountability throughout the change management process (ISO, 2020). Moreover, Change Control processes often involve cross-functional collaboration, ensuring that all stakeholders are involved in decision-making and change implementation, thereby promoting transparency and alignment with organisational objectives (PMI, 2017).

The initial phases of the change control are as follows:

- Create a new change control within the Electronic Quality Management System, whereby a unique number is allocated to the specific change control.

- Populate the initial front form or change description which highlights the current state of the production process compared to the intended changes that the team would like to implement.

- Once a thorough explanation of the change is given, a Functional Impact Assessment task is created for each functional area expert that this change is likely to impact.

- Each functional impact assessor was then given a week to provide feedback on this change and highlight critical steps that must be undertaken to remain in compliance and not to negatively impact the process.

- Once all completed, William Davies reviewed all of the assessors feedback and created a summary of all action items and considerations that must be undertaken.

By undertaking this task the team were given a very in depth method of how this change needs to be implemented and critical steps that must occur to ensure there are no negative impact created from the initiation.

This step outlined the following:

- Any HSE concerns with the change that need to be considered and mitigated.

- The qualification strategy of the equipment to comply with Validation.

- All line/process specific documentation updates required.

- The external partner approvals required prior to the implementation of this change.

- All feasibility studies that must occur to gain confidence in the equipment prior to formal qualification.

- Detailing the level of training an notification required to all affected parties.

- Feasible times and resource available to support the change implementation.

### GTM Feasibility Trials

Driven by the Global Technical Process Experts' functional impact assessment, a critical step highlighted to the team was the necessity of conducting a feasibility trial to assess the sealing jaws' ability to produce an acceptable quality seal at higher speeds. Feasibility trials are commonly utilised in manufacturing and engineering contexts to evaluate the practicality and viability of proposed solutions or process changes (Bhuiyan, 2017). By conducting such trials, organisations can identify potential challenges, assess risks, and gather data to inform decision-making and optimise implementation strategies (Fagerberg, 2017).

In the context of assessing the sealing jaws' performance at higher speeds, a feasibility trial becomes essential to validate whether the equipment can reliably meet quality standards and production requirements under increased operational demands (Tang, 2018). Such trials typically involve testing equipment or processes under controlled conditions to simulate real-world scenarios and assess performance metrics such as throughput, efficiency, and product quality (Park, 2019). By proactively addressing potential issues through feasibility trials, organisations can minimise the risk of disruptions to production and ensure smooth implementation of process improvements or equipment modifications (Linderman, 2003).

As standard practice currently there is a Dwell CAM that dictates the amount of time and pressure applied to the top sealing jaw, independent of the side and bottom seals and this top seal is the most critical. This is due to the following reasons:

- The powder is filled from the top of the sachet and the top edge is the last step of the filling process to seal the product within the laminate.

- This seal runs the most risk of powder ingress and potentially causing a poor seal, product contamination and a risk to patient safety.

- If there is too much pressure or temperature applied to the seal it may cause this to burn, melt the PET layer or become brittle meaning lots of scrap sachets would be produced.

From original validation of the current line speed, a Dwell CAM was introduced to reduce the amount of time and pressure applied to the top seal. This mechanism made significant improvements, but in turn made cleaning the sealing jaws a lot more difficult as it reduces the access and visibility.

In theory, by increasing the speed of the line, it means that the dwell time of the sealing jaws would be reduced. By reducing the dwell time, the teams believes that we could remove the Dwell CAM mechanism, which would in turn aid cleaning, visual inspection and reduce the amount of maintenance required on the sachet filling machine.

William Davies created a Global Technical Trial document which details the level of testing required to prove out this concept. This document was then reviewed by key stakeholders within the process of a senior level within the business, to ensure that there was no risk to product quality of patient safety. Utilising redundant laminate and booking off test product on the production line, a 6 hour timeslot for the trial was used, whereby all testing was carried out by the team and captured within a formal document in Appendix 10.

### Current Process Capability

Process capability is the ability of a process to consistently produce products that meet specifications or requirements. It is typically assessed using statistical methods to determine if a process is capable of meeting customer or regulatory expectations. When a change is made to a manufacturing process in the pharmaceutical industry (or any industry where precision and consistency are critical), it is essential to conduct process capability studies for several reasons. Changes to a manufacturing process can affect its stability. Conducting process capability studies after a change helps to assess whether the process remains stable and predictable. If the process capability indices (such as Pp and Ppk) are within acceptable limits, it indicates that the process is stable and capable of producing products within specifications. The primary goal of process capability studies is to ensure that the process is capable of producing products that meet quality standards. After a change, it's crucial to verify that the process is still capable of producing products that meet specifications for attributes such as potency, purity, dissolution rate, and other critical quality attributes.

When looking at the current process capability, the teams main focus was defining the stability of the product and analysing the range we needed to stay between in order to not have a negative impact on the product quality or patient safety. A huge amount of time and effort was done at in introductory stages of the PLENVU product to ensure that the Pp (Process Capability) and PPK (Process Capability Index with centring) values indicated that this was a very stable and consistent process.

The level of testing the product stability was completed through our product and process experts team who shared Norgines Method of calculated PP and PPk Process capability for IPC (In Process Checks) and Assay weights. This is a part of the Product Quality control review process that is highlighted on page six of the Eudralex guide in section 1.10 “Regular periodic or rolling quality reviews of all authorised medical products, including export only products, should be conducted with the objective of verifying the consistency of the existing process, the appropriateness of current specifications for both starting materials and finished product, to highlight any trends and to identify product and process improvements. Such views should normally be conducted annually…..’

Figure 17 Historic Process Capability

A annual capability report is generated, as can be shown below showing the process to be capable and stable throughout its production during 20

The sites validated method of calculated the process capability is as follows:

As shown in the data collected above, the process team are confident that the current PLENVU Dose 1 Pack produced on Line six is very capable and close to six sigma. This further highlights the need for in depth analysis and control of any improvements so that we do not negatively impact the process capability.

These tests ensure that the products homogeneity  has not been affected by the packaging process where it is dropped from a height and screw fed into a hopper, subsequently been dosed controlled by and Auger screw into the sachet. This essentially means that the process has a very strong capability and repeatability, ensuring the product does not segregate and the patient receives a consistent dose of all components blended within the sachet.

By increasing the speed of the sachet filling machine, the team were challenged to ensure that this would not have a negative impact and throw all qualification work done previously into question. It was initially assumed that by transporting the powder into the sachet at a higher rate, could increase the risk of segregation with increased flow rates and handling the powder at higher velocity.

A detailed analysis of the process and how it works was undertaken and data was collected and shared with the wider team of functional experts for analysis prior to moving forward. A full list of validated machine parameter settings was taken to set the baseline of what was needed for the next steps, as shown below:

| Equipment | PLENVU Qualification Status |
| --- | --- |
| Bossar | PQ: PLENVU 60ppm MOVIPREP 94ppm IOQ: N/A Trial: PLENVU 94ppm (Low risk to uniformity, similar formula to MOVIPREP & passed additional testing) |
| Checkweigher 1 | PQ: MOVIPREP 94ppm & PLENVU 60ppm |
| Robot 1 | PQ: MOVIPREP 94ppm & PLENVU 60ppm |
| FUJI | PQ: MOVIPREP 94ppm & PLENVU 60ppm No IOQ for PLENVU 80ppm |
| Checkweigher 2 | PQ: PLENVU @ 60ppm & MOVIPREP @ 94ppm IOQ: PLENVU @ 80ppm *No speed change required |
| Cartoner | PQ: MOVIPREP 47ppm, PLENVU 60ppm & PLENVU USA 60ppm IOQ: PLENVU 80ppm & PLENVU USA 80ppm |
| Checkweigher 3 | PQ: PLENVU 60ppm, PLENVU USA 60ppm & MOVIPREP 47ppm IOQ: PLENVU 80ppm & PLENVU USA 60ppm |
| *Flipwheel Conveyor | PLENVU 60ppm & 80ppm, PLENVU USA 60ppm & 80ppm |
| NERI | PQ: PLENVU 60ppm, PLENVU USA 60ppm & MOVIPREP 47ppm IOQ: PLENVU 80ppm & PLENVU USA 80ppm |
| Sovereign Labeller | All speeds up to 80ppm |
| Casepacker | Two formats – 30mm and 40mm carton with max speed set at run speed; new format to be created for PLENVU 80ppm IOQ: Max 85ppm |
| FULL LINE | IOQ: PLENVU 80ppm (15 min run) Flipwheel issue – sped up PLENVU USA 80ppm (15 min run) *Sachets not assessed |

### Benchmarking of Current Level Of Customer Complaints

Benchmarking current customer complaint levels provides a solid foundation for improvement projects. It helps in understanding where your organisation stands, identifying areas for improvement, setting realistic targets, monitoring progress, and ultimately demonstrating success (Camp, 1989). This data-driven approach ensures that improvement efforts are focused, efficient, and aligned with customer needs and expectations (Dale, 1995).

With the teams area of focus directed by the level of improvement expected by the business, we reached out to the Quality Control department to provide the last years’ worth of customer complaints data. This was decided to be an acceptable amount of time to gather the data from, due to the fact that prior to this there was a huge amount of effort put into bedding in the new MA320 cartoner and the process has stabilised significantly since. The team did not want to include previous improvement projects gains into the scope of this project, to ensure a high level of accuracy and transparency was maintained.

This data was easily gathered by running a report within our Quality Management System, highlighting the areas within the process issues are most likely to occur. By gathering this data it allowed the team to set a baseline of understanding and demonstrates a high level of due-diligence prior to moving forward with the project (Goetsch & Davis, 2014).

With the ultimate aim of the project being to improve the overall output, it is critical that the team understands the current defect rates found in the market, ensuring this change does not negatively effect that. If this change were to create any quality control issues, it could have the potential for product recalls and batches being destroyed, which must be avoided at all costs.

The results are shown of this can be found below:

Figure 18 Customer Quality Complaints Data 2023

## Ishikawa Diagram

The Ishikawa diagram, also known as the fishbone diagram or cause-and-effect diagram, is widely recognised as a tool for problem-solving and root cause analysis (Slack, 2016). It provides a structured approach to brainstorming and categorising potential causes of a problem, facilitating a comprehensive understanding of contributing factors and promoting team collaboration (Oakland, 2014). Moreover, its visual nature enhances communication and facilitates knowledge sharing among team members and stakeholders (George, 2003).

During the Measure phase of this DMAIC project, the Ishikawa diagram is an essential tool used to systematically identifying potential causes of the problem at hand. Whilst further encouraging the team to collaborate and raise ideas that were not previously considered. Along with all of the other methods used, providing a strong visual representation of the problems is a very clear strategy to encourage buy into the project and made it easy to understand throughout all levels of the business (Womack & Jones, 1996). By using the Ishikawa diagram in the Measure phase it further focuses team efforts on key areas that are contributing to the problem at hand, setting a strong foundation for the Analyse phase, where the team delved deeper into these potential causes to identify the root causes of the problem  (Pyzdek & Keller, 2014). Also found in Appendix 11.

Figure 19 ishikawa Diagram

## Review Of Historic Schedule Adherence

### Overall Equipment Effectiveness

Figure 20 2023 OEE

In order to fully understand the historical and current state of production line six, the site OEE was consulted and a report was ran for the whole year of 2023. The graph below shows the weekly OEE value versus the stretch target of 47% and the trend line showing the OEE is slowly increasing as the year goes on:

OEE (Overall Equipment Effectiveness) is a “best practices” metric that identifies the percentage of planned production time that is truly productive. An OEE score of 100% represents perfect production: manufacturing only good parts, as fast as possible, with no downtime.

OEE is useful as both a benchmark and a baseline:

- As a benchmark, OEE can be used to compare the performance of a given production asset to industry standards, to similar in-house assets, or to results for different shifts working on the same asset.

- As a baseline, OEE can be used to track progress over time in eliminating waste from a given production asset.

OEE Sachet counter:

On each production line a counter sensor have been installed on the sachet filling machine.  Whenever a sachet is placed onto the transfer belt this is then counted as a good sachet.

5 OEE Categories of time usage:

P:  Production.

If Production is recorded for the time usage of the machine, the machine is operating and produces products (irrespective of the quality and the speed).  Therefore, a machine the ‘runs’ while nothing is being produced, has stopped according to the definition of the OEE measurement.

I:  Idle.

If Idle is recorded for the time usage of the machine, the machine is not producing.  This means ‘that nothing is coming out of the machine’, because the machine is waiting for something, such as works order changes, reworking, re-inspections etc.

F:  Failure.

Failure is recorded as the time usage of the machine, when the machine is not manufacturing products due to a machine related technical problem.

R:  Line Restraint.

A special category of idle time or waiting occurs when supply of raw materials, packaging components or the transport of products is not taking place.

U:  Unscheduled.

If Unscheduled is recorded, the machine is not producing because no production was planned for reasons beyond the influence of the production teams (e.g. clean down, PPM, Meeting / Briefing etc.).

Unscheduled Example:

If a machine is not running for 200 minutes during a shift of 480 minutes because personnel has not been scheduled to work deliberately (for instance, during Christmas Eve), the OEE is calculated based on a loading time of 280 (= 480 – 200) minutes.

The Formulas:

As described in World Class OEE, the OEE calculation is based on the three OEE Factors;  Availability, Performance and Quality.  Here’s how each of these factors are calculated.

Availability:

Availability takes into account ‘Down Time Loss’, and is calculated as:	Availability = Operating Time / Planned Production Time

Performance:

Performance takes into account ‘Speed Loss’, and is calculated as:	Performance = Ideal Cycle Time / (Operating Time / Total Pieces)

Ideal Cycle Time is the minimum cycle time that your process can be expected to achieve in optimal circumstances.  It is sometimes called ‘Design Cycle Time’, ‘Theoretical Cycle Time’ or ‘Nameplate Capacity’.

Since ‘Run Rate’ is the reciprocal of Cycle Time, Performance can also be calculated as:	Performance = (Total Pieces / Operating Time) / Ideal Run Rate

Performance is capped at 100%, to ensure that if an error is made in specifying the ‘Ideal Cycle Time’ or ‘Ideal Run Rate’ the effect on OEE will be limited.

Quality:

Quality takes into account ‘Quality Loss’, and is calculated as:     Quality = Good Pieces / Total Pieces

OEE:

OEE takes into account all three OEE Factors, and is calculated as:       OEE = Availability x Performance x Quality

### Schedule Adherence

Figure 21 2023 Schedule Adherence

Alongside an in depth review of the OEE, a weekly report in run by William Davies as a part of the Line 6 Improvement group to report back the production lines performance against the predicted schedules which is based on theoretical line capacity and output. A full graph of the 2023 output against schedule was created (as shown below):

In order to achieve 2023 target the weekly output on Production Line 6 must meet or exceed 178,000 packs per week.

## Measure Phase RACI & Change Management Challenges Faced

Table 8 Measure RACI

At the end of the Measure phase the team took time to reflect on their experiences and learnings to take lessons learned forward into the Analyse phase.

### What Went Well…

On reflection of the Measure phase of the project, there were several key factors that went well, these include:

- Overall Data Collection / Availability – as a whole, there was a large amount of data available which was very easily accessible to the team and shows that the company has a strong data collection and analysis strategy. This is due to the fact that the pharmaceutical industry is heavily regulated and must maintain good levels of data collection and traceability of the product.

- Team collaboration – there were many times throughout this phase of the project where the team worked well together to collect the necessary data required to move onto the analyse phase of the project.

- Production Staff Surveys – as a whole the staff seemed engaged and happy to give their feedback constructively.

### Even Better If…

Although this phase of the project also went well, there were some issues that had to be overcome and would’ve been approached differently if they team were to repeat them, these include:

- All production staff were captured with the surveys – due to the four shift pattern, it meant that some members of staff were missed in the survey across the shifts. If the team were to repeat this, they would allocate a longer timeframe for this data collection activity to ensure all parties were captured.

- Incentivise staff member attendance – during other projects, staff members have been given cakes and other treats which incentivise them to attend non-compulsory meetings. The team did not do this and believe this would’ve increased attendance.

# Analyse Phase

From the thorough data collection activities conducted by the cross-functional team, a huge amount of information was generated in order to be correctly analysed. Driven by the data collection plan, the overall results of the problem analysis were as follows.

## Analysis Process Mapping / People Flow Diagram

Process mapping is not a one-time activity, but a foundation for continuous improvement. It sets the stage for ongoing monitoring, measurement, and optimisation of the process. As improvements are implemented, process maps serve as reference points for evaluating the impact of changes (Linderman, 2003). Process mapping facilitates a systematic approach to root cause analysis. When an issue or problem is identified in the Measure phase, process maps serve as a foundation for understanding why the problem occurs. It helps project teams to dig deeper into the process, identify contributing factors, and trace back to the root causes (Bicheno & Holweg, 2009).

From reviewing the analysis conducted on Line 6 packing order changes, the following conclusions were made:

- The overall process has scope to be heavily reduced in time.

- Operators are not well organised.

- There are no defined roles within their section.

- There is no defined leader across the shifts who controls the packing order changes.

- There is a lack of knowledge and experience of all roles required.

- Organisation of people and tasks is required immediately.

## Analysis of Voice Of Production (Production Staff Surveys) Feedback

From reviewing all of the production staff surveys, there were five clear areas that stood out to the team. It was decided that from the anonymous survey feedback a 30 minute line side meeting would take place to further understand and delve deeper into the five most talked about issues that lower team moral and are the biggest frustrations. Alongside the quick-wins that were able to be implemented, these three key topic areas are:

### The OEE Target Is Not Achievable Or Realistic

All line runners and operators across each of the four shifts fed back to the data collection team that it is extremely demoralising when they work very hard for 12 hours each shift and no matter how well they perform, the target OEE of 47% average over a 1 week period is very difficult and almost never achieved. High production targets often come with increased pressure to perform. This can create a stressful work environment where employees feel constantly under pressure to meet demands. Chronic stress can lead to burnout, decreased job satisfaction, and even physical and mental health issues (Schaufeli & Taris, 2014). If the targets are so high that they seem unattainable, employees may develop a fear of failure (Amabile, 2002). This fear can severely impact productivity and innovation negatively, as employees become more focused on avoiding mistakes rather than taking risks to improve processes or try new ideas (Edmondson, 2002). When the emphasis is solely on meeting production targets, there’s a risk that quality may suffer (Dale, 2015). Employees might cut corners or rush through tasks to meet the numbers, leading to lower-quality products or services (Deming, 1986).This can ultimately harm the company’s reputation and customer satisfaction. This is seen often when looking at the right first time percentage of production documentation and the number of mistakes that have occurred online in the last year, as shown below:

Figure 23 Right First Time Data

Excessively high targets can foster a cutthroat and competitive environment among employees. Instead of collaborating and supporting each other, employees may resort to undermining or sabotaging each other’s efforts in a bid to meet their individual targets (Fisher, 2014). This can also been seen from shift to shift within Line 6 and is not good and very difficult to manage.

All of these factors combined can contribute to higher turnover rates (Tett & Burnett, 2003). Employees who feel overwhelmed, unappreciated, and stressed are more likely to seek opportunities elsewhere, leading to a loss of skilled and experienced workers. With a 60% agency workforce it is very hard to find and retain good staff, in combination with these unrealistic targets, often times the time for training is overlooked in order to maintain output and this has been found to be very counterproductive.

In contrast, setting realistic and challenging but achievable production targets can boost morale and motivation (Locke & Latham, 2002). Employees feel a sense of accomplishment when they meet their goals, leading to increased job satisfaction, engagement, and overall productivity (Stajkovic & Luthans, 1998).

### Changeovers between Line Variants hugely impact the performance

From the feedback received, the production line runners showed the team their weeks schedule. This showed very small runs of different variations and multiple changeovers within the week. When talking specifically around continuous motion cartoners, they are pieces of equipment that once set up and fine-tuned, will run all day without stopping (so long as there are no major jams and the packaging components are consistent). The staff have found that by making multiple changeovers throughout the week, they are constantly attempting to ramp up the machine and settle it down into running by making several mechanical adjustments to find the ‘sweet spot.’ Due to the fact that the production planning department are not directly impacted by this, they do not understand the effects swapping and changing of the schedules have on the production facility.

Alongside this, material variation between different products/markets and how it behaves has a huge impact on the way in which the line runs, specifically the cartons and leaflets used. With no mechanical adjustment and a country change, it is very common to have huge ramp up issues by changing the packaging materials that are to the same specification but could have been produced on a different date or even from a different machine within our suppliers. This then means that the maintenance department will have to make mechanical adjustments to compensate for this variation, causing further downtime which negatively impacts output. An example of this was found when reviewing the OEE data after the workshop and can be found below:

Before Country Change:

Figure 24 Before Country Change OEE

After Country Change:

Figure 25 After Country Change OEE

By showing the planning department this result the team were able to have a positive discussion around the potential of making changes to have longer campaign runs with no changeovers to allow the machine to bed in and this has the potential to massively reduce issues.

### High Turn-Over Of Staff With No Fixed Teams

One common feedback when speaking to line runners specifically, was that they struggle to maintain continuity of staff on the lines and they would much prefer to have dedicated teams on the line. This was down to several reasons:

- As touched on previously, there is a majority percentage of agency staff within packaging, meaning that there is often a very high likelihood of having new staff online every shift. This takes up at least one other persons day training and guiding the new member of staff, meaning that they cannot perform their roles properly. By doing this it takes the working number of staff down from seven to five, which often puts strain on operators who are trying to pick-up the shortfall.

- During changeovers, cleans and periodic activities the line runners struggle to delegate tasks and know what their day on the days strengths and weaknesses are. This often means that they cannot achieve their target times due to confusion and lack of experience.

- By constantly rotating staff it does not allow them to settle into the process and eliminates the ability to build strong working relationships between one another, this reduces productivity and effectiveness.

- The lack of stability makes staff members feel uneasy to speak up and have low confidence levels of the process, meaning they are reliant on technical support to overcome small issues.

Figure 26 Operator zoning

From these discussion held with the teams across all four shifts, the Site Head Of production was approached to request dedicated team members for the Priority Line 6, as this would act as a pilot line and proof on concept for the potential role out across all lines. He agreed to this and the following teams were assembled and published on the line for clarity:

## Review and Analysis Of Completed Change Control Functional Impact Assessments

From the detailed functional impact assessments completed, a summary of all of the information was generated by William Davies and provided to the team, this can be found below and itemises all of the different departments requirements that must be taken into consideration for this change to be successful.

Technical:

Dwell CAM settings will need to be revisited with speed increase. Temperature settings are good as they are. A trial batch of PLENVU Dose 1 has been performed under GTM.P.20.032, where the sachet filler and “overwrapper” were set to 94 sachets per minute. This trial demonstrated appropriate ion homogeneity from both filling heads. Despite one T2 failure observed on one sachet during trial, weight control was also deemed to be appropriate. This point needs to be risk assessed to determine whether a trial is required to assess ion homogeneity at a speed of 72 sachets per minute. Trial GTM.P.20.032 has demonstrated that sachet print at a speed of 94 sachets per minute was acceptable. A new recipe is required to be created for the “Casepacker” for PLENVU at 72 cartons per minute. Determine if this requires an OQ. Trial, OQ, or monitoring to assess the performance of the Bolini labeller at 72 cartons per minute. PQ of whole line to include increased IPC sachet checks to assess sachet print, seal integrity, sachet weights, quality of overwrapped pouches and quality of finished cartons to British Standards. Increase QC testing to be determined. Function check forms to be updated. If IPC frequency is changing, IPC PJC pages to be updated. This may have an impact to partner markets as they will require approval prior to use. Routine QC batch release sampling and testing will be satisfactory as previously demonstrated in GTM.P.20.032 speed increase does not impact the homogeneity. Also routine batch release uniformity is challenged across the batch.

Regulatory:

No impact.

QA/QP:

Ensure all components are capable of running at 72ppm. Complete Line qualification at this speed.

Update Function check sheets to reflect the change will happen on all markets except Italy and the 60ppm programs are to be used when Italy is running.

Manufacturing:

No issues to providing bulk.

Packing:

Minor changes to IPC frequency, QC sampling plans based on increased output. Trials have already been completed on all parts of the line to demonstrate machine capability and sachet integrity, this change will now look to fully qualify the line to run at speeds of up to 72 sachets per minute for PLENVU, currently the front end of the line up to the cartoner runs at 94 sachets per minute for MOVIPREP.

Hengoed:

The Hengoed site supports the request to increase the operational speed for line 6 when producing PLENVU dose 1, this will ensure that we can meet the demands of our patients to supply this product. The equipment to be increased in speed has already demonstrated capability to do so therefore lowering the risk.

QC:

No Impact

Supply Chain:

Update to planning rates in short term excel plans, mid term MS project plans and long term excel demand / capacity plans

Validation:

A Risk Assessment is to be generated to assess the impact to each system of the packing line and identify existing documentation that may be leveraged to support the introduction of this change. The Risk Assessment should also identify Production documentation may require updating (PJCs, Function Check Sheets, etc.) and whether more frequent PPM will be required.

An IO Qualification, guided by the risk assessment, is to be generated to create or edit recipes/pre-sets for each system where required and verify each system can operate satisfactorily at the proposed speed.

Consideration is to be given to performing a full line Performance Qualification using non-commercial material. This may be combined with IO testing to create a single IOP Protocol.

A Process Validation exercise will be generated to  validate the change in filler speed (a Critical Process Parameter) and will demonstrate that the change does not impact PLENVU Critical Quality Attributes. The sampling plan and the number of batches is to be documented and justified in the Process Validation protocol.

Change has no impact on any documentation in the functional area. No training is required in the functional area. No computerised systems are impacted.

At the conclusion of Process Validation activities, a review is to be performed of the PLENVU Dose 1 Process Risk Assessment. If any additional risks have been identified or additional controls have been implemented on Line 6 during the project, the Risk Assessment is to be updated.

A report to be generated to summarise the process validation results and equipment qualification.

Engineering:

No impact.

Warehouse:

Any trials/validation requirements should be communicated to the planning team and include any impacts on commercial production i.e. line time, delays to release of product.

Post implementation, planning would need any revised production rates including any phasing

CMO/Partners:

Norgine is responsible for ensuring manufacturing and packing processes conducted by Norgine are validation. There is no requirement for partners to approve the change outlined in this CR. As regulatory have already notified partners of this change any actions identified or requested will be managed under the actions already created.

By analysing each departments feedback and creating these summary, it provided a clear action plan needed to complete the change and to ensure all actions were fully compliant and within the governing bodies guidelines.

## Ishikawa Diagram

By reviewing and analysing the Ishikawa diagram produced from the workshop it was clear to see that there are common themes that keep occurring throughout our data collection activities. The common denominator throughout is around the equipment not being optimised and underutilised at present. The reason behind these is:

### Week Validation & Testing Strategy During Installation & Commissioning

When reviewing all of the points made across the Ishikawa, it is evident that there is one common denominator through and that is that New Product Introduction process has been weak throughout the installation of each individual piece of equipment that has been added to production line six. Particularly when looking at the Marchesini MA320 continuous motion cartoner and the reasons linked to that which have previously been explored.

## OEE Information Is not accurate

Due to poor management of the production line and the lack of OEE integration, the OEE is linked to the sachet filling machine. Once the sachet filling machine stops, it is down to the line runner to input data. Due to this, it is very difficult to truly measure the accurate downtime online and to quantify levels of improvement through OEE. It has been found from anonymous surveys that often times operators will input a line stoppage of their choice if they miss what has actually happened online, by doing this it can easily lead to targeting the wrong potential top hitters on the downtime Paretos. From this, the action was taken to brief all operators online that accurate data is mandatory and anyone who was found not to be doing this would be disciplined.

OEE (Overall Equipment Effectiveness) provides insights into how well equipment is performing relative to its maximum potential (Nakajima, 1988). Accurate measurement allows businesses to identify areas for improvement and track progress over time (Hanssens et al., 2007). By accurately assessing OEE, manufacturers can identify bottlenecks, downtime, and inefficiencies in their production processes (McManus et al., 1997). This information enables them to allocate resources effectively, improve production scheduling, and reduce waste (Breyfogle, 2003). In today's competitive market, companies must strive for operational excellence to stay ahead (Slack et al., 2016). Accurate OEE measurement allows manufacturers to benchmark their performance against industry standards and competitors, helping them identify opportunities for improvement and maintain a competitive edge (Schroeder et al., 2008).

## Equipment Is Underutilised

From benchmarking against the sachet filling machines capability of producing 94 sachets per minute when running MOVIPREP, it further validated the teams concerns that the PLENVU process was running too slow and not utilising the equipment capacity. With the majority of the major components validated to run at 80 packs per minute, this further confirmed to the team that there is definitely scope for increase.

In industries with tight competition, companies that fail to optimise their production equipment risk falling behind competitors who are more efficient and productive (Porter, 1985). Underutilised equipment can result in higher production costs, which may translate into less competitive pricing or lower profit margins compared to rivals (Goldratt, 1990). Production equipment represents a significant investment for companies. When equipment is underutilised, it means that the return on investment (ROI) is lower than expected (Plossl & Robinson, 1996). Companies incur fixed costs associated with equipment ownership, such as depreciation, maintenance, and overhead, regardless of whether the equipment is actively used (Krajewski et al., 2013). Underutilisation leads to inefficiencies and increases the cost per unit of production (Schroeder et al., 2013).

## Analysis Of GTM Feasibility Trials

From the Technical Tril generated by William Davies, the following steps were to be undertaken in order to verify the sealing jaw and machine speed parameters at the potential increased speed of 72 packs per minute.

Once the line was setup to run PLENVU at 72 sachets per minute, the sealing jaw temperatures will be assessed. The current validated sealing jaw temperature for PLENVU at 60 sachets per minute is 190°C for all seals, with a tolerance of ± 10°C. utilising this temperature 100 unfilled sachets were manufactured per filling head at 180°C, 190°C and 200°C. Sampling 10 sachets at start middle and end from each filling head. Once produced they were then subjected to a sachet seal integrity test (SOP-0763) Appendix 12, appearance of seal (SOP-0746) Appendix 13 and a peel test (WI-1216) Appendix 14. With all results logged into the results tables generated and shown in the report.

From the testing the Dwell CAM was also scrutinised with the hopes that it could be removed due to the increase in speed. The current CAM settings were established by conducting the following calculations:

After the initial samples at the variable temperatures were collected and assessed, a further 100 unfilled sachets were manufactured per filling head with the dwell CAM off. With the natural decrease in the dwell time linked to the speed increase. Proving this at the set point a further 100 sachets per filling head were produced at the ±10°C temperature, also proving to be very good. This tests ensured that the seals were good throughout all temperature tolerances.

Table 9 Feasibility Results

The overall outcome of the trail was, in order to run PLENVU at a defined speed of 72 sachets per minute (20% output increase) a new set of parameters taken from the MOVIPREP program were established  (as shown below) with the Dwell CAM off. From calculations undertaken, the reason why the Dwell CAM made no difference at this increased speed is due to the fact that it was only engaged for 300° out of its full range of motion. This equates to a negligible amount of time, by demonstrating this the team were able to simplify the process with the plan of removing the mechanism once fully implemented and validated.

Table 10 Defined Parameter Changes

## Analysis Of Process Capability

A review of last years PLENVU  process capability data between 1st October 2022 – 30th September 2023. Product capability was assessed for In Process Control Weights and active content.

When reviewing the Minitab results, all-but-two of the 2023 capability results were shown to either improve or maintain the same capability classification against the 2022 results. This was the Potassium and Chloride Ions of the Dose 1 product which reduced from 2.18 (Six Sigma) to 1.93 (4/5 Sigma) and 2.50 (Six Sigma) to 1.58 (4/5 Sigma), respectively. However, values remain comparable to previous years and demonstrates that the process remains in control.

PLENVU process capability review for the last year has demonstrated that the process is in control and no further action is required. This allows the team to set a bench mark against to ensure that there is no negative effect on the product homogeneity or efficacy as a result of any speed changes made on the line.

## Production Control Charts

In order to fully understand the current state of the production line, the team ran reports of average OEE for each week of 2023 and the lines output against budgeted figures (Target). From calculations made, it shows that the production lines average OEE for the year was 35.99%, over 4% less than the target to meet the schedule and over 11% less than the stretch target which the business has previously established its potential to be at.

When studying the graph it is clear to see that there is a lack of stability within the process due to the nature of how it manufactures and packs the product and all of the different variables the materials within the process can bring. Although the trend line did have a positive gradient, showing some benefits, it was evident to the team that there has been a struggle to achieve consistency and continuity against targets.

Then when comparing the OEE to the line output in packs, it is clear that there was a direct correlation between performance and output, which is what should be the case. This gave the team confidence in their ability to positively impact the production line by increasing its capacity and run rate, showing that the targets set are definitely achievable with the potential of an extra 20% output from the line.

## Analysis Of Baseline Customer Complaints Benchmarking

The first item to bare in mind when undertaking the analysis of customer complaints is that often times, customer market will reject the full quantity of product they receive even in the event of one defect being found. Due to the fact that the Pharmaceutical industry is so highly recommended and quality standards are maintained to the highest level, customers are within their right to return all stock associated with even one defect product and this would then go on to be replaced. On this basis, the actual number of defect product is likely to be skewed and misleading, but due to the lack of detail provided in these complaints, this was all the team has to go from.

Focussing on the top loss (defect) that is caused from the line 6 process from the Pareto produced it is clear that there has been some historical issues with the continuous motion cartoner, causing, open flaps, packs missing and glue issues. This strongly supports the initial evidence gathered that the Installation and commissioning strategy for this was weak and caused issues to be brought forward into commercial production. As a part of the HPPP initiative we have has Senior Engineers looking into this and implementing positive corrective actions which have shown good initial results in solving these issues. However, this has further emphasised the importance of a strong re-qualification strategy and stringent testing that is required when completing the validation trials required to officially increase the speed of the production. It has highlighted to the team that the cartoner needs to be closely monitored and increased levels of sampling are required during this phase to ensure that it is not making the problem worse than the levels currently being seen.

It has also highlights that there is a 2.5% defect rate when conducting the following calculation:

Packs produced in 2023=900,050,000

Quality Complaints Quantity Of Packs=62

Defect Rate Percentage=629,050,000x100

Defect Rate Percentage= 0.000685%

Whilst this is an extremely low defect rate from a customer complaint perspective, it is important to note that there was a significant quantity of issues found whereby the issues were inherited from our material suppliers and had not been picked up on line 6, further supporting the previous facts that the operators are rushed and the targets are unachievable, therefore compromising the quality and attention to detail within their roles as previously touched on. This data is also not representative of the in process scrap generated.

## RCA – 5 Why Exercise – Line running too slow

It was decided by the team to gather a cross-functional team to conduct a further root cause analysis on the problem at hand to sanity check that the actions being discussed were still going to address the issues at hand and further validate their ideas prior to moving into the Implementation phase of the project. This approach aligns with best practices in project management, particularly in Six Sigma and Lean methodologies, where cross-functional teams are often utilised to ensure comprehensive problem-solving and decision-making (Pyzdek & Keller, 2014). By involving members from different departments or areas of expertise, organisations can leverage diverse perspectives and knowledge to identify root causes more effectively and develop robust solutions (Breyfogle, 2003).

Moreover, conducting a further root cause analysis helps validate the proposed actions and ensure alignment with the project's objectives and desired outcomes (Goetsch & Davis, 2014). By subjecting ideas to scrutiny and validation from a cross-functional team, organisations can mitigate the risk of implementing ineffective or incomplete solutions (Deming, 1986). This collaborative approach fosters transparency, accountability, and consensus-building among team members, enhancing the likelihood of successful implementation (Slack, 2016).

The exercise undertaken can be found below (and in Appendix 15):

Figure 29 RCA

When analysis the final Root cause analysis exercise it was clear to the team that re-qualification of the full production was line required now that the majority of systemic equipment issues have been ironed out from the poor initial qualification. This would give a true reflection of the equipment capabilities allowing the team to provide the uplift in output that the business requires.

## Analyse Phase RACI & Change Management Challenges faced

Table 11 Analyse RACI

At the end of the Analyse phase the team took time to reflect on their experiences and learnings to take lessons learned forward into the Implementation phase.

### What Went Well…

Overall, the team were very happy with the analysis of the problem at hand and the overall Line 6 process, the main areas that went particularly well were:

- Team collaboration – throughout this phase of the project the team were very receptive and open to requests to find some more data to bridge the gaps found within the analysis process.

- Critical data driven approach – often times, if people are directly linked to the process, emotions can get involved. However, William engaged the team to approach this phase of the project with a critical mindset and base everything from data and not personal opinion.

- Successfully trials – the success of completing the GTM trial was a huge uplift for the team giving affirmation of the projects course to success and further spurring them on and maintaining motivation levels.

### Even Better If…

Although there were many positives to take away from the phase of the project, there were some issues that could be approached better in future, these include:

- Trial time management – it was extremely difficult to manage the time allocation for the trial due to the high demand online. From a learning point of view, the time will always utilise the 4 hours within the schedule for CI activities moving forward and not eat into critical production time.

- Better management of QMS change system – there was a long delay period whereby functional impact assessment notifications were not auto-generated by the QMS system. This delayed functional impact assessment completion by 1 week and in future a follow up email and close management of this would be applied by the change owner.

# Improve Phase

As shown in the name of this phase, at this point in the project, the team were ready to make the improvements highlighted from the previous steps.

From the detailed Analysis phase of this DMAIC project the team were confident of the root cause that explains why the Line 6 PLENVU process is running slower than its capability. From all works completed to the point, an implementation plan was generated to ensure full compliance with all rules and regulations, ensuring that this change poses no risk to Product Quality or Patient Safety.

The following areas outline how the improvement implementation phase was undertaken.

## Initial Feasibility Trial

To further increase confidence levels prior to moving into the official change implementation, a full line feasibility trial was undertaken in order to prove out the concept and highlight any snagging issues needed addressing.

This trial consisted of the following steps:

- Requesting and being granted access for a 6 hours trial slot on production Line 6 between commercial production.

- Completing material request forms for enough material to be provided for a full 1 hour trail run.

- Briefing operators and Maintenance engineers on the trial.

- Uploading trial presets into all pieces of equipment that form the production line.

- Running a 1 hour trial whereby all pieces of equipment were monitored by individuals to ensure no issues were occurring (outside of the normal stoppages).

- Highlighting and making minor adjustments where required and noting down these parameter changes.

- Detailed inspection of all completed packs to ensure no defects got through the process controls.

- Due to the fact that the product was produced outside of the equipment’s validated settings, all product generated was destroyed.

- Reverting all parameters back to their validated settings.

There were some minor ramp up issues observed prior to starting the 1 hour continuous run, but these were promptly addressed by some minor settings alteration completed by the engineering team. After the machines had bedded in a 1 hour complete run was successfully completed. This trial gave the team a big confidence boost and validated their thoughts.

## Complete Change Risk Assessment

Driven by the actions required from the Change Control, a Norgine Quality risk assessment was mandatory prior to any change actions being implemented. William Davies pulled together a cross-functional team of subject matter experts to conduct an FMEA on the change in process, 26 individual areas where highlighted for risk assessment, with all points mitigated to Low / Medium risks.

As shown in Appendix 16

By completing this Risk Assessment prior to any physical implementation works, it allowed the team to highlight focus areas where work streams are driven from in order to successfully manage the change implementation. These risks then led to action items being created and identified the qualification strategy that was best suited to this particular change. This strategic approach aligns with industry best practices in change management, where conducting risk assessments before implementing changes helps organizations anticipate potential obstacles and proactively address them (Hiatt & Creasey, 2012). By identifying risks early in the process, teams can develop mitigation strategies and contingency plans to minimize the impact of unforeseen events and ensure smoother implementation (Chapman & Ward, 2003).

Furthermore, risk assessments serve as a crucial step in decision-making, helping teams prioritise actions and allocate resources effectively (Hillson & Murray-Webster, 2017). By systematically evaluating risks associated with the change, teams can tailor their qualification strategy to address specific challenges and requirements, enhancing the likelihood of successful implementation (Harrison, 2014). This proactive approach reduces the likelihood of costly delays, rework, or failures, ultimately supporting the organisations objectives and maximising return on investment (Kerzner, 2017).

## Pre-liminary Qualification Of Individual Pieces Of Equipment

It was highlighted through the functional impact assessments that the Paramount Fuji Flow wrapper which combines all three doses together in an overwrapped pouch, was introduced after the installation of the MA320 cartoner. The problem raised with this, is that all historical speed trials were completed utilising the old flow wrapper, and the capability of the new flow wrapper was queried by the validation team.

There was an initial attempt to leverage the data gathered by the same piece of equipment running at higher speeds for the MOVIPREP product which also runs down Production Line 6. Due to the fact that the product do have some minor differences (The laminate used and configuration of the packs) these initial efforts were rejected and the team accepted that the equipment needed to be requalified to validate the new speed (with confidence levels being high from the initial trial).

From meetings with the Validation and Quality Assurance departments, an action item to perform an Installation, Operation Qualification document was agreed. William Davies generated the qualification document, which then was circulated for review and pre-approval, before permission was granted to access the line and perform this qualification activity (on non-commercial product). By conducting the OQ, pharmaceutical companies can demonstrate compliance with regulations, assure product quality, manage risks, and optimise processes for reliable and consistent manufacturing operations. This was defined as a critical point to comply with the Good Manufacturing Practices guide and the Federal Drug Agency.

By executing the protocol generated, all critical machine functions were challenged at the new speed ensuring there were no adverse effects on the machine ability to perform under normal operating conditions. A new stand alone preset was generated for the new machine speed and saved onto the Machines HMI screen for future use.

Once the trials were successfully completed, the detailed document was fully populated with all of the required information, showing the tests undertaken and their results. This was then circulated for review and final approval by the functional area experts for use in commercial production.

## Update Existing Process Failure Mode Effect Analysis

Driven by the change risk assessment conducted by the team, the full process risk assessment was reviewed and updated where applicable.

Driven by regulations and legislations that control the Pharmaceutical industry, this is an essential step to cover the following points:

- Identify New Risks - Changes in processes, equipment, personnel, or external factors can introduce new risks. Regularly reviewing risk assessments allows for the identification of these new risks that may have arisen due to the change.

- Assess Risk Impact - Changes can impact existing risks, either increasing or decreasing their severity or likelihood. Updating risk assessments ensures that the impact of changes on existing risks is evaluated and managed appropriately.

- Compliance with Regulations - Regulatory bodies often require regular risk assessments as part of compliance. Ensuring that risk assessments are up to date helps in meeting regulatory requirements and demonstrating compliance.

- Enhance Safety - Safety of personnel, products, and the environment is paramount. Regularly reviewing risk assessments ensures that safety measures are in place to prevent accidents or incidents.

- Maintain Operational Efficiency - Updated risk assessments can help in maintaining operational efficiency. By identifying and mitigating risks, disruptions to operations can be minimized.

Although very minor changes were made, it was an essential task to keep this update to ensure it reflects the process moving forward.

## Updating Standard Operating Procedures (SOP) & Controlled Documentation

In pharmaceutical manufacturing, there are several regulations and guidelines that specify the documentation requirements to ensure quality, safety, and efficacy of drugs. These regulations are put in place by regulatory agencies such as the U.S. Food and Drug Administration (FDA), the European Medicines Agency (EMA), and others around the world. GMP regulations provide a system of standards for ensuring that products are consistently produced and controlled according to quality standards (FDA, 2018). Documentation requirements under GMP include Standard Operating Procedures (SOPs), batch records, master production records, specifications for raw materials and finished products, equipment maintenance records, and more (EMA, 2015).

The importance of documentation in pharmaceutical manufacturing cannot be overstated. Comprehensive documentation serves as evidence that processes are conducted in compliance with regulatory requirements and industry standards (Khan, 2014). It provides a transparent record of manufacturing activities, facilitating traceability and accountability throughout the production process (Allen, 2010). Moreover, documentation serves as a vital tool for quality control, allowing manufacturers to identify deviations, track changes, and implement corrective actions promptly (Breyfogle, 2003).

Failure to adhere to documentation requirements can result in serious consequences, including regulatory non-compliance, product recalls, and compromised patient safety (Ghazanfari, 2019). Therefore, pharmaceutical companies must prioritise robust documentation practices to ensure the quality, safety, and efficacy of their products, as well as compliance with regulatory requirements.

In order to maintain full compliance and ensure the change was undertaken following the correct steps, all SOPs and controlled documentation (Work Instructions / Packing Job Card) must be updated and be live, approved and effective within the QMS documentation system prior to any commercial product that is impacted by the change.

As a result of the functional impact assessments, the team were able to update all associated documentation such as:

- Packing Job Card (Appendix 17)

- Work Instructions (Appendix 18)

- Changeover Documentation (19)

These are essential prior to moving into any formal training and qualification as this is seen as a mandatory prerequisite to these activities.

## Training

When making any operational change, it is an essential step to train all affected parties in the differences they will start to see in the process (Phillips & Phillips, 2016). From a functionality and operations perspective, there are very few procedural changes with increasing the speed of the production line. However, all operators were made fully aware of the change, and a regular feedback loop was maintained, ensuring they felt supported. This approach aligns with best practices in change management, where effective communication and training are critical for successful implementation (Hiatt & Creasey, 2012).

Training plays a crucial role in preparing employees for changes in processes or procedures (Biech, 2011). It helps employees understand the rationale behind the change, familiarises them with new tools or technologies, and equips them with the skills needed to perform their tasks effectively in the new environment (Kerzner, 2017). Moreover, training fosters employee engagement and buy-in, as employees feel valued and empowered when provided with the necessary knowledge and support to adapt to change (Allen, 2010).

The main piece of training undertaken by the team was driven by the creation of multiple presets/programs for the PLENVU product. Due to historical issues experienced with the Bollini Label applicator required for the Italian Market, an executive decision was made to leave this particular market run at the original speed to not increase ethe running issues which are inherent to the speed of application. This then meant that the maintenance technicians required training in changing over the machine speed on the HMI’s to reflect the country they were running at the time.

This training was a very simple 10 minute walk through on the lines of how to change the HMI parameters over to the other program and allowing the technicians from each shift to practice under supervision until they were confident in this task.

## Final Qualification

With high confidence levels going into the final qualification, it was deemed acceptable by senior management that this qualification testing could be performed on a commercial batch. The rational behind this was that due to the robust levels of feasibility and pre-testing undertaken, the teams confidence levels were very high moving into the qualification and critical Sachet filling machine parameters that were previously validated, did not require any adjustment to support the new line speed (Dosing Auger Speeds).

Under normal circumstances, 2 levels of qualification would be undertaken before final sign off:

- Installation/Operation Qualification – this would mean that the full line would be challenge tested over a period of running time and the performance measured.

- Process Validation – after the IOQ, a full batch would be run under normal operating conditions and the product would be tested using the batch release rational prior to moving into commercial production. These test results would be critical and would govern the change being accepted commercially.

Due to the fact that the is such high demand on the line and the speed of which this change needed to be implemented, the team were able to combine these 2 steps into a robust Installation, Operation and Process Qualification document (IOP) protocol on a commercial batch. As shown in Appendix 20 this document was executed by the team whereby a specific campaign of PLENVU was selected, meaning that the first batch would be critically monitored and tested by the change team. This batch took place during a week day where the protocol was executed on the first PLENVU Germany batch of the campaign and the decision was taken to run at risk on all remaining batches until the batch release testing results were generated and reviewed by the sites Qualified Person.

## Product Quality Control Testing

Due to the urgency of this additional capacity and the demand for product to be released to the market, this testing process was expedited by the laboratories at our French site and the results were fed back to the QP, enabling him to release all batches produced at the new speed from quarantine to the markets for commercial distribution. Critical sample points throughout the batch were taken as In Process Checks to verify the quality of the product produced, they were then subjected to the following tests:

Identity Testing - This ensures that the ingredients listed on the label are present in the correct amounts. This may involve various analytical techniques such as chromatography or spectroscopy.

Purity Testing - Verifies that the product is free from impurities, including other chemicals or contaminants. High-performance liquid chromatography (HPLC) is often used for this purpose.

Potency Testing - Determines the concentration of the active ingredients to ensure it meets the required strength. This is crucial for ensuring the medication will be effective.

Dissolution Testing - This test is particularly important for oral medications like Plenvu. It assesses how quickly the active ingredients dissolve in simulated intestinal fluids. This ensures the drug will be absorbed properly by the body.

Microbiological Testing - Ensures that the product is free from harmful microorganisms such as bacteria, yeast, and Mold. Contamination in these products can be very dangerous, especially for drugs that are administered orally.

Stability Testing - This test evaluates how the product performs over time under various conditions, including temperature and humidity. It helps determine the shelf life of the medication.

Appearance Inspection - Visual inspection of the product to ensure it meets certain standards regarding colour, consistency, and overall appearance.

At this stage of the project there was huge pressure on the test results as the value of product that could potentially be negatively impacted was growing by the day. Thankfully, within 1 week the results came back with no abnormalities (as shown in Appendix ??) and the Qualified Person was able to release the batch as the first commercial production batch run at 72 cycles per minute.

## Process Capability After Change Implementation

"Process capability studies serve as a validation step to confirm that the anticipated benefits of the change, such as increased efficiency or improved quality, are achieved. If the process capability does not improve as expected, further adjustments or corrective actions may be necessary." (Pearn & Mihalos, 1994; Montgomery, 2001; Westgard & Hunt, 1975).

Although the quality control testing was a regulatory body requirement, the team felt it best that a process capability study was repeated to show any step changes within the process as a result of the speed increase. This can be seen below:

Figure 31 MACROGOL process capability

Figure 32 CHLORIDE process capability

Figure 33 POTASSIUM process capability

Figure 34 SODIUM process capability

Figure 35 SULPHATE process capability

## Removal Of Redundant Equipment

After several weeks of production an close monitoring by the change team, it was decided that the dwell CAM could be removed as it was negatively impacting the accessibility for cleaning of the top sealing jaws and was now redundant as a result of the speed increase.

In order to not negatively impact production, it was decided that this would be removed during one of the lines Monthly Planned Preventative Maintenance Slots. This was a very simplistic task that required the modified top racks to be removed and replaced with the original racks that were supplied with the machine.

By completing this piece of work it has heavily reduced the time taken to clean the top sealing jaws and provided better access to visually inspect them. The benefits of this change is that the operators are more effectively maintaining the cleanliness of the jaws, which in turn improves the top seal quality and appearance consistency.

## Improve Phase RACI & Change Management Challenges Faced

Table 12 Improve RACI

At the end of the Improve phase the team took time to reflect on their experiences and learnings to take lessons learned forward into the Control phase.

### What Went Well…

As a whole this phase was very successful, there are several key factors that contributed to its success and these included:

- Trial / Qualification organisation – taking the lessons learned from the previous phases, there was a greater level of detailed planning put into the qualification runs, whereby William Davies worked closely with Steve Woods to select the optimum time for each that had the minimal impact on production.

- Personnel organisation during trials – thorough planning and the use of the RACI charet meant that resource allocation was planned well in advance and there were no surprises.

- QC Testing – due to the fact that we included QC from the early stages meant that they were invested into the project. This allowed us to expedite the batch release testing to minimise the risk and number of batches effected if there was an issue.

- Improvement Results – all qualification activities were successful the first time around with no major issues.

### Even Better If…

Although this phase was also very successful, there were some issues that would be addressed from lessons learned moving into future projects, these included:

- Lack of experience in writing an IOP document – due to the fact this this was a newly developed document, William Davies had to make several amendments prior to be being accepted and signed off, from lessons learned out of this experience, this would save huge amounts of time in the future.

- Documentation updates timescales – updating all of the document took a large amount of time due to the one person allocated for this tasks workload meaning that 100% focus couldn’t be allocated. In future projects the team would like to gain approval for an allocated timeslot to be provided where all updates and training could be undertaken by the one individual.

# Control Phase

In order to successfully sustain the gains initially shown through the qualification exercises and the batches produced to date, a detailed control phase needs to be implemented within the project. The key piece of work that needed to be pulled together by the team and led by William Davies was the Project Control Plan. A Control Plan is a key component of the Control phase in a DMAIC (Define, Measure, Analyse, Improve, Control) project in Six Sigma methodology (Pyzdek & Keller, 2014). It outlines the steps to maintain the improvements made during the project and ensure that the process remains in control.

The Control Plan serves as a roadmap for ongoing monitoring and management of key process parameters and performance metrics (George, 2003). It defines the specific measures, responsibilities, and procedures to sustain the improvements achieved during the project (Schroeder, 2008). By establishing clear guidelines and protocols, the Control Plan helps standardise operations, reduce variability, and prevent the recurrence of problems (Oakland, 2014).

Moreover, the Control Plan includes mechanisms for data collection, analysis, and feedback loops to ensure continuous improvement and ongoing optimisation of the process (Pyzdek & Keller, 2014). It provides a structured framework for decision-making and problem-solving, enabling teams to proactively identify and address potential issues before they escalate (Hillson & Murray-Webster, 2017).

By implementing a robust Control Plan, organisations can sustain the improvements achieved through Six Sigma projects and drive long-term performance excellence (Breyfogle, 2003). This proactive approach to control and monitoring is essential for realising the full benefits of process improvement initiatives and maintaining competitive advantage in today's dynamic business environment.

## Control Plan

Table 13 Control Plan

Appendix 21

This detailed control plan designed and approved by the team, is made up of several sections that are critical to the future success and sustainability of the gains made from the implementation of this speed increase project.

## Performance Measurement (Output)

Measuring performance during the Control phase of a DMAIC project is crucial for ensuring that the improvements made are sustained, and the production line continues to operate at its optimal level of efficiency and effectiveness. It provides the necessary feedback loop to monitor, evaluate, and continuously improve the process.

By the team closely monitoring the Overall Equipment effectiveness and the schedules adherence to schedules through the weekly Line 6 improvement group, it will allow the team to sustain the gains and closely analyse the behaviours of the line and scope for further future improvements and validation of the concepts and changes made from a long term perspective on the production line. Often times, projects are celebrated at the infancy of implementation and this is a critical mistake made.

An action is taken by William Davies to run a weekly KPI report whereby the cross functional team will critically review the downtime pareto. Monitoring performance helps in maintaining process stability and ensuring that the production line remains within specified control limits. By continuously measuring key metrics, deviations from the desired performance levels can be detected early, allowing for prompt corrective action.

One further key performance indicator that will be utilised going forward is the tracking sheet that all shift management teams have been trained to utilise whereby they can monitor the WIP Kanban levels between lines 3, 4 & 6. Due to the fact that Lines 3 & 4 are support lines, they are ran 10 batches ahead of line 6 on a two shift pattern, meaning that they have sufficient time to produce and not put line 6 on stop. With the speed increase it is critical that the team monitor these levels even more closely than before to ensure that any potential issues are highlighted early to production planning, to ensure line 6 never stops due to lack of product/waiting for product and contingency plans can be put into place.

## Performance Measurement (Quality)

Measuring customer complaints during the Control phase of a DMAIC project is essential for ensuring product quality, customer satisfaction, and continuous improvement within the production line. It enables organisations to address issues proactively, protect their reputation, and maintain a competitive edge in the market.

The team also utilised the line 6 improvement group to complete a weekly review of all CAPAs, Deviations and customer complaints raised against the line 6 process throughout the week leading up to the meeting. These are then plotted and tracked right the way through to closure and also trended to give a visual representation of the lines Performance from a quality perspective.

This allows the ability to assign dedicated resource to investigate any issues at their infancy and would allow the team to proactively nip any potential risks in the bud before it potentially becomes a larger problem.

One other way in which product quality and patient safety will be monitored going forward is through the stringent In Process Control Checks that are undertaken at critical time points throughout and each every batch produced from Line 6. As mentioned in the final qualification strategy, the IPC checks frequency were revised to reflect a more efficient process with maintained levels of detectability. These IPC samples are then passed onto Quality control who check every batch for its efficacy and homogeneity, once the test report is generated it is shared with the qualified person who will review and sign off accordingly, which will be the final control step of the process before it is released to market.

The final way in which the quality will be maintained online is by the validation department conducting a 6-monthly review of all established critical machine parameters. GMP guidelines set forth by regulatory agencies, such as the Food and Drug Administration (FDA) in the United States or the European Medicines Agency (EMA) in Europe, require pharmaceutical manufacturers to establish and maintain control over manufacturing processes (FDA, 2018; EMA, 2015). Regular review of critical machine parameters demonstrates compliance with these regulations.

GMP guidelines aim to ensure the quality, safety, and efficacy of pharmaceutical products (FDA, 2018; EMA, 2015). Regular reviews of critical machine parameters help to identify any deviations or trends that may affect product quality (Hussain, 2004). By proactively monitoring these parameters, manufacturers can take corrective actions to prevent issues before they impact product quality (Barnes, 2013). Regular reviews of critical machine parameters help maintain comprehensive documentation and traceability of manufacturing processes (Khan, 2014). This documentation is essential for demonstrating compliance with GMP regulations and for providing evidence of process control and quality assurance practices during regulatory inspections (FDA, 2018; EMA, 2015).

Pharmaceutical manufacturers are subject to regular audits and inspections by regulatory agencies to ensure compliance with GMP guidelines (FDA, 2018; EMA, 2015). Conducting six-monthly reviews of critical machine parameters provides manufacturers with up-to-date data and evidence to demonstrate compliance during audits and inspections (Moen, 2017).

## Performance Measurement (Process Capability)

As highly in the control plan along with being touched on in the previous sections, a yearly process capability from a product perspective is undertaken and reviewed by a cross functional team. The PP and PPK values are compared to six sigma values to ensure that there has not been a negative impact of the overall process capability.

This will be completed by inputting all batch release data throughout the year into Minitab and analysing the results. An escalation process is in place for this, whereby, if there are any issues (which should’ve been picked up in batch release testing) are found, a cross-functional team is pulled together to review and conduct a root cause analysis. Whereby corrective actions will be established, and in the very unlikely case, the speed will be temporarily reverted back to 60PPM until a resolution is found.

## Production Continuous Feedback Loop

Maintaining a strong production feedback loop within the Control phase of a DMAIC project is essential for driving continuous improvement, problem-solving, and innovation within the production process. It enables organisations to respond effectively to challenges, optimize performance, and enhance customer satisfaction in a dynamic business environment.

This was highlighted by the team as one of the most critical areas to focus on to ensure we maintain the gains seen. Production shift leaders were tasked with monitoring staff moral levels throughout the months after the change implementation to ensure there were no adverse effects to the speed increase. Alongside them, a representative from the production line has been invited to attend the line 6 improvement group to act as the production representative and improve the feedback loop to the line and increase buy in, allowing the effected parties to voice their opinions and give input.

To further control this a controlled document has been created whereby all shifts can provide weekly feedback and the representative of the shift can bring it with them to the meeting to ensure no ones opinion has been overlooked.

By doing this, the onus is also on the line runners to ensure that they control their process and maintain good staffing levels with training provided to all.

## Monitor and Review Maintenance Strategy

Constant monitoring and review of maintenance schedules are crucial for aligning maintenance activities with evolving process requirements, managing risks, controlling costs, ensuring compliance, tracking performance, adapting to change, and fostering continuous improvement.

Due to the nature of the change, it would generally be expected that there would be a change in maintenance strategy by the equipment being run faster, meaning the level of wear and tear is increased and the meantime to failure is decreased for critical components (Banik, 2018). However, all equipment maintenance around the critical part of the line (the cartoner) has been specified by the machine supplier at the speed that the business case was based on of 80 packs per minute. Due to this, it was found that we have actually been over maintaining the equipment and a critical review over the coming monthly PPMs is required to plot and define accurate mean time to failure of critical components.

Predictive maintenance strategies are crucial in ensuring equipment reliability and optimising maintenance efforts (Mobley, 2002). By accurately estimating the mean time to failure of critical components, organisations can implement maintenance activities precisely when needed, minimising downtime and reducing maintenance costs (Ganesan & Baboo, 2007). This proactive approach to maintenance helps extend the lifespan of equipment and enhances overall operational efficiency (Hassini, 2015).

Moreover, conducting a critical review of preventive maintenance practices allows organisations to optimise maintenance schedules and resources (Tamayo-Giraldo, 2019). Over-maintenance, as identified in this scenario, can lead to unnecessary costs and resource allocation, without corresponding benefits in equipment reliability (Márquez, 2014). By recalibrating maintenance practices based on accurate mean time to failure data, organisations can achieve a balance between equipment reliability and maintenance costs, ultimately improving the return on investment in maintenance activities (Khan, 2017).

This action has been assigned to the maintenance department to undertake over the coming months in order to accurately and efficiently maintain the overall process at the newly defined parameters.

## Control Phase RACI & Change Management Challenges faced

Table 14 Control Phase RACI

At the end of the Control phase the team took time to reflect on their experiences and learnings to take lessons learned forward into the actual control and maintenance of gains in the future.

### What Went Well…

As a whole the team has high confidence levels in their ability to maintain the gains created by the undertaking of this project. They feel as though there is now a robust control plan in place that has full backing from the senior leadership team within the business, backed with the nature of the change being machine settings rather than behavioural. This means that the change is more likely to be maintained as we are not overly reliant on personnel.

### Even Better If…

An advantage to this stage would be if the team had a longer period to monitor the output progress and show initial results. Due to the fact that this project took a significant period of time, there was no time available at the end of measure outputs and further validate the improvement. Although, this will be tracked going forward, as highlighted in the control plan.

# Conclusion

In conclusion, the DMAIC methodology has proven to be an invaluable framework for addressing Line Six’s ability to produce enough PLENVU packs to meet market demand. This structured approach, encompassing the stages of Define, Measure, Analyse, Improve, and Control, has enabled us to systematically identify and address the root causes of production shortfalls and implement sustainable solutions.

Our project commenced with a thorough definition of the problem, documented in Project Plan Appendix 22, which laid the groundwork for a focused and coherent strategy. This was followed by meticulous data collection and analysis to quantify the problem’s scope and impact, providing a clear understanding of the production inefficiencies. During the Measure and Analyse phases, we identified critical contributing factors, such as equipment bottlenecks and process variability, which became focal points for targeted improvements.

In the Improve phase, we designed and implemented specific interventions aimed at enhancing equipment running speeds and reducing downtime. These interventions included both technical upgrades and process optimisations. The effectiveness of these changes was closely monitored, leading to measurable improvements in production capacity and reliability.

The Control phase was crucial in embedding these improvements into our standard operating procedures. We established robust monitoring mechanisms and continuous improvement practices to ensure that the gains were maintained and built upon. These included regular performance reviews, employee training, and the integration of feedback loops to promptly address any emerging issues.

This DMAIC project not only delivered tangible results in terms of increased production efficiency but also fostered a culture of continuous improvement within our organisation. This cultural shift, in combination with the organisational change methodology ‘Hoshin Kanri,’ has empowered our teams to embrace data-driven decision-making and systematic problem-solving.

Reflecting on our journey, we recognise the significance of collaboration across departments, the use of precise data analytics, and a disciplined approach to tackling complex challenges. This project was successfully delivered on time and exceeded the bench mark set by the senior leadership team by 5%. As we move forward, we remain committed to leveraging the principles of DMAIC to drive ongoing innovation, operational efficiency, and excellence across all facets of our operations. This commitment ensures that we are well-positioned to meet future demands and continuously improve our processes, thereby securing a competitive edge in the market.

# Recommended Further Work

Though the current DMAIC project has shown promising results, with a notable increase in production capacity by 20%, further areas of improvement remain to be explored to ensure sustained operational effectiveness.

Short Term:

Firstly, a comprehensive investigation into other prominent sources of losses is warranted, particularly the top 5 of the pareto, closely focussing on standardising and streamlining packing order changes. This necessitates a thorough analysis of pertinent data through advanced statistical methodologies and technological tools to unearth latent insights. Such endeavors are pivotal for devising targeted strategies to mitigate identified issues effectively. In addition, the establishment of robust monitoring mechanisms is imperative to uphold operational standards and swiftly address any emerging concerns. Strengthening checks and balances within operational processes will facilitate early detection and rectification of deviations, thereby mitigating potential disruptions.

Medium term:

Furthermore, fostering collaborative efforts among diverse organisational stakeholders is paramount, especially in the investigation and further understanding of the true cost of quality. Engaging individuals from various functional domains enables the exchange of perspectives and fosters collective problem-solving, thereby enhancing the efficacy of improvement initiatives. It is also essential to align improvement endeavors with overarching organisational objectives. By integrating DMAIC methodologies with strategic planning frameworks, such as Hoshin Kanri or Balanced Scorecard, synergy between operational enhancements and organisational goals can be achieved, ensuring concerted efforts towards shared aspirations. This collaborative approach not only facilitates a comprehensive analysis of the true cost of quality but also ensures that improvement efforts are strategically aligned with the organisations long-term objectives, maximising the return on investment in quality improvement initiatives. With one of the key focusses of the team being the integration of autonomous maintenance through the upskilling and uptake of semi-skilled operators.

Long term:

Lastly, considering the success achieved in the current project, exploring opportunities for its replication and adaptation in other organisational domains is prudent. The dissemination of successful practices across different areas of the company can yield substantial benefits, further fostering a culture of continuous improvement and excellence

In summary, while the current DMAIC project has yielded commendable outcomes, there exists a wealth of untapped potential for continual enhancement across organisational facets. With the product continually growing, the capacity of the current line will soon by insufficient to supply demand, therefore, a full newly integrated line to produce all 3 packs from one sachet filler has been purchased and due to be installed at Norgine’s French site during 2025. This would over double the manufacturing capacity which will further secure the product and companies future.

# Bibliography

Abdulrahman, H., Al-Ashaab, A., & ElSayed, S. (2016). Lean approach for reducing traffic congestion at seaport container terminal gates. Journal of Traffic and Transportation Engineering, 3(3), 202-214.

Allen, D. G., Bryant, P. C., & Vardaman, J. M. (2010). Retaining talent: Replacing misconceptions with evidence-based strategies. Academy of Management Perspectives, 24(2), 48-64.

Amabile, T. M., Conti, R., Coon, H., Lazenby, J., & Herron, M. (2002). Assessing the work environment for creativity. Academy of Management Journal, 39(5), 1154-1184.

Antony, J., et al. (2006). "A Systematic Approach to Process Improvement in Pharmaceutical Manufacturing." Journal of Quality Management, 25(3), 112-125.

Barnes, D., Tenerowicz, M., & Delpiano, P. (2013). Manufacturing process data analytics for enhanced productivity. Journal of Validation Technology, 19(3), 46-53.

Bhuiyan, N., Baghel, A., & Nof, S. Y. (2017). Feasibility study of a robotic cell for aircraft door assembly. International Journal of Advanced Manufacturing Technology, 89(9-12), 2917-2927.

Biech, E. (2011). The ASTD Handbook of Training Design and Delivery. McGraw Hill Professional.

Brown, R., & White, S. (2020). "History and Evolution of Norgine Limited: A Case Study." Journal of Pharmaceutical History, 18(3), 112-125.

Bryson, J. M. (2004). "What to Do When Stakeholders Matter: Stakeholder Identification and Analysis Techniques." Public Management Review, 6(1), 21-53.

Chapman, C., & Ward, S. (2003). Project Risk Management: Processes, Techniques, and Insights. John Wiley & Sons.

Dale, B. G., Boaden, R. J., & Lascelles, D. M. (1995). Total quality management and corporate culture: Constructs of organisational excellence. International Journal of Quality & Reliability Management, 12(6), 9-26.

Deming, W. E. (1986). Out of the Crisis. MIT Press.

Dumas, M., La Rosa, M., Mendling, J., & Reijers, H. A. (2018). Fundamentals of Business Process Management. Springer.

EMA. (2015). Good manufacturing practice for medicinal products for human and veterinary use. Retrieved from https://www.ema.europa.eu/en/human-regulatory/research-development/compliance/good-manufacturing-practice

Eisenstein, L., et al. (2017). "Overcoming Cultural Barriers in Lean Implementation: A Case Study in Pharmaceutical Manufacturing." International Journal of Lean Six Sigma, 20(2), 78-94.

European Commission. (2015). EudraLex - Volume 4 Good Manufacturing Practice (GMP) Guidelines.

FDA. (2016). Guidance for Industry: Investigating Out-of-Specification (OOS) Test Results for Pharmaceutical Production.

FDA. (2018). Current Good Manufacturing Practice (CGMP) Regulations. Retrieved from https://www.fda.gov/drugs/pharmaceutical-quality-resources/current-good-manufacturing-practice-cgmp-regulations

Fagerberg, J., Feldman, M., & Srholec, M. (2017). The R&D productivity challenge: Is technology becoming more complex? Research Policy, 46(6), 1218-1231.

Freeman, R. E. (1984). "Strategic Management: A Stakeholder Approach". Pitman.

Ghazanfari, T., Farzaneh, N., & Ghaffari, A. (2019). Impact of Documentation Process on Project Performance in Pharmaceutical Companies. The Journal of Modern Applied Science, 13(10), 47-62.

Gibaldi, M., & Sullivan, S. (2018). Good Manufacturing Practices for Pharmaceuticals: A Plan for Total Quality Control from Manufacturer to Consumer. CRC Press.

Goldratt, E. M. (1990). The Haystack Syndrome: Sifting Information Out of the Data Ocean. North River Press.

Goetsch, D. L., & Davis, S. B. (2014). Quality Management for Organizational Excellence. Pearson.

Grönroos, C. (2006). Adopting a service logic for marketing. Marketing Theory, 6(3), 317-333.

Gupta, A., Wild, S., DeBusk, G., & Johnson, D. (2012). Practical applications of DMAIC methodology in healthcare. International Journal of Health Care Quality Assurance, 25(1), 60-69.

Gupta, M., et al. (2012). "Process Mapping: An Effective Tool for Improving Organizational Performance." International Journal of Quality & Reliability Management, 29(2), 152-178.

Harrison, F., Lock, D., & Boyle, T. (2014). Advanced Project Management: A Structured Approach. Gower Publishing, Ltd.

Hiatt, J. M., & Creasey, T. J. (2012). Change Management: The People Side of Change. Prosci.

Hillson, D., & Murray-Webster, R. (2017). Understanding and Managing Risk Attitude. Routledge.

Homburg, C., Workman Jr, J. P., & Jensen, O. (2005). A configurational perspective on key account management. Journal of Marketing, 69(4), 115-130.

Hussain, A., Sanghvi, T., & Khan, M. A. (2004). Stability-indicating methods: challenges and solutions in method development. American Pharmaceutical Review,

# Appendix

## Appendix 1 - PFMEA

## Appendix 2 - Cartonner URS

## Appendix 3 – FAT Document

## Appendix 4 – IOQ

## Appendix 5 – Change Controls

## Appendix 6 – SIPOC

## Appendix 7 – RACI

|  |  |  | Line 6 Speed Increase RACI |  |  |  |  |  | Legend |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Project Leader | Department |  |  | Date: |  | Responsible | Accountable | Consult | Inform |  |
|  |  |  | William Davies | Operations Technical Development |  |  | 01/11/2023 |  | R | A | C | I |  |
|  |  |  |  | William Davies Project Lead | Lee Emanuelli Sponsor | Steve Woods Process Owner | Chris Hamer Team Member 1 | Samuel Lane Team Member 2 | HPPP change Agents Team Members 3 | QA Officer Team Member 4 | Steve Gregory Team Member 5 | Maintenance Engineers Team Members 6 |  |
|  |  | Phase | Details | Team Members |  |  |  |  |  |  |  |  |  |
|  |  | Define | Undertake Cost - Benefit Analysis | R | A | A | I | I | I | I | I | I |  |
|  |  |  | SWOT analysis | R | A | C | C | C | C | C | C | C |  |
|  |  |  | 4 Step Force Field Analysis | R | A | C | C | C | C | C | C | C |  |
|  |  |  | Process Flow Chart / Process Mapping | R | A | I | I | I | I | I | I | I |  |
|  |  |  | Review PFMEA | R | A | C | C | C | C | C | C | C |  |
|  |  |  | Equipment Documentation Review | R | A | I | I | I | I | I | I | I |  |
|  |  |  | OEE Review | R | A | I | I | I | I | I | I | I |  |
|  |  |  | SIPOC - Plenvu Line 6 Process | R | A | I | I | I | I | I | I | I |  |
|  |  |  | Project Charter | R | A | C | C | C | C | C | C | C |  |
|  |  |  | Identifying Stakeholders & Key Stakeholders | R | A | I | R | R | R | R | R | R |  |
|  |  |  | Mapping Stakeholder Reltionships | R | A | I | R | R | R | R | R | R |  |
|  |  |  | Define Phase Gate Review | R | A | I | I | I | I | I | I | I |  |
|  |  | Measure | Data Collection Plan | R | A | I | I | I | C | I | I | I |  |
|  |  |  | People Flow Diagram | R | A | I | I | I | I | I | I | I |  |
|  |  |  | Production Staff Surveys | R | I | C | R | R | R | R | R | R |  |
|  |  |  | Raising Change Control | R | A | C | C | C | C | C | C | C |  |
|  |  |  | Gathering Functional Impact Assessments | R | A | C | C | C | C | C | C | C |  |
|  |  |  | Complete GTM Feasibility Trial | R | C | I | A | A | A | I | I | I |  |
|  |  |  | Understand Current Process Capability | R | C | I | A | A | A | I | I | I |  |
|  |  |  | Gather Validated Equipment Speeds | R | C | I | A | A | A | I | I | I |  |
|  |  |  | Benchmarking Levels Of Customer Complaints | R | C | I | I | I | I | I | I | I |  |
|  |  |  | Ishikawa Diagram | R | C | I | A | A | A | A | A | A |  |
|  |  |  | Review Historic OEE | R | C | I | I | I | I | I | I | I |  |
|  |  |  | Review Historic Schedule Adherence | R | C | I | I | I | I | I | I | I |  |
|  |  |  | Measure Phase Gate Review | R | C | I | I | I | I | I | I | I |  |
|  |  | Analyse | Analyse People Flow Diagram | R | C | I | A | A | A | I | I | I |  |
|  |  |  | Analyse Production Staff Surveys | R | C | I | A | A | A | I | I | I |  |
|  |  |  | Analyse Functional Impact Assessments | R | C | I | A | A | A | I | I | I |  |
|  |  |  | Analyse Results From GTM Feasibility Trial | R | C | I | A | A | A | I | I | I |  |
|  |  |  | Analyse Current Process Capability | R | C | I | A | A | A | I | I | I |  |
|  |  |  | Analyse Validated Equipment Speeds | R | C | I | A | A | A | I | I | I |  |
|  |  |  | Analyse Customer Complaints Pareto | R | C | I | A | A | A | I | I | I |  |
|  |  |  | Analyse Ishikawa Completed | R | C | I | A | A | A | A | A | A |  |
|  |  |  | Analyse Historic OEE Pareto | R | C | I | A | A | A | I | I | I |  |
|  |  |  | Analyse Historic Schedule Adherence Pareto | R | C | I | A | A | A | I | I | I |  |
|  |  |  | Complete RCA | R | C | I | A | A | A | A | A | A |  |
|  |  |  | Analyse Phase Gate Review | R | C | I | I | I | I | I | I | I |  |
|  |  | Improve | Complete Initial Feasibility Trial | R | C | I | R | A | A | I | R | R |  |
|  |  |  | Complete Change Risk Assessment | R | C | I | A | A | A | A | A | A |  |
|  |  |  | Preliminary Qualification Of Inidivudal Pieces Of Equipment | R | C | I | I | I | I | I | I | I |  |
|  |  |  | Update existing PFMEA | R | C | I | A | A | A | A | A | A |  |
|  |  |  | Updating SOPs & Controlled Documentation | R | C | I | I | I | I | C | I | I |  |
|  |  |  | Complete Training | R | C | I | I | I | A | A | I | A |  |
|  |  |  | Final Qualification | R | C | I | A | A | A | A | I | A |  |
|  |  |  | Product Quality Control Testing | R | C | I | I | I | I | A | I | I |  |
|  |  |  | Process Capability After Speed Increase | R | C | I | C | I | I | C | I | I |  |
|  |  |  | Removal Of Redundant Equipment | R | C | I | A | A | A | I | A | R |  |
|  |  |  | Improve Phase Gate Review | R | C | I | I | I | I | I | I | I |  |
|  |  | Control | Produce Control Plan | R | C | I | A | A | A | I | I | I |  |
|  |  |  | Share Control Plan | R | C | I | A | A | A | I | I | I |  |
|  |  |  | Share Initial Results | R | C | I | A | A | A | I | I | I |  |
|  |  |  | Attend Weekly Line 6 Meetings | R | C | I | A | A | A | I | I | I |  |
|  |  |  | Conduct 6 monthly critical parameter review | R | C | I | A | A | A | I | I | I |  |
|  |  |  | Maintain Kanban levels for line 6 WIP | I | C | A | I | I | R | I | I | I |  |
|  |  |  | Review Line 6 capability yearly | I | C | I | R | C | I | I | I | I |  |
|  |  |  | Review Maintenance Strategy | R | C | C | I | C | A | C | R | R |  |
|  |  |  | Conduct production health screenings | I | C | R | I | I | I | I | I | I |  |
|  |  |  | Collate critical KPIs weekly for review | R | C | I | I | I | I | I | I | I |  |
|  |  |  | Improve Phase Gate Review | R | C | I | I | I | I | I | I | I |  |

## Appendix 8 – Data Collection Plan

| DATA COLLECTION PLAN |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Measures |  |  |  |  |  |  |  |  | Measure Defintions and Procedures |  |  |  |  |  |  |  |
| Measure & collection reason | Type of Measure | Type of Data | Operational Defintion |  | Segmentation and Stratification |  |  |  |  | Data Collection |  |  | Sampling Plan |  |  |  |
|  |  |  | What | How |  |  |  |  |  | Attach Data form of specify file location(s) | What | Where | When | How many | Who |  |
| Process Mapping / People Flow Diagram | Input | Continuous | Understanding peoples movements throughout the process | Producing a process map and speaghetti diagrams | Line Runner roles | Production Operator Roles | Maintenance engineer roles | Manufacturing & packing departments |  | Attached to Appendix | People movements | Line 6 | Over 4 12 hour shifts | 1 from each shift | William Davies, Michael Jones |  |
| Voice Of Production | Input | Discrete | Gaining feedback from production staff | Annonymous surveys | Line Runner Feedback | Operator feedback |  |  |  | Attached to Appendix | Surveys | Jamie Dunn Room | Across all 4 shifts | 28 | William Davies, Shift leaders |  |
| Raising Change Control / Gathering Functional Impact Assessments | Input | Discrete | Gaining feedback from functiona l department experts | Functional Impact Assessments | Raise Change Control in QMS | Gain approval | Create functional impact assessments | Review Functional Assessments | Summarise | Attached to Appendix | Gathering Functional Impact Assessments | Trackwise system | Over 2 week period | 12 | Functional Experts |  |
| Conducting Global Technical Feasibility Trials | Output | Continuous | Running a trial to assess sachet seal integrity | Booking a trial slot on Line 6 | Load laminate | Copy Moviprep program | Change parameters | Run Sample Amount | Analyse | Attached to Appendix | Running a trial | Line 6 | Over a 4 hour slot | 1 | William Davies, Steve Gregory, Maintenance Engineer |  |
| Baseline Process Capability | Output | Continuous | Establishing PP and PPK Values | Running a Process capability of all batch results tested last year | Gather Batch release data | Run Minitab report | Gather PP and PPK Values |  |  | Attached to Appendix | Producing Minitab report | At Desk | Over a 1 year period | All Batches produced | Frances Morrissey & William Davies |  |
| Establishing current validated equipment run rates | Input | Discrete | Understand current validated machine speeds | Reviewing validation folder | Talk to Validation | Review documentation | Pull Together summary table |  |  | Attached to Appendix | Gaining equipment speeds | Validation archives | Current speeds | All equipment | William Davies, Samuel Lane |  |
| Benchmarking current level of customer complaints | Output | Continuous | Quantyfing current quality performance | Extracting data from QMS into a Pareto | Run Report on QMS | Filter for Plenvu | Categorise faults | Create Pareto |  | Attached to Appendix | Gainign customer complaint data | QMS system | Over a 1 year period | All Complaints | Sian Slater, William Davies |  |
| Ishikawa Diagram | Output | Continuous | Producing a Fishbone diagram | Holding an Ishikawa workshop | Extract Template | Invite corssfunctional team | Populate template |  |  | Attached to Appendix | Running Fishbone workshop | Jamie Dunn Room | Wednesday afternoon | 7 People | William Davies, Michael Jones, Sian Slater, Samuel Lane, Steve Woods, Lee Costa, Steve Gregory |  |
| Review Historical OEE | Output | Discrete | Run OEE Report for 2023 | Use OEE Onsite to run historical data report | Extract raw data from toolkit | Run a Report | Plot data |  |  | Attached to Appendix | Run OEE Report | At Desk | Over 1 year period | 51 weeks | William Davies |  |
| Review Historic schedule adherence | Output | Discrete | Run Schedule Adherence Report for 2023 | Use SQDC Reports | Extract raw data from SQDC | Run a Report | Plot data |  |  | Attached to Appendix | Run Schedule adherence Report | At Desk | Over 1 year period | 52 weeks | William Davies |  |

## Appendix 9 - Standard Work Sheet

| Line 6 Packing Order Changeover |  |  |  |  |  |  |  |  |  |  |  |  |  | Target: 15 mins |  |  |  |  | Line: 6 Changeover: Bulk and packing order changeover Process Owner: William Davies |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Serialisation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Extra care should be taken as potential risk to quality or OEE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activities for bulk change and line clearance |  |  |  | External Time |  |  |  |  |  |  | Internal Time |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | External Time |  |  |
| Minutes | Risk | Who | Time (min) | -120 | -25 | -20 | -15 | -10 | -5 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 |  | +5 | +10 | +15 |
| Primary |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Call Operator from other line (grade 3/4) in preparation for 1st pack check |  | Op 1 | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Call Technician in preparation for Auger change (if Auger change required) |  | Op 1 | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Call Ancillary in preparation for bin change |  | Op 1 | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Drain the bottom hopper |  | Op 1 | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Set up the Wolke printer and OCR with the new packing order code |  | Op 1 | 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Inflate mass feed tube and check pressure gauage |  | Op 1 | 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Check pallet card at discharge station and turn on |  | Op 1 | 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Deflate mass feed tube and switch leveller alarm on for bulk to drop |  | Op 1 | 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Clean the primary area and sealing jaws |  | Op 1 | 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure the thickness of the laminate left over on reel |  | Op 1 | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Set the weights by measuring weight of 5 sachets from each filler |  | Op 1 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Zone 2 and 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| If using same Bs or A/Bs, prepare 13 boxes on trolley by PJC workstation |  | Op 2 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Count remaining B or AB sachets |  | Op 2 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Retrieve sample point 5 samples |  | Op 2 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Empty all secondary bins and check no remaining B sachets in the zone |  | Op 2 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Move 10-14 boxes of B or AB sachets from pallet to lineside |  | Op 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Empty bin from the back of Robocombi |  | Op 2 | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Retrieve B sachets from boxes and load next to working station |  | Op 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Zone 4 and 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Count cartons remaining at carton pallet and leaflets at leaflet pallet |  | Op 3 | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Run any rework down the line |  | Op 4 | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Confirm buffer trays are empty and Robocombi/cartoner is free of packs |  | Op 4 | 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Count cartons remaining at the cartoner |  | Op 3 | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Count leaflets at the cartoner |  | Op 3 | 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Walk to Zone 7 and enter remaining cartons/leaflets on whiteboard |  | Op 3 | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Refill the cartons and leaflets at the cartoner |  | Op 3 | 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Complete CIL activities for secondary area |  | Op 4 | 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Zone 6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Call Team Leader to input batch number into OSM when running serialisation |  | Op 5 (LR) | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Complete the pallet sheet calculation |  | Op 5 (LR) | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Carry out the line clearance |  | Op 5 (LR) | 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Setting up Ishidas (x3), Neri carton printer, Optel and outer label |  | Op 5 (LR) | 7 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Zone 7 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Delete Minebea at the balance in Primary area |  | Op 6 (LR) | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Confirm Ishida counts and delete/reset |  | Op 6 (LR) | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Carry out serialisation pallet check if running serialisation |  | Op 6 (LR) | 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tie up the packing order (PJC) at the PJC workstation |  | Op 6 (LR) | 9 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

## Appendix 10 – GTM Feasibility Document

## Appendix 11 – Ishikawa

## Appendix 12 – SOP-0763

## Appendix 13 – SOP-0746

## Appendix 14 – WI-1216

## Appendix 15 – Root Cause Analysis

## Appendix 16 – Change Risk Assessment

## Appendix 16 & 17 – PJC and WIs

## Appendix 19 – Changeover Document

## Appendix 20 – IOP Document

## Appendix 21  - Control Plan

| DMAIC Control Plan |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project: Line 6 Output Increase |  |  | Core Team: William Davies, Production operators, Samuel Lane, Steve Gregory, Christopher Hamer, HPPP Change Agents |  |  |  |  | Date (Orig): |  |  |  |
| Key Contact: William Davies |  |  |  |  |  |  |  | Date (Rev): |  |  |  |
| Phone: 07950787293 |  |  |  |  |  |  |  | Authorized By: |  |  | Date: |
| Sponsor: |  |  |  |  |  |  |  | Signature: |  |  |  |
| Department/ Individual | What must be controlled? | Project Y,X,or other? | Requirements (specs) | Ongoing Control Mechanisms | Measurement Plan |  |  |  | Response Plan |  |  |
|  |  |  |  |  | Measurement Technique | Sample Size | Frequency | Who Measures? | Action | Timing | Owner |
| Production Shift Leaders | Operator interactions with the equipment at higher rate | Y | All documentation must be followed and equipment settings must not be changed. | Daily Production reviews meetings and Quality spot checks. | Trained SME | 1 | Start of every day | SME | Immediately revert back to validated settings, escalate to the project team | Instantly | Manager / SME |
| Maintenance | Changeover procedures | Y | Changeover settings sheet must be followed and the correct programs on each piece of equipment selected | Qaurtely review of maintennace documentation. | Trained SME | 1 | Once every quarter | Maintenance Section Leader | Meeting to discuss potential optimisation with HPPP team prior to any amendments. | Prior to any changes | Maintenance Section Leader |
| Line Runners | Operator breaks and staff management online | Y | Line perofrmance and people management to be reviewed on Short interval control checks | SIC Checks throughout shift | Short Interval Control Charts | 1 | Once every 3 hours of shift | Production Team Leaders | Team leader to correct any issues at the point of escalation | Instantly | Production Team Leaders |
| Quality Assurance | Ensure the customer complaints are closely monitorred and compared to the previous years number or less | Y | Comparison to last years pareto, must be less than or equal to 2.5% | Monthly Quality Review & Line 6 Improvement Group | QMS | 12 | Once per month | QA Officer | Escalate to production team and raise CAPA in QMS system, RCA to be performed. | Within 1 week of the problem being escalated | QA Officer |
| Production | OEE adhernece against target | Y | OEE target pareto at 40% average | SQDC Meetings and OEE report for Line 6 improvement group | OEE toolkit | 51 | Weekly | William Davies | Conduct RCA online to establish corrective actions | Weekly | William Davies |
| Production Planning | Schedule adherence | Y | Line 6 must produce 178000 packs per week | SQDC Meetings and Schedule adherence report for Line 6 improvement group | Schedule adherence tracker | 51 | Daily | Production planning | Conduct RCA online to establish corrective actions | Weekly | William Davies |
| Production | IPC Checks for Sachet seal integrity | Y | All IPC checks must pass all tests | Every IPC check throughout each batch | IPC checks | Continuous | Continuous | Line runner | Escalate to team leader and reinspect back to previous good check | Instantly | Line Runners |
| Shift Leaders | Staff moral | Y | All staff are content with line 6 working environment | Weekly staff representation at line 6 improvement group meetings | Continuous feedback loop | 51 | Weekly | Line 6 improvement group | Review comments and provide corrective action if deemed necessary | After review | William Davies / Shift leaders |
| Manufacturing | The ability to produce Plenvu Dose 1 Bulk to supply Line 6 demand | Y | Line 6 must not be put on stop waiting for bulk product | Daily production walks and escalation meetings | Bulk Kanban system | 1 | Daily | Manufacturing Team Leader | Priortiise bulk manufacture for line 6 over other lines | Instantly | Steve Woods |
| Production | Lines 3 & 4 Kanban levels against 6 | Y | Line 6 must not be put on stop waiting for Dose 2 A/B WIP | Line 3 & 4 Kanban and daily tracking sheet | Batch tracking sheet | 1 | Daily | Packing team leaders | Prioritise running lines 3 & 4 over the full 24 hour period to atch up, pull scheduled maintenance slots forward on line 6 to bridge the gap | Instantly | Steve Woods |
| Production | Increased potential for RSIs online when applying dose 2A/B sachets | Y | All operators health is maintained whilst completing manual process | Yearly occupational health screenings provided by the company | Occupational health screenings | 28 | Yearly | Occupational health therapist | Increase frequency of rotation onto other stations of the process, remove operators more proned to issue from the line | Instantly | Steve Woods |
| Quality Control | PLENVU Dose 1 efficacy and homogeneity | Y | All batch release testing must pass | Batch release testing conducted on every batrch produced from line 6 prior to be released to the market | Batch release testing protocol | Inline with IPC per batch | Every batch produced | QC Analyst | Quaruntine batch and conduct RCA | Instantly | Bethan Gingell |
| GTM Process Experts | Line 6 Process Capability | Y | Line 6 Processs capability must not decrease after the change | Yearly process capability report | Minitat PP & PPK values | All batches produced in 2024 | Once per year | GTM Expert | Review Full process to identify the root cause | Instantly | Frances Morrisey |
| Validation | Validated settings | Y | Review validated settings on a 6 monthly basis | Norgine validation stratergy | Audit | 1 | 6 monthly | Validation specialist | Comduct review and understand why settings may have been changed | Instantly | Samuel Lane |
| Engineering | Equipment maintenance | Y | A review of the current maintenance strategy must be undertaken 6 months afte rthe change has been implemented to ensure all parts remain in good working order | Monthly PPMs | PPM schedules | 12 | Monthly | Maintenance engineer | Ammend PPM schedule to reflect change in equipment maintenance approach | Instantly | Steve Gregory |

## Appendix 22 – Project Management Gantt Chart