## Blank
Feature | Initial Estimate | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Hours Left
Lyrics | [9 empty] | 0
Melody | [9 empty] | 0
Bass | [9 empty] | 0
Drums | [9 empty] | 0
Settting | Start | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon
Planned Hours |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Hours |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining Effort | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal Burndown | 0 | 0 | 0 | 0 | 0 | 0

## Solution
Feature | Initial Estimate | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Hours Left
Lyrics | 40 | 8 | 8 | 8 | 8 | 4 | 2 | 1 | 1 | 0
Melody | 40 | 10 | 5 | 2 | 2 | 5 | 7 | 7 | 2 | 0
Bass | 30 | Tue: 6; Wed: 8; Thu: 8; Fri: 8 | 0
Drums | 10 | 2 | 2 | 3 |  |  | 1 | 2 |  | 0
Settting | Start | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon
Planned Hours |  | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24
Actual Hours |  | 20 | 21 | 21 | 18 | 17 | 10 | 10 | 3
Remaining Effort | 120 | 100 | 79 | 58 | 40 | 23 | 13 | 3 | 0
Ideal Burndown | 120 | 96 | 72 | 48 | 24 | 0