## Gantt example i1
Project to undertake a large scale staff development programme for e-Learning
Gantt Chart Plan of the Start-Up and Initiation of the Project | [9 empty] | Status key
= on target
|  | SMT |  |  | CPD Programme Leader / Team |  | Specialist Members of Team |  |  |  | = some issues but ok
= serious problems
Time | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | ..etc |  | ..Week n | Status
Task
Secure SMT Commitment
Identify Steering Group | [9 empty] | example (see key above)
Identify CPD Programme Leader
Evaluate Strategies
Identify Team
Identify link to strategy
Identify Goals and Objectives
External Liaison (RSC, Professional Bodies)
Identify Roles & Responsibilities
Formulate Communications Strategy
Promote across College
Risk Analysis
Decide reporting needs
ILT Skills Audit
Identify Scope
Secure Funding
Investigate, choose and customise staff development modules
Formulate implementation & delivery strategy
Identify accreditation route
Analyse IT resources
Commit/timetabling physical resources
Identify all stakeholders
Identify sources and nature of resistance
Produce project budget
Produce initiation document
Agree PID with SMT