Academic Essay

Newham Heritage Month 2023

Name: Pavel Lyubomirov Karadachki

Student ID: 1920456

Module: Community Engagement

Module Code: LCBB4002

Lecturer: Nadeem Mirza

Submitted on: 5th of August 2023

Table of Contents

1. Introduction	3

2. Overview of Newham Heritage Month	3

3. Planning Process	4

4. Stakeholders	5

5. Community Engagement	6

6. Goal and Potential Benefits	7

7. Approaches and Focus Arias	8

8. Lessons Learned	8

9. Conclusion	9

Reference List	10

# Introduction

This essay will provide an in-depth examination of the community engagement processes and standards implemented during the recently conducted festival Newham Heritage Month 2023, which was arranged by the Newham Council and financially supported by The National Lottery Heritage Fund and the Royal Docks Team (Royal Docks, n.d.). First, information about Newham Heritage Month and some of the events included in it will be provided to get a better understanding of the project. Next, an analysis of the planning process will be conducted by providing definitions and examining their practical application, followed by a comprehensive discussion of the festival’s stakeholders. Afterwards, the examination will continue by exploring the community engagement principles put into action by the Newham Council and the goals and potential benefits of the project. The essay will also discuss what community engagement approaches were adopted and identify in which areas they were most active and why and will finish with a review of the insights gained from the event, followed by a conclusion highlighting the most important information derived from this analysis.

# Overview of Newham Heritage Month

Newham Heritage Month, marking its fourth successive year, celebrated the rich cultural tapestry of the borough with its 2023 theme, "Our Creative Newham" (Royal Docks, n.d.; Stradford Original, n.d.). This vibrant festival, which took place throughout June, paid homage to the diverse artistic talents and historical legacies that have shaped the community into what it is today. The month-long event, organised by the Newham Council and local cultural partners, aimed to engage residents and visitors alike in an immersive journey through the borough's artistic heritage. Under the banner of "Our Creative Newham," the festival boasted a plethora of more than 50 free activities, all created by the community, ensuring there was something for everyone to enjoy (Newham London, 2023). From riveting live events that showcased the dynamic performing arts scene to thought-provoking film screenings that explored the borough's history through a creative lens, attendees were treated to an eclectic range of experiences (Newham Unlocked, 2023). The festival's exhibition spaces provided a visual feast where local artists proudly displayed their works, offering a unique glimpse into the artistry of Newham's talented community. Interactive workshops provided an opportunity for budding artists to hone their skills while engaging talks delved into the stories behind some of the borough's most iconic landmarks and hidden gems. The celebration didn't stop there, as guided tours guided curious participants through the streets, unearthing various neighbourhoods' history and cultural significance. This served as a reminder of Newham's strong identity, shaped by the contributions of individuals and communities from diverse backgrounds. Newham Heritage Month 2023 successfully fostered a sense of unity, pride, and appreciation for the borough's creative spirit. As the event came to a close, the impact of this celebration was felt throughout the community, leaving a lasting legacy of creativity, diversity, and inclusivity for years to come.

# Planning Process

“Planning is the fundamental management function, which involves deciding beforehand, what is to be done, when is it to be done, how it is to be done and who is going to do it” (Business Jargons, n.d.). It plays a pivotal role in the successful execution of projects or events, providing a systematic approach to achieving specific objectives. According to an article from Blackberry Productions (2014), in order to ensure success, planning is crucial as it encompasses all aspects of the event. Furthermore, a community engagement plan is a strategic guide for uniting leaders and community members around shared objectives, beginning with envisioned outcomes and outlining actions and interactions needed to achieve them within a set timeframe (Mighty, n.d.). Newham Heritage Month exemplified the significance of planning and community involvement in crafting a vibrant and meaningful celebration of the borough's creative heritage. On the second of November 2022, the Newham Heritage Month team announced the launch of community grants for the festival. Individuals and groups were offered up to £8,000, inviting them to be an integral part of this annual festival, both in-person and online, created by and for Newham's community (Newham Unlocked, 2022). The team also invited all community members to an Inspiration Day, which took place on the 12th of November 2022 at Stratford Library and presented an opportunity for them to meet the Newham Heritage Month team and discuss projects and ideas (Newham Unlocked, 2022). The meeting also gave them access to Newham’s Archives as a source of inspiration. Furthermore, an online event was held on the 16th of the same month, which aimed to support people who wanted to participate in the festival by offering them a step-by-step guide to the application process for funding (Eventbrite, 2022). Additionally, the Newham Heritage Month blog realised the article “Top tips: How to start your own heritage project” on the 1st of December 2022, aimed to encourage people to participate with their projects by sharing tips from five project creators from the previous festival (Newham Unlocked, 2022). These events brought together the festival's organisers and the local community, working together to plan the festival. Furthermore, the Newham Heritage Month team invited and encouraged all people of the borough with the help of meetings and articles to participate by offering funds, support and inspiration, thus creating a festival that left a lasting impact, honouring Newham's creative spirit and preserving its artistic legacy for generations to come.

# Stakeholders

A stakeholder is an individual, group, or entity that has a vested interest in the decision-making and operations of a business, organisation, or project, which may include both affiliated members and those without official ties, with the capacity to exert direct or indirect influence on these activities, and whose backing is frequently vital for the accomplishment of business and project goals (Barney, n.d.). In order words, a stakeholder is anybody that affects a business or a project: from investors, government entities, managers and employees to customers, community members, and suppliers. Newham Heritage Month 2023 brought together a diverse array of stakeholders, each playing a crucial role in shaping and enriching the vibrant cultural celebration. At the forefront stood the Newham Council, the orchestrator of the event, which held the responsibility of planning, coordination, and overall management. The Council's commitment to community engagement was evident in its collaboration with The National Lottery Heritage Fund and the Royal Docks Team, who provided financial support that underpinned the festival's realisation. Furthermore, Newham Heritage Month 2023 paid homage to twenty-four individuals and organisations who took a critical role in the success of the project (Newham Unlocked, n.d.). The community members who participated in the festival with their own events or as volunteers also can be considered stakeholders, as they had a huge impact on the realisation of Newham Heritage Month 2023. Their active participation and enthusiastic involvement breathed life into the event. Local artists, creators, and performers showcased their talents, contributing to the diverse array of more than 50 free activities that formed the festival's backbone. The attendees, including residents and visitors, formed an integral part of the stakeholder matrix. Their enthusiastic presence and engagement during the month-long festivities validated the event's success. Their interactions with the art installations, performances, workshops, and guided tours were a testament to the event's impact, promoting a sense of cultural appreciation and shared experience. In conclusion, the Newham Council, financial supporters, local artists, community members, attendees, community leaders, and organisers all intertwined to craft a vibrant celebration that not only honoured Newham's creative spirit but also fostered unity, pride, and cultural appreciation within the borough. The seamless interplay of these stakeholders exemplified the essence of community engagement and cultural celebration, leaving a legacy for Newham's present and future generations.

# Community Engagement

For a community engagement initiative to possess substantive significance and operational efficacy, adherence to specific principles and standards is imperative (Communities Scotland, n.d.). Fairness, inclusion, equality, and empowerment are a few of the principles which the standers are based upon (Communities Scotland, n.d.). Newham Heritage Month 2023 embraced a set of robust community engagement principles and standards to ensure an inclusive and collaborative approach to event planning. These principles prioritised active participation, transparency, and responsiveness. By launching community grants for individuals and groups, the event organisers empowered local residents to contribute their creative ideas and projects, fostering a sense of ownership and pride within the community. Through transparent communication channels like social media, their own webpage, podcasts and face-to-face meetings and accessible application processes for which the organisers offered support, Newham Heritage Month facilitated open dialogue, ensuring that diverse voices were heard and considered in the decision-making process. The standards set for engagement also aimed to create a safe and welcoming space, encouraging individuals from various backgrounds to share their perspectives and stories. This inclusive approach extended beyond traditional event planning, promoting partnerships with local organisations, artists, and cultural stakeholders. By adhering to these community engagement principles and standards, Newham Heritage Month 2023 cultivated a sense of unity and collaboration, ultimately enriching the celebration with a diverse range of perspectives and contributions from the vibrant Newham community.

# Goal and Potential Benefits

“Community engagement should have clear and agreed purposes” (Communities Scotland, n.d., p.5). The primary goal of Newham Heritage Month 2023 was well defined: to celebrate and honour the borough's rich cultural tapestry by engaging the community in a month-long festival of events, exhibitions, and activities. By showcasing Newham's diverse artistic heritage, the event aimed to foster a deeper sense of connection among residents. Additionally, Newham Heritage Month provided an opportunity for intergenerational learning, where younger generations could gain insight into the borough's history and traditions from their elders. Through increased community participation and collaboration, the event also aimed to stimulate local economic activity by attracting visitors and promoting local businesses. Moreover, the celebration sought to create a platform for emerging artists and cultural practitioners to showcase their talents and contribute to the artistic legacy of the borough. By achieving these goals, Newham Heritage Month 2023 had the potential to strengthen social cohesion, promote cultural appreciation, and enhance the overall quality of life for Newham's diverse population.

# Approaches and Focus Arias

Newham Heritage Month 2023 embraced a range of community engagement approaches and focused on key areas to ensure a meaningful and inclusive celebration. The event adopted proactive outreach initiatives, encouraging direct involvement from local residents through community grants and project submissions. The approach prioritised two-way communication, allowing community members to shape the event's direction actively. Additionally, Newham Heritage Month emphasised cultural diversity and inclusivity, focusing on amplifying marginalised voices and uncovering hidden stories that reflect the borough's multicultural identity. The celebration also fostered collaborations with local organisations, artists, and cultural stakeholders, nurturing partnerships that enriched the festival's content and impact. Through workshops, exhibitions, and live events, Newham Heritage Month 2023 encouraged intergenerational dialogue, enabling the transmission of cultural heritage and knowledge from one generation to the next. By adopting these multifaceted community engagement approaches and focusing on diverse cultural aspects, the event aimed to create a participatory and enlightening experience that resonated deeply with the Newham community.

# Lessons Learned

Newham Heritage Month 2023 yielded valuable lessons that underscored the significance of community engagement and cultural celebration. The event demonstrated that when communities are actively involved in shaping and participating in festivities, a sense of shared ownership and pride is fostered, resulting in a more authentic and impactful celebration. The festival highlighted the importance of uncovering lesser-known narratives and hidden stories, enriching the understanding of local history and cultural diversity. Moreover, the success of Newham Heritage Month reaffirmed that partnerships with local organisations and stakeholders are vital for creating a comprehensive and inclusive event that resonates with a wide range of community members. The intergenerational dialogue facilitated by the event emphasised the importance of preserving and passing down cultural traditions and heritage to younger generations. Overall, Newham Heritage Month 2023 illuminated the transformative power of community-driven celebrations in strengthening social bonds, promoting cultural appreciation, and enhancing the collective identity of the borough.

# 9. Conclusion

In conclusion, Newham Heritage Month 2023 provided a rich tapestry of insights into effective community engagement processes and cultural celebrations. The event demonstrated that planning and community involvement are integral to successful projects, offering a systematic approach to achieving specific goals. Through the collaborative efforts of various stakeholders, including the Newham Council, financial supporters, local artists, community members, and attendees, the festival seamlessly interwove diverse perspectives to craft a vibrant celebration honouring Newham's creative spirit. By adhering to robust community engagement principles and standards, the event fostered inclusivity, transparency, and collaboration, enriching the celebration with many voices and contributions. The festival's primary goal was to celebrate and connect the community with Newham's cultural heritage, thereby fostering unity and intergenerational learning. Lessons learned from Newham Heritage Month 2023 underscored the transformative potential of community-driven celebrations in strengthening social bonds, promoting cultural appreciation, and preserving the borough's artistic legacy. As Newham Heritage Month ended, its impact reverberated throughout the community, leaving a lasting legacy of creativity, diversity, and unity for generations to come. This comprehensive analysis provides a profound understanding of the community engagement processes and standards that drove the success of Newham Heritage Month 2023 and sheds light on the powerful connection between cultural celebration and community engagement.

# Reference List

Barney N. (no date) Stakeholder. Available at: https://www.techtarget.com/searchcio/definition/stakeholder#:~:text=A%20stakeholder%20is%20a%20person,a%20business%2C%20organization%20or%20project. (Accessed: 05 August 2023).

Blackberry Productions (2014) Why event planning is so important. Available at: https://www.blackberryproductions.co.uk/why-event-planning-is-so-important/ (Accessed: 05 August 2023).

Business Jargons (no date) Planning. Available at: https://businessjargons.com/planning.html (Accessed: 05 August 2023).

Community Scotland (no date) National Standards for Community Engagement. Available at: https://www.communityplanningtoolkit.org/sites/default/files/EngagementR5.pdf (Accessed: 05 August 2023).

Eventbrite (2022) Newham Heritage Month 2023 Community Grant Surgery. Available at: https://www.eventbrite.co.uk/e/newham-heritage-month-2023-community-grant-surgery-tickets-435688334537 (Accessed: 05 August 2023).

Mighty (no date) What is a community engagement plan? Available at: https://www.mightynetworks.com/encyclopedia/community-engagement-plan (Accessed: 05 August 2023).

Newham Unlocked (no date) Contributors. Available at: https://www.newhamheritagemonth.org/contributors/?festival-year=2023 (Accessed: 05 August 2023).

Newham Unlocked (2023) Explore Newham's Rich Local Heritage. Available at: https://www.newhamheritagemonth.orgx (Accessed: 05 August 2023).

Newham Unlocked (2022) Newham Heritage Month 2023 Lunch. Available at: https://www.newhamheritagemonth.org/blog/newham-heritage-month-2023-launch/ (Accessed: 05 August 2023).

Newham Unlocked (2022) Top tips: how to start your own heritage project. Available at: https://www.newhamheritagemonth.org/blog/top-tips-how-to-start-your-own-heritage-project/?fbclid=IwAR3KthZ3CHPhINH3qOyF1mTHoXg3lsonbSAO8XL5R3gX7YjOHop9h9zBSms (Accessed: 05 August 2023).

Royal Docks (no date) Newham Heritage Month 2023. Available at: https://www.royaldocks.london/whats-on/newham-heritage-month-2023 (Accessed: 05 August 23).

Stratford Original (no date) Newham Heritage Month. Available at: https://stratfordoriginal.com/whatson-all/newham-heritage-month (Accessed: 05 August 2023).