# Report

# Spirit of Croeso 2025: A Festival of Welsh Culture and Nature

Module: International Meetings Management

Module code: BMIH6007

Lecturer name: Kathryn Roberts

Student name: Petre Chiriac

Student ID: 2246594

I acknowledge the use of Grammarly (https://www.grammarly.com/) on 11 June 2025 to check my work using the prompt(s):

- Please check the following text for readability, grammar and syntax.

I confirm that I have not presented any AI generated text as my own work. I confirm I have copies of my drafts, notes, and other resources I used before, and after the use of AI tools which I may be asked to provide in evidence.

Table of Contents

Introduction	4

The Event Cycle	5

Event Concept	7

Aim and Objectives	9

Event Management	11

Event Budget	13

Industry Trends, Issues, and Impacts	14

Situational and Cultural Considerations	16

Conclusion	17

Recommendations	18

References	19

# Introduction

“Spirit of Croeso 2025: ‘A Festival of Welsh Culture and Nature” is a three-day international event which was thought up during the ‘Year of Croeso' campaign of Visit Wales. Expanding from the feasibility analysis that you presented in your initial presentation, this report refocuses attention away from feasibility but onto strategic planning and acute delivery concerns. The festival is structured to represent Wales’ cultural background, beautiful environments, and various sustainable tourism practices to a select spectatorship of foreign tour operators, tour bloggers, and eco-travel companies. Aberystwyth, situated on Cardigan Bay and surrounded by the Cambrian Mountains, provides the perfect mixture of scenic coastline, past historic railways, and a bustling university, thus being equally logistically practical and attractive.

Figure 1: Croeso campaign

(Source: Wales, 2025, https://www.wales.com/)

The event is selected to capitalise on “Year of Croeso” - a year-long campaign promoting the Welsh language, hospitality, and sustainable care of Wales. Combining the existing event management theory and practicalities, for example, alignment of stakeholders, resource distribution, and risk management, this document is a roadmap towards delivering Spirit of Croeso 2025 for effective maximisation of its long-term impact on Wales’ international tourism profile.

# The Event Cycle

Event Cycle is one of the key frameworks in event management, with an elaboration of stages an event encounters on the way from its conception to post-event evaluation. Outlines five key phases: research, design and planning, coordination, and evaluation. Invoking this model on Spirit of Croeso 2025 assures systematic practices that cater for both theoretical intensity and practical exigencies.

In the research phase, the factual data from global ecotourism trends and from the statistics of Wales’ tourism were analysed. Quantitative measures like the continuous annual growth in experiential travel supported the strategic organisational fit of an eco-culture festival. Qualitative interviews with the representatives of Visit Wales and local council officers provided for stakeholders’ buy-in and identified community concerns in terms of environmental impact and cultural authenticity (Lara-Morales and Clarke, 2024).

In design, the experience itinerary of the event was developed, which balances cultural immersion and sustainability principles. Based on the authors’ “Experience Economy” theory, the structure of each activity, coastal foraging walks, and bilingual storytelling, was designed to involve the delegates intellectually, emotionally, and socially (Morris, 2024). At this point, the main performance indicators were established; they are referred to as Key Performance Indicators (KPIs). Delegate satisfaction, media reach, partnership agreement secured, and carbon‐offset metrics.

In coordination, the cross‐functional teams under the guidance of a professional event manager perform the operational plan. Coordination tools are daily huddles, digital project management platforms, and on-site command centres. The regular stakeholder briefings keep up to date with Visit Wales’s strategic goals; meanwhile, volunteers receive training in cultural interpretation and first aid for the well‐being of the delegates (Bowdin et al., 2023).

Finally, evaluation is both a summative and formative assessment. Summative evaluation is done through delegate surveys, media analysis, and financial reconciliation immediately post‐event. Formative evaluation will also be carried out throughout the following quarter by longitudinal monitoring of tour operator bookings associated with the festival and social media sentiment analysis. An evaluation report guides the future editions and conforms to an ethos of continuous improvement (Ruben, 2023).

# Event Concept

Below is the Event Concept presented as a three-day itinerary in table format:

| Day | Time | Activity | Description |
| --- | --- | --- | --- |
| Day 1 | Morning | Welcome Ceremony & Coastal Walk | Opening address by Visit Wales, followed by a guided walk along the Ceredigion Coast Path |
|  | Midday | Local Lunch | Lunch using locally sourced produce; opportunity to mingle with guides and Visit Wales ambassadors. |
|  | Afternoon | Vale of Rheidol Heritage Railway | Scenic steam-train journey through Cambrian woodlands to Devil’s Bridge |
|  | Early Evening | Welsh Cooking Masterclass | Hands-on preparation of traditional dishes (cawl, bara brith) |
|  | Evening | Food Tasting & Networking | Tasting session paired with local ciders; informal networking |
| Day 2 | Morning | Bilingual Storytelling Workshop | Interactive session in Welsh and English featuring Mabinogion legends |
|  | Late Morning | Artisan Craft Demonstrations | Live weaving (tapestry) and pottery workshops with local artisans |
|  | Afternoon | “Community Croeso” Village Visit | Guided tour of rural homestay operation; tea with hosts and discussion of community hospitality |
|  | Evening | Welsh Music & Folklore Concert | Live performance blending traditional harp, fiddle, and contemporary folk songs |
| Day 3 | Morning | “Green Hospitality” Panel | Industry panel on sustainable accommodation and eco-certification |
|  | Midday | Foraging Walk & Sustainability Workshop | Expert-led walk identifying native edible plants + best practices for integrating them into menus. |
|  | Afternoon | Eco-Accommodation Site Visit | Tour of local eco-lodges; Q&A with owners on green operations |
|  | Evening | Closing Banquet & Award Ceremony | Celebration dinner featuring seasonal produce and delegate awards, followed by farewell remarks |

# Aim and Objectives

Aim

To boost the global tourism brand of Wales by creating a strategically designed festival, which will immerse the international delegates in Welsh culture and eco-tourism, thereby guaranteeing sustainable partnerships and a visible rise in sustainable holiday bookings (Ruhanen, Whitford, and Lane, 2019).

Objectives

| Objective | Specific | Measurable | Achievable | Relevant | Time-bound |
| --- | --- | --- | --- | --- | --- |
| 1. Engage 60 international delegates, including at least 20 key tour-operator decision-makers and 10 travel influencers, by July 2025 | Targets distinct delegate groups (tour operators, influencers) | Delegate registration numbers are tracked through the event CMS | Capacity and marketing plan calibrated to reach 60 within budget | Supports Visit Wales’ goal of building B2B partnerships | Registration closes on 31 July 2025 |
| 2. Secure a minimum of £30,000 in sponsorship and in-kind support from Welsh tourism stakeholders by four weeks prior to the event | Specifies the financial target and stakeholder segment | Sponsorship agreements and in-kind valuations are recorded in the finance ledger | Based on initial sponsor interest and Visit Wales endorsements | Offsets cost and deepens local stakeholder engagement | All funds committed by 14 June 2025 |
| 3. Achieve at least an 85% delegate satisfaction rate according to post-event surveys | Focuses on the overall delegate experience | Satisfaction measured via Likert scales in digital surveys; results tabulated | Balanced itinerary and service standards designed to deliver high satisfaction | Ensures quality delivery and positive word-of-mouth | Survey data collected and analyzed by 24 July 2025 |
| 4. Generate at least 50 unique media outputs (blogs, social posts, press features) within 30 days following the festival | Defines types of media and minimum volume | Tracked via media-monitoring tools (e.g., Meltwater) | Influencer partnerships and press outreach plan calibrated to meet targets | Enhances Wales’ tourism visibility and ROI on marketing | Media outputs counted through 12 August 2025 |

These are well coordinated with Visit Wales’ strategic priorities and best practices in the evaluation of events, which brings clarity in performance measurement, especially to the organisers of events (Evans, 2024).

# Event Management

The provision of Spirit of Croeso 2025 requires a cross-disciplinary management system, concentrating on operating and planning as well as marketing capabilities:

Operational Management

With a lead event manager in charge, venue logistics such as liaison with Aberystwyth University, Ceredigion Coast Path authorities, and local village councils are organised (Andrews, 2021). Such accessibility provisions as (for example) wheelchair-friendly transport and multilingual signage are the guarantees of inclusive general participation.

Planning Management

A key planning team made up of the event manager, logistics coordinator, and finance officer uses the PRINCE2 methodologies to maintain baseline controls and stage gates as well as have risk registers (Hartley, 2020). Progress of work against the Gantt chart is monitored in weekly planning sprints, while stakeholder liaison officers ensure open communication channels with Visit Wales and sponsors, as well as the community partners. The mitigation of such obstacles as weather and transport issues is accomplished through the utilisation of contingency plans (e.g., alternative indoor venues, charter bus backups).

Marketing Management

The marketing lead comes up with a three-phase promotional campaign. Phase one targets B2B channels: participation in trade shows, e.g., ITB Berlin, and personalised outreach to specific tour operators. Personalised delegate communications, pre-travel preparation email, and virtual welcome session. Real-time analytics dashboards monitor website traffic, click-through rates, and registration conversions and allow dynamic optimisation (Phatak et al., 2020).

Human resource needs are 20 trained local volunteers mobilised through Aberystwyth University’s student body for in-situ support, as well as a multicultural facilitation team for bilingual interpretation. Technical resources include storytelling workshops’ audiovisual equipment and live-stream abilities for remote stakeholders (Huggett, 2024).

# Event Budget

A strong multi-stream budget plan is financial sustainability with the provision of strategic investments (Manescu, 2024).

Income Sources:

- Visit Wales Grant: £ 30,000 (secured from a formal application in line with the “Year of Croeso” objective).

- Delegate Fees (60 x £250): £15,000 (tiered pricing structure: full access and meals).

- Sponsorship & In-Kind Support: £15,000 (three core sponsors giving cash pledges and product contributions).

Total Projected Income: £60,000

Expenditure Breakdown:

- Venue Hire & Equipment: Conference centre, village halls, AV gear – £ 8.5 K.

- Catering & Hospitality: £9,000 (local buying for menus, materials for a workshop on foraging).

- Transport & Logistics: Heritage rail charters, shuttle buses, contingency vehicles – £7,000.

- Marketing & PR: £7,500 (participation in trade shows, digital campaigns, fees to influencers).

- Staffing & Volunteer Support: £6,000 (training sessions, uniforms, stipends).

- Insurance & Licences: 8,500 (public liability, event permits, music rights).

- Guest Speakers & Entertainment: £7,000 (cultural facilitators, musicians, chefs).

- Accommodation Subsidies: £8,000 (negotiated discounted block-bookings at eco-lodges).

- Contingency (10%): £6,000

Total Projected Expenditure: £62,500

A trivial shortage of £2,500 shall be compensated through late sponsorship top-ups and an early-bird registration levy. The “zero-based” principle is followed as each cost item is justified in reference to event objectives, diversifying ways of earning to reduce financial risk. Quarterly budget reviews shall apply actuals against forecasts, hence making corrective measures possible (Dakurah, 2020).

# Industry Trends, Issues, and Impacts

A number of macro-trends and new issues within the meetings and events industry explicitly inform the strategic design of Spirit of Croeso 2025.

Sustainability and Carbon Accountability

Environmental responsibility has gone from a niche to a mainstream, and delegates are already calling for low-carbon credentials and open declaration (Shrivastava and Bhusan, 2023). The green panel of the festival, the zero-waste policies, and the cooperation with the local carbon-offset project contribute to the fact that the event is a leader in the sphere of sustainable meetings.

Experience-Driven Travel

Contemporary travellers want to achieve an authentic and transformative experience, and not passive consumption. By combining hands-on workshops, storytelling, and homestays, Spirit of Croeso belongs to the experience economy model, offering lasting emotional and educational value (LOZA, and BERMANTO, 2025).

Digital Integration and Hybrid Formats

Post-pandemic event design combines more and more digital and hybrid characteristics (Chodor, 2020). Although Spirit of Croeso focuses on direct immersion, additional live streams of keynote events and a digital library of content enable a worldwide scope of impact with a longer lifespan. In real-time engagement metrics (social media sentiment, live polling), we hear on-the-fly changes.

Health and Safety Regulations

Ongoing changes in public health recommendations require strong hygiene practices, in particular in close-contact workshops. The strategic choice to hold the majority of outdoor activities, to keep the small number of participants, and to require contactless cheques-means it is risk-averse but welcoming (Basseal, Westerway, and McAuley, 2020).

Economic Volatility

It is subject to inflationary pressures and fluctuations in exchange rates when it comes to delegating travel budgets. Advanced sales in the form of early-bird rates and group discounts, coupled with lenient cancellation policies, serve as a buffer against economic uncertainty, as well as drive maximum levels of delegate commitment.

Through its systematic incorporation of these industry imperatives of event design, the Spirit of Croeso programme both differentiates for competitiveness and builds operational resilience (Beckett, 2023).

# Situational and Cultural Considerations

PESTEL analysis describes the external context that affects Spirit of Croeso 2025.

- Political: The Welsh Government’s tourism plan for 2025 clearly supports the “Year of Croeso”, offering grants and marketing support. Nevertheless, after the Brexit visa rules for EU delegates, with talks about the UK travel regulations, the event team will need to be actively informative and helpful (Hall, 2020).

- Economic: With the cost of hospitality going up by a predicted 6% year on year, lean budgeting and the support for local sourcing help mitigate price fluctuation. The festival’s economic effect radiates locally with microenterprise cooperations such as homestays, artisans, and caterers, tripling regional earnings.

- Social: Interest in the minority languages and revival movements in culture is a growing concern at the global level (De Varennes, 2021). The bilingual nature of storytelling workshops and promotional materials emphasises social inclusion and makes Wales a model for cultural stewardship.

- Technological: Mobile-first registration platforms and event apps simplify the management of delegates. Utilisation of augmented reality features like an AR coastal biodiversity guide could also improve engagement, subject to feasibility studies.

- Environmental: The “clean and green” image of Wales is supported by zero-waste procedures, digital documentation, and eco-transport decisions (McLaughlin, 2021). Environmental Impact Assessments inform where to send foraging walks to minimise ecological damage.

- Legal: The processing of delegated information is based on compliance with the data protection legislation (GDPR). Advanced licences have been taken for public concerts, food service, and rail charters, with legal advisors to review each contract to minimise liability.

Cultural considerations extend beyond logistics. Considering local community views, the organisation of the event involves true partnerships with Welsh language activists and environmental NGOs to make sure that the narrative of “welcome” is genuine and mutually beneficial (Matras, 2024).

# Conclusion

This strategic report has identified the key planning and delivery considerations that would serve to turn Spirit of Croeso 2025 from an adequate proposition to a best-in-class cultural and eco-tourism event. Following the use of the Event Cycle framework, integrating sustainability and digital trends, and careful PESTEL analysis, the planning process ensures alignment with Visit Wales’ goals and the best practices in the industry.

Comprehensive admixture of immersive cultural interaction, best-practice sustainability implementation, and stringent money management will bring Wales’ tourism brand to the world stage, dancing into 2025 in the form of Spirit of Croeso 2025. Ongoing assessment, quantitative and qualitative in nature, will support future renditions so that the soul of Welsh hospitality lives on once the delegates are back home. After all, this event not only celebrates the “Year of Croeso” but also draws a sustainable direction for Wales in the international gatherings and conferences, which it is filled with cultural riches.

Moreover, Spirit of Croeso 2025 will facilitate the partnership between the public, private, and community stakeholders that will lead to sustainable economic uplift through the county of Ceredigion. Digital content library and post-event toolkit development will help Visit Wales and partners expand this festival’s influence and stimulate practice in other areas. The event makes a sustainable legacy of increased skills and stakeholder networks through its investment in capacity building in SMEs and volunteer training programmes. This long-lasting impact confirms Wales as the front-runner when it comes to sustainable, culturally authentic event delivery.

# Recommendations

Maximising Spirit of Croeso 2025’s lasting effects suggests that Visit Wales work with its partners to create a festival that recurs yearly or every two years, to ensure the event becomes better recognised by people from different countries (Allen, Harris, and Jago, 2022). Improve digital methods for museums, with interactive apps and virtual tours, to help more people visit and feel included. Seeking relationships with sustainable tourism platforms can help the destination stay visible at all times. Also, reaching out to event participants and promoting events together on branded materials can help turn enthusiasm into actual guests. Certifying and organising workshops for volunteers helps to benefit and empower our local communities. In addition, setting up a clear and honest way to measure carbon impacts will improve Wales’ reputation for sustainable events worldwide. Because of this, Spirit of Croeso will stand out among places that promote their unique, green features to both Welsh and international visitors (Hestler, Spilling, and Scirri, 2020).

# References

Allen, J., Harris, R. and Jago, L., (2022). Festival & special event management. John Wiley & Sons.

Andrews, G., (2021). Smooth Operator: The Life and Times of Cyril Lakin, Editor, Broadcaster and Politician. Parthian Books.

Basseal, J.M., Westerway, S.C. and McAuley, T., (2020). COVID‐19: infection prevention and control guidance for all ultrasound practitioners. Australasian journal of ultrasound in medicine, 23(2), pp.90-95.

Beckett, L., (2023). Child Poverty in Wales: Exploring the Challenges for Schooling Future Generations. University of Wales Press.

Bowdin, G.A., Allen, J., Harris, R., Jago, L., O'toole, W. and McDonnell, I., (2023). Events management. Routledge.

Chodor, B., (2020). Transitioning to virtual and hybrid events: How to create, adapt, and market an engaging online experience. John Wiley & Sons.

Dakurah, A.A., (2020). Assessing budgeting and budgetary control effectiveness of Credit Unions in the Upper West Region of Ghana. Research Journal of Finance and Accounting, 11(12), p.1.

De Varennes, F., (2021). Language, minorities and human rights (Vol. 45). Brill.

Evans, N.G., (2024). Strategic management for tourism, hospitality and events. Routledge.

Hall, D., (2020). Brexit and tourism: Process, impacts and non-policy (Vol. 86). Channel View Publications.

Hartley, S., (2020). Project Management: A practical guide to planning and managing projects. Routledge.

Hestler, A., Spilling, J.A. and Scirri, K., (2020). Wales. Cavendish Square Publishing, LLC.

Huggett, C., (2024). The virtual training guidebook: How to design, deliver, and implement live online learning. American Society for Training and Development.

Lara-Morales, O. and Clarke, A., (2024). Sustainable tourism value chain analysis as a tool to evaluate tourism's contribution to the sustainable development goals and local Indigenous communities. Journal of Ecotourism, 23(2), pp.129-147.

LOZA, V.W. and BERMANTO, B., (2025). PROPOSED MARKETING STRATEGY TO INCREASE BRAND AWARENESS OF HOMESTAY (CASE STUDY OF.

Manescu, C.B., (2024). The Planning of Public Investments in EU Member States: Long-Term Strategy, Selection and Budgeting Issues (No. 213). Directorate General Economic and Financial Affairs (DG ECFIN), European Commission.

Matras, Y., (2024). Speech and the city: Multilingualism, decoloniality and the civic university. Cambridge University Press.

McLaughlin, J., (2021). This information is available free of charge in electronic, audio, Braille and large print versions on request. For assistance in understanding or reading this document or specific information about this Agenda. INDICATORS, 22.

Morris, M., (2024). Tribal: How the cultural instincts that divide us can help bring us together. Penguin.

Phatak, M., Saxena, A., Singh, P.Y. and Singh, S., (2020). MARKETING AUTOMATION BY GROWTH HACKING [online]

Ruben, B.D., (2023). Excellence in higher education Guide: a framework for the design, assessment, and continuing improvement of institutions, departments, and programs. Routledge.

Ruhanen, L., Whitford, M. and Lane, B. eds., (2019). Sustainable tourism and indigenous peoples. London: Routledge.

Shrivastava, A. and Bhusan, A., (2023). Sustainable Boardrooms.