LEVEL 7 ASSESSMENT SPECIFICATION

| Student name: | Choi Wing Mui, Angel | Student ID number: | 2019403 |
| --- | --- | --- | --- |
| Programme: | MBA |  |  |
| Module: | Leading and Managing Projects |  |  |
| Module code: | HKBM7010 | ## Contribution to Overall Module Assessment (%): | 20% |
| Lecturer: | Dr. Joe Leung | Internal Verifier: | Dr. Poon Che Cheong |
| Assignment Title: | Assignment 1 - Project Initiation Document (PID) | Word count (or equivalent): | 1,000 words (PID) |
| Submission deadline: | 15 March 2021 | Return date of provisional marks & written feedback: | 6 April 2021 |

Table of Contents

|  |  |  |  | Page |
| --- | --- | --- | --- | --- |
| 1 | Introduction |  |  | 3 |
| 2 | Company Background |  |  | 3 |
| 3 | Project Idea |  |  | 4 |
| 4 | Project Aim and Objectives |  |  | 6 |
| 5 | Project Deliverables and Scope |  |  | 6 |
| 6. | Research Method and Work Plan |  |  | 7 |
| References. | 8 |

1	Introduction

As a consultancy firm specializing in reviewing business challenges and opportunities, we have pulled together a Project Initiation Document (PID) for Li & Fung (LF).  This document aims at evaluating LF’s company background, project idea of the problems identified, aim & objectives, deliverables & scope of the project and research method & work plan.

2	Company background

This section is to illustrate the company background of Li & Fung (LF) with its history, key milestones, business model and product portfolio.

LF was founded in 1906 by Fung Pak Liu, an English Teacher and Li To Ming, a merchant, to start the Trading and Export business to the West.  This two-person start up the business originally focusing on trading porcelain and silk from China, then exploring into bamboo, rattan ware, jade and handicrafts to the Western countries.  With the civil war in China, Fung Hon Chu, grandfather of the current CEO (Spencer Fung), moved from China to Hong Kong and set up LF’s first overseas branch in Central with 12 persons (Li & Fung Limited, 2021).

Now, LF operates with more than 230 offices and distribution centers across 40 markets (mainly Europe, US, and Asia) with over 15,000 employees (Li & Fung Limited, 2021).

LF is a Trading Agency model specializing in providing design and end-to-end sourcing & supply chain solutions for its customers mainly retailers and department stores in the world.  It consists of three parts of business namely supply chain solution (trading), logistics and onshore wholesale business.  It went through some key milestones as one of the biggest public listed company in the trading & distribution industry in Hong Kong and now become a privatized company starting in Mar 2020. Its product portfolio includes soft goods (garments and textiles) and hard goods (furniture, home decorations, beauty, toys, electrical and consumer products).

Belavina and Girotra (2012) said LF is a well-known sourcing intermediary which offers end-to-end sourcing solutions and supply chain management to key brands and retailers such as Walmart, Target, Zara and Levis.  They are best known for sourcing cost competitive products of garments and home consumer products with nearly 15,000 suppliers to their thousands of buyers across North America, Europe and Asia.

3	Project Idea

This project aims at reviewing on why LF, such a leading trading company, has been through their business downturn year on year and then provide resolutions to overcome the problems.

For the past twenty years, LF as an agency has been negotiating with suppliers to make close to zero profit margin.  As margins dropped to zero, suppliers are not willing to commit to LF’s business.  With the competition on fast-fashion retailers like Zara, H&M and Uniqlo, they are emphasizing on quick lead time over just squeezing on profit margins and directly sourcing with factories which causes LF’s business significantly decline (Kaiser and Sheng, 2014).

Also, LF’s customer bankruptcies have also been affecting the scores of LF with the increase competition of Amazon’s e-market share.  LF has been through major restructuring to embrace the digitalization with $150 million investment and to privatize its sweaters, cosmetic and furniture business in a sale to the Fung Group and Hony Capital in order to overcome the challenges facing (Ap, 2020).

According to Li & Fung’s Annual Reports (2015-2019), LF’s sales turnover and margin have decreased year on year significantly in the last five consecutive years which has raised an alarm for problem evaluation.

Table 1 shows Supply Chain Solutions Business Results:

| Year of Annual Report | Sales Turnover US$ million | Profit Margin US$ million | Geographical Market Turnover US$m (%) |
| --- | --- | --- | --- |
| 2015 | $17,907 (-2.8%) | $1,909 (-4.7%) | US (62%), EU (17%), Asia (15%) & Rest of World (6%) |
| 2016 | $15,857 (-1.4%) | $1,650 (-3.5%) | US (64%), EU (17%), Asia, (12%) & Rest of World (7%) |
| 2017 | $10,989 (-6.2%) | $733 (-5.5%) | US ($8,373, 76%), EU ($1,357, 12%), Asia ($440, 4%) & Rest of World ($818, 8%) |
| 2018 | $9,933 (-9.6%) | $647 (-11.8%) | US ($7,776, 78%), EU ($1,151, 12%), Asia ($242, 2%) & Rest of World ($764, 8%) |
| 2019 | $8,834 (-11.1%) | $534 (-17.5%) | US ($6,861, 78%), EU ($1,212, 14%), Asia ($131, 1%) & Rest of World ($630, 7%) |

Source: Li & Fung Limited, Annual Reports (2015, 2016, 2017, 2018 & 2019)

4	Project Aim and Objectives

The aim is to evaluate on the key problems of the business strategies of LF and suggest resolutions for optimizing the business strategy direction in short run and long run.

The objectives are to review on three areas:

First, Trading Network Geographical Market - Customer Base Analysis:  review on the current customer geographic splits and their sales turnover contributed to the company respectively and how to increase the sales turnover by geographic customers diversification with short-term, medium term and long-term plans.

Second, Business Model Review:  review on the business model as an intermediary agency and its business model optimization going forward.

Third, Supply Chain Management: focus on the SWOT analysis to review on the current strengths and weaknesses and thus suggest opportunities for future growth.

5	Project Deliverables and Scope

This is to evaluate on the problems identified for LF and to provide solutions and recommendations for problem solving in the full consultancy report to let LF’s management team understand the strategy direction change to be less reliance on US and European customers like Walmart but to review the opportunities on the customers geographic diversification.

The scope is to focus on LF’s supply chain solutions (trading) business. The logistics and onshore wholesale business are excluded in the scope of project.

6	Research Method and Work Plan

This project is based on using the method of literature review, LF’s website & annual reports and government & international statistics reports. To facilitate, SWOT analysis is to be used to review on the internal strengths, weaknesses, opportunities and threats.  PESTEL analysis is to be applied to evaluate on the macro external factors. Finally, Boston Consulting Group (BCG) Matrix is to be used to analyze on the development lifecycle.

The Work Plan is as below:

| Date | Event |
| --- | --- |
| 21/02/2021 | Project Initiation Document (PID) - LF starts |
| 27/02/2021 | LF’s website and annual reports review and literature review |
| 06/03/2021 | Review on SWOT, PASTEL and BCG Models |
| 13/03/2021 | Writing of PID - LF |
| 15/03/2021 | Delivery of PID – LF |
| 20/03/2021 | Document & literature review to come up with analysis & solution plan for LF |
| 27/03/2021 | Writing of Consultancy Report - LF |
| 12/04/2021 | Delivery of Consultancy Report – LF |

References

Aguilar, F.J. (1967) ‘Scanning the Business Environment’, Macmillan.

Anthony, S. (2016) ‘Kodak’s Downfall Wasn’t About Technology’, Harvard Business Review.

Ap, T. (2020) ‘Supply Chain Giant Li & Fung to Privatize’, Women’s Wear Daily.

Belavina, E. and Girotra, K. (2012) ‘The Relational Advantages of Intermediation’, Management Science, 58(9), pp.1614–1631.

Cheng, Z. (2019) ‘Li & Fung Sees Silver Lining in Trade War’, Women’s Wear Daily.

Doz, Y. and Wilson, K. (2018) ‘Why Successful Companies Usually Fail?’, Insead.

Gong, A. (2016) ‘Li & Fung Sets up $2 Billion Securities Programme’, Global Capital.

Huang, A. (2020) ‘Li & Fung Makes Quick Return with $100 Million Tap’, Global Capital.

Huang, A. (2020) ‘Li & Fung Uses Coupon Step-up to Tackle Downgrade Risks’, Global Capital.

Humphrey, A. (2005) ‘SWOT Analysis for Management Consulting’, SRI Alumni Newsletter, SRI International.

Kaiser, A. and Sheng, E. (2014) ‘Li & Fung Defends “Middleman” Model’, Women’ s Wear Daily, 207(55).

Li & Fung Limited (2021) Creating the Supply Chain of the Future. Available at: http://lifung.com (Accessed: 9th March 2021).

Li & Fung Limited (2015) Annual Report. 2015. Available at: http://lifung.com/investors/annual-reports (Accessed: 9th March 2021).

Li & Fung Limited (2016) Annual Report. 2016. Available at: http://lifung.com/investors/annual-reports (Accessed: 9th March 2021).

Li & Fung Limited (2017) Annual Report. 2017. Available at: http://lifung.com/investors/annual-reports (Accessed: 9th March 2021).

Li & Fung Limited (2018) Annual Report. 2018. Available at: http://lifung.com/investors/annual-reports (Accessed: 9th March 2021).

Li & Fung Limited (2019) Annual Report. 2019. Available at: http://lifung.com/investors/annual-reports (Accessed: 9th March 2021).

Morgan, D. (2019) ‘Hong Kong’s Li & Fung grabs $100 million from tap’, Global Capital.

Robson, D. (2019) ‘The bias that can cause catastrophe’, BBC Capital.

Stern, C.W. and Stalk, G. (1998) ‘Perspectives on strategy from the Boston Consulting Group’, John Wiley & Sons:

Sull, D.N. (2005) ‘Why good companies go bad’, Financial Times.

Zaczkiewicz, A. (2019) ‘Li & Fung and First Insight Team Up’, Women’s Wear Daily.

Zhang, T. (2019) ‘Li & Fung Turnover Drops’, Women’s Wear Daily.