A MODULE NAME: MANAGEMENT PROJECT IN

THE ORGANIZATION

BMSW 5104

LERNER: ADEREMI OJEBOD

STUDENT: MARIA CIORASCU (2121406)

Project management Plan for Opening Birmingham

Blossomkids Nursery

# Abstract

The Blooming Kids Nursery project design in Birmingham (United Kingdom), is a plan build on evidence, research made in the Birmingham, area, on internet and various sources of Information. The project seeks to support families and cater to the requirements of young children. Personnel, teaching, registrations, capacity, financial sustainability, and community participation are the main priorities of the design. It tackles important problems including balancing work and family life, finding inexpensive daycare options, and increasing demand. The aim of this project is to establish a high-quality educational facility that caters to the needs of young children Galloway (2018) and supports and overall development. The Nursery Bloomskids Plan is based on Increased Demand of Children Care Addressing Crucial Needs, which made me to going ahead with the project.

Table of content

Abstract...............................................................................................................1

Introduction.........................................................................................................3

Project description and Market Evaluation …................................................... 3

Objectives...........................................................................................................4

Goals …..............................................................................................................4

Project Scope …............................................................................................  4/5

In Scope................................................................................................5/6

Outside of Scope..................................................................................6/7

Market gaps........................................................................................................7

The problems aim to solve.................................................................................8

Business Model ….............................................................................................8

Work breakdown structure............................................................................ 9/10

Stakeholders ….................................................................................................11

Competitors …..................................................................................................11

Organizations and Individuals affected by Nurseries.......................................11

Quad chart …....................................................................................................12

Birmingham Blossom Kids Nursery Gannt Chart …..................................12/13

Financial Projection ….....................................................................................13

Critical Path Activities ….................................................................................14

Resurce Management …..............................................................................14/15

Project Success Criteria.....................................................................................15

Conclusion...................................................................................................15/16

References........................................................................................................17

Introduction

# Opening a nursery in the United Kingdom requires a thorough understanding of the institutional, organizational, managerial, and legal aspects involved. This analysis aims to provide a comprehensive overview of these key areas, highlighting the requirements, challenges, and opportunities associated with such a project. Doing a comprehensive market analysis is necessary to ensure the nursery's success. Important details regarding the demand for childcare services in the interest area will be provided by this analysis. The purpose of this research is to shed light on the viability and profitability of starting a nursery in the United Kingdom (UK). Mitchell, R. (2023). The paper will examine the competitive landscape, target market, market dynamics, and marketing tactics needed to launch and expand a profitable nursery business in the United Kingdom. Sword, R. (2022).

Project description and Market Evaluation

A comprehensive market analysis is necessary to guarantee the nursery's success. Important insights on the target area's childcare service demand will be obtained from this analysis. Key details regarding the demand for childcare services in the interest area will be provided by this analysis. A well will shed light on variables including neighborhood demographics, accessibility to transit, population density, and distance from schools, Salon et al.’s (2012) how local planning actions affect distance. It is crucial to choose a site that satisfies the nursery's operating needs and guarantees parent convenience.

Objectives‏

The main objective is to satisfy Birmingham's growing demand for child care services, making sure that working parents have a dependable and easily accessible choice for their kids' care.: Meeting Growing Demand; Secondly, Providing High-Quality Care: the nursery's goal is to provide a supportive and instructive atmosphere where the safety, growth, and well-being of the kids entrusted to its care come first.‏ Thirdly ,Assisting Working Families: the nursery strives to assist working families in striking a balance between their personal and professional life by providing flexible hours and reasonable fees.

Goals

The Goal of this project is Addressing Growing Demand, Providing High Quality Care, Supporting Working Families. Over the past few years, the nursery market in the UK has grown steadily. Several variables, such as the growing number of working parents, the increased emphasis on early childhood education, and government programmes supporting (Murphy. et al, 2021) accessible daycare alternatives, might be blamed for this. IBISWorld predicts a £4 billion UK nursery market by 2021. Understanding market trends, consumer preferences, competitive analysis, and legal requirements is crucial for a nursery's success. Enrolment and capacity are key, with a focus on accommodating 2–6-year-olds while maintaining high-quality care. Hiring and education are also essential for a secure environment. (Article What Does Nursery Education Offer Children? 2003). To achieve financial sustainability, ensure income meets operational expenses and allows for future expansion. Build trust with the neighbourhoods and establish a strong rapport as a trustworthy daycare partner, ensuring future growth and improvement.

Project Scope

This describes the services and facilities that the nursery project will offer, along with its limits and bounds.

In scope Childcare Services:‏ The Childcare Act (2006) mandates local authorities to conduct a Childcare Sufficiency Assessment (CSA) to understand the use of nursery services, the county's childcare supply, and any factors affecting demand for nursery services - The project will involve the construction and management of a creche that will provide instruction (Stanley. Y & Bradbury. P, 2021) and care for kids in the specified range-2 to 6 years old.

Age-appropriate educational programmes, including as play-based learning, early childhood development, and kindergarten preparedness, will be offered by the nursery:

Curriculum for Education, ‏Expert Employees‏ Security and Safety,‏ Adaptable Hours, ‏Reasonable Costs,‏ Involvement of Communities, Adherence to Regulations.

Curriculum Instruction:‏ Statutory guidance, The Early Years Foundation Stage (EYFS, 2023). What you want the kids to learn throughout their time with you is outlined in the curriculum. The Early Years Foundation Stage (EYFS), which provides a framework upon which you can develop through the seven areas of learning, must serve as its foundation. By designing a curriculum specifically for your environment and offering experiences and activities that address those learning areas, you may determine the most effective way to teach those subjects, according to “Good Practice in Early Education” (SEED), (2017).

Age-appropriate educational programmes, including as play-based learning, early childhood development, and kindergarten preparedness, will be offered by the nursery.‏ Play-based learning encompasses a broad range of methods in a variety of settings, such as staff-led exercises and unstructured play. Play-based learning | (EEF (Education Endowment Foundation) - Education Endowment Foundation (2023).

Skilled Personnel: Assembling and educating a team of compassionate and competent early childhood educators and support personnel‏

Safety and Security: Enforcing strict safety and security protocols to guarantee the welfare of children under our supervision .According to “: Safeguarding and Welfare Requirements  "Safety and suitability of premises, environment and equipment: Safety 3.53, 3.56-3.65, (see reference) will fallow all the Regulation and Procedure to guarantee that every child is securely cared for while they are with us, we keep our nursery grounds as secure as possible. UK nursery operations must adhere to health and safety regulations, safeguarding policies, employment laws, staff-to-child ratios, premises suitability, risk assessments, and GDPR (General Data Protection Regulation) compliance for data protection and confidentiality (Needham, 2012).

Flexible Hours: To meet the diverse schedules of working parents, flexible daycare hours should be provided

Reasonably Priced: Offering competitive and reasonable rates to enable access to high-quality childcare

Community Engagement: Community engagement is the process of forging close ties with the neighbourhood through outreach, gatherings, and assistance for working families.

Regulatory Compliance: guaranteeing adherence to all licencing and regulation requirements for childcare‏ (National Planning Policy Framework ,2023) which lays out the planning policies of the government for England and how they should be implemented.

Outside of Scope‏

Primary Education: Formal K–12 instruction will not be offered by the daycare

Medical Services: No further medical attention will be given beyond first assistance.

Extended Hours: The nursery will not run around-the-clock, but it will provide flexible hours.

Transportation: There will be no transportation provided to and from the nursery for the kids.‏

Food Services: The nursery does not offer full-service catering, although it may serve meals or snacks. The project scope identifies the facilities and services the nursery will provide, while also recognising its limitations. This clarity guarantees that the project stays concentrated on its primary goals and duties.‏

The market gaps

Is it when there is no current product or market presence; there is a market gap that might be original, existing, or new. Upgrade or launches can significantly boost sales. This is a summary of the market gap for our nursery project: Limited Supply, High Demand:  Birmingham's need for childcare services have increased as a result of the government's elimination of its recommendation that people work from home. There can be a vacuum in the market if the current childcare facilities and providers are unable to handle the rising demand.

Quality and Accessibility: It can be difficult for many working parents to locate high-quality, reasonable price daycare services. Our nursery can fill this need by providing the community with a dependable, easily accessible, and first-rate childcare option (Equality Act 2010. Gov.UK)

Persistent Need: The nursery aims to cater to working parents in Birmingham, who have long-standing concerns about childcare costs and safe play environments. It will provide a safe, nurturing environment for children to learn, play, and develop under knowledgeable and compassionate staff, regardless of their background or income. These parents may come from a variety of backgrounds, occupations, and income levels, but they all share the same need for dependable childcare services.

The problems aim to solve

The project addresses the surge in childcare demand due to the government's removal of work-from-home guidelines, the struggle for working parents to find affordable, accessible daycare, and the increasing balance between job and family obligations.

Business Model

A nursery's business model is to offer a defined plan for making money while providing necessary childcare services. In this instance, the nursery will be able to support itself financially and serve a wide range of families thanks to a combination of tuition fees, government subsidies, and extra services. ‏

Tuition: The tuition that parents or guardians pay for their children's care and education will be the nursery's main source of income. In order to maintain competitiveness with other local childcare providers, tuition prices will be set in a manner that reflects market rates (IBISWorld).‏

Government Assistance Programmes: The Tax-Free Childcare Scheme and Universal Credit are two examples of government assistance programmes that can be extremely helpful in aiding families and lowering the cost of childcare. The nursery can obtain additional funding and lower the cost of childcare for parents by taking part in and making the most of these programmes (GOV.UK).‏

Extra Services: For a price, the nursery may provide extra services like transport, longer hours, or specialised educational programmes. According to MarketWatch, these value-added services support the various needs of working parents while also boosting total revenue.‏

Community Engagement: According to the Harvard Business Review, establishing trusting bonds with the neighbourhoods' companies and employers and working together can lead to partnerships and sponsorships that increase sales.‏

Work breakdown structure

Breaking down the project into manageable tasks and subtasks is necessary to create a work breakdown structure (WBS) for launching a nursery.‏

1. Project Commencement ‏

2. Analysis of Markets

Consumer Demand ‏

Competition Evaluation ‏

Geography Analysis

3. Adherence to Regulations ‏

Permits & Licenses

Rules for Health and Safety   ‏

Staffing Level Needs‏

4. Planning for Facilities

Select the Location

Layout and Design of the Facility

Equipment and Furnishings‏

5. Personnel and Instruction

Hiring of Qualified Personnel

Employee Education ‏

Establishing Payroll and HR‏

6. Curriculum- Design ‏‏

Designing Educational Programme

Educational Resources and Materials ‏

Scheduling Activities‏

7. Promotion and Marketing ‏

Marketing Plan and Branding ‏

Website Creation   ‏

Public Relations and Outreach‏

8. Accounting for Finances‏

Budgetary Planning   ‏

Funding Distribution ‏

Spending Control‏

9. Setup of Operations ‏

Installing Security Systems ‏

Purchasing Supplies

Programmes and record keeping

10. Assurance of Quality ‏

Quality Control Methodologies

Safety Guidelines    ‏

Frequent Examinations

11. Pre-launch examination   ‏

Childcare Services Trial Run    ‏

Staff Training Assessment

Mock Enrolment‏

12. Official Launch ‏

"Event Management"   ‏

The formal opening ceremony and Start of Complete Operation

From the first stages of preparation to the big opening day, the tasks required to launch the nursery might be arranged according to a hierarchical structure. Depending on the requirements and schedule of our project, we might further develop and specify these responsibilities.‏

Stakeholders

The nursery plan involves various stakeholders including parents, teachers, healthcare professionals, childcare providers, educational consultants, government agencies, community organizations, and a Parental Involvement Committee. Parents entrust their children's care to the facility, while teachers create a safe learning environment. Health professionals collaborate on immunization schedules, routine check-ups, and medical emergencies. Community organizations address specific needs and promote inclusivity. (Harrist, A.W.,et al.,2007).

Competitors

Birmingham nursery project faces potential rivals such as Busy Bees Nurseries, King Edward's School, Birmingham Community Education, local church nurseries, and corporate on-site childcare. These competitors provide excellent childcare services, cater to local families, and offer early childhood education programs. It is crucial to identify and compete with these potential competitors to ensure success. Nurseries' planning encompasses more than academic instruction, as it significantly influences children's social, emotional, and physical development. The focus is on crucial policy measures aimed at enhancing the learning environment for all children (Denham & Brown 2010).

Organizations and Individuals affected by Nurseries

Nurseries affect people and organisations in both direct and indirect ways, such as parents, kids, carers, educators, government agencies, healthcare providers, social service providers, educational institutions, and organisations dedicated to health and safety. (Nursing Research, 1976)

Quad chart

This quad chart provides challenges, opportunities, and future of Birmingham Blossom Kids Nursery.

Birmingham Blossom Kids Nursery Gannt Chart

| # Task | # Start date | # End date | # Resources and assignation |
| --- | --- | --- | --- |
| # Planning and development | # 01/01/2024 | # 15/03/2024 | # Project management and project team |
| # Regulatory compliance | # 01/02/2024 | # 15/04/2024 | # Compliance officer, legal consultant |
| # Facility setup | # 01/03/2024 | # 30/06/2024 | # Facility manager, contractors |
| # Staff recruitment | # 15/03/2024 | # 30/06/2024 | # HR manager, recruitment team |
| # Curriculum development | # 01/04/2024 | # 31/07/2024 | # Education manager, curriculum team |
| # Marketing and promotion | # 01/05/2024 | # 31/08/2024 | # Marketing manager and team |
| # Operations setup | # 01/06/2024 | # 30/09/2024 | # Operations manager, facilities team |
| # Pre-launch testing | # 01/08/2024 | # 30/09/2024 | # Facility manager, QA (Quality Assurance) team |
| # Grand opening | # 01/10/2024 | # 15/10/2024 | # Event planner and marketing team |

Financial Projection

Startup Costs:

Initial capital required: £200,000.

Allocation of funds for facility setup, staff hiring, marketing, and equipment.

Revenue Projections (Year 1):

Tuition fees from 80% enrolment rate: £160,000.

Additional services revenue: £20,000.

Government subsidies: £10,000.

Total expected revenue: £190,000.

Expenses (Year 1):

Staff salaries: £80,000.

Facility rent and maintenance: £30,000.

Marketing and promotion: £10,000.

Educational materials and supplies: £15,000.

Administrative and operational costs: £25,000.

Total expected expenses: £160,000.

Profit (Year 1): Expected profit (revenue minus expenses): £30,000.

Must be keeping count that these are only estimates counts; actual financials could differ depending on a number of variables and state of the market.

Critical Path Activities

Facilities Scheduling:‏

This is important since the building design and location selection affect other responsibilities including staffing, curriculum development, and operations setup.‏ A create a data where everyone is aware of data's potential, uses it, understands its limitations, and uses it for progress, empowering employees to act on it, and better communication (Data Analytics & Data Science, 2019).

Personnel and Instruction:‏

Curriculum development and operational setup must come first, followed by recruitment and training. ‏

Promotion & Marketing

In order to increase brand recognition before to the grand opening, it should begin early.‏

Handling Finances:

Monitor spending control and budgets throughout the project.‏

Guarantee of Quality:‏

ongoing duties to guarantee that quality and safety requirements are fulfilled at every turn.‏

Resurce Management

To ensure the successful running of the childcare centre, resource management for the opening of a nursery requires managing workers, facilities, and finance in an effective manner. ‏

Staff: Qualified Early Childhood Educators: Selecting knowledgeable, seasoned employees to offer the kids' education, care, and supervision.‏

Support Staff: Hiring workers for general operations, cleaning, and administrative duties.‏

Resources: Recruiting, staff development, and training may fall within the purview of a human resources manager. (Employee training,2023. Coursera)

The role of the health and safety officer is to make sure that safety rules are followed and that kids are kept in a secure setting.

Resources:‏ finding an appropriate site with lots of indoor and outdoor space for classrooms, play spaces, and restrooms is known as facility space; furnishings and Equipment: Purchasing toys, safety gear, instructional materials, and furnishings that fits the age of the recipient;

Security Systems: Implementing access control and other security measures.

Project Success Criteria

The nursery aims to achieve a high enrolment rate of 80% within the first year, a financial target of break-even within 12-18 months, a profit margin of 15% by the end of the second year, and a 90% customer satisfaction rate.

Conclusion

This marketing research outlines the possible advantages and difficulties of starting a nursery in the United Kingdom. A nursery may create a strong brand and prosper in this expanding sector by comprehending the market dynamics, determining the target market, and putting efficient marketing methods into practise.

Several governmental organisations and agencies manage the institutional environment for nurseries in the United Kingdom. The Office for Standards in Education, Children's Services and Skills, or Ofsted, is the main regulatory organisation for early childhood education. It inspects and oversees all early childhood providers. Getting the licences and permissions required to run a childcare requires adhering to Ofsted requirements. The main regulating organisation in the UK for early childhood education is Ofsted, which inspects and evaluates providers to make sure all relevant licences and permits are complying (Sakr et al., 2023).

Birmingham's need for creche services is growing. Opportunities and obstacles in a cutthroat market. Put an emphasis on community involvement and regulatory compliance. Dedication to a range of services and joint venture possibilities.

Potential partners and funders are invited to take part in this initiative by Blossom Kids Birmingham. You may contribute to a solution that meets the urgent demand of working parents and provides a loving, learning environment for kids by making an investment in the nursery project.‏

# References

# Article: What Does Nursery Education Offer Children? (2003.) Journal: Transforming Nursery https://www.citethisforme.com/cite/sources/journalautociteeval#:~:text=What%20Does%20Nursery%20Education%20Offer%20Children Education, Publication year, 2003.

# Blossom Educational (2022) EYFS statutory policies and procedures for nurseries: 5 top tips for the New Nursery, Blossom Educational. Available at: https://blossomeducational.com/blog/eyfs-statutory-policies-and-procedures-for-nurseries-5-top-tips-for-the-new-nursery/ (Accessed: 16 October 2023).

# Susanne A. Denham & Chavaughn Brown (2010) “Plays Nice With Others”: Social–Emotional Learning and Academic Success, Early Education and Development, 21:5, 652-680, DOI: 10.1080/10409289.2010.497450 https://www.tandfonline.com/action/showCitFormats?doi=10.1080%2F10409289.2010.497450#:~:text=Susanne%20A.%20Denham%20%26%20Chavaughn%20Brown%20(2010)%20%E2%80%9CPlays%20Nice%20With%20Others%E2%80%9D%3A%20Social%E2%80%93Emotional%20Learning%20and%20Academic%20Success%2C%20Early%20Education%20and%20Development%2C%2021%3A5%2C%20652%2D680%2C%20DOI%3A%2010.1080/10409289.2010.497450

Data Analytics & Data Science, 2019. Building a data culture to accelerate digital transformation, by Editor's Choice11 April 2019 https://www.information-age.com/building-a-data-culture-digital-transformation

13429/#: ~:text=A%20data%20culture%20is, to%20act%20on%20data.

Department for Education, Published3 1 March 2014, Last updated,4 September 2023, Early years foundation stage (EYFS) statutory framework https://www.gov.uk/government/publications/early-years-foundation-stage-framewor-2#:~:text=Early%20years%20foundation%20stage%20(EYFS)%20statutory%20framework

Early Years entitlements: Operational guidance - GOV.UK. (2018) Available at

https://assets.publishing.service.gov.uk/media/6172900ae90e07198018f9a1/Early_years_entitlements-operational_guidance__3_.pdf (Accessed: 15 October 2023). (2023)

Early education and childcare - gov.uk (2023) Available at:  https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/1149556/Early_education_and_childcare_statutory_guidance_-_April_2023.pdf (Accessed: 12 October 2023).

Early Years leadership development during workforce crisis. (2023) (Accessed: October2023). Available at: https://www.tandfonline.com/doi/full/10.1080/1350293X.2023.2234108

Employee training: What it is and why it is important?2023. Coursera. Available at:

https://www.coursera.org/articles/employee-training?utm_medium=sem&utm_source=gg&utm_campaign=B2C_EMEA_ibm-data-science_ibm_FTCOF_professional-certificates_country-GB-country-UK-pmax-nonNRL-within-14d&campaignid=20486968205&adgroupid=&device=m&keyword=&matchtype=&network=x&devicemodel=&adposition=&creativeid=&hide_mobile_promo&gclid=CjwKCAjwkNOpBhBEEiwAb3MvvRYt3L4cTc0cUMxSRyhwyl9K2kYcEG1Hc5BmNDhLr-GFVVo2N1AlMxoC9wQQAvD_BwE (Accessed: 16 October 2023).

Equality Act 2010. Guidance Reasonable adjustments: a legal duty,2020-Gov.UK Updated 15 September 2020, under the equality plan guidance, Government Equalities Office and Equality and Human Rights CommissionPublished27 February 2013Last updated

16 June 2015 — https://www.gov.uk/guidance/equality-act-2010-guidance#:~:text=Equality%20Act%202010%3A%20guidance

Galloway (2018), Journal: Schools, Pupils and Special Educational Needs. Article: Conclusions: Creating Special Educational Needs? or Meeting Them? Publication month:09; publication day 03. https://www.citethisforme.com/cite/sources/journalautociteeval#:~:text=Conclusions%3A%20Creating%20Special%20Educational%20Needs%3F%20or%20Meeting%20Them%3F

Good Practice in Early Education” (SEED), (2017). Department for Education Published 27 January 2017, Gov.uk Available on https://www.gov.uk/government/publications/good-practice-in-early-education#:~:text=Research%20and%20analysis-,Good%20practice%20in%20early%20education,27%20January%202017,-Get%20emails%20about

Harrist, A.W.,et al.,2007. Defining Quality Child Care: Multiple Stakeholder Perspectives. June 2007.Early Education and Development 18:1-32. DOI:10.108010409280701283106. Amanda W. Harrist, Stacy D. Thompson, Deborah J. Norris.

https://www.researchgate.net/publication/236333361_Defining_Quality_Child_Care_Multiple_Stakeholder_Perspectives.

Murphey et al, 2021.Partnership with families in early childhood education: Exploratory study Research Article, First published online January 5, 2021, Catherine Murphy https://orcid.org/0000-0003-4866-4693 cmurphy@parentingrc.org.au, Jan Matthews, […], and Warren Cann+1View all authors and affiliation, Volume 46, Issue 1https://doi.org/10.1177/1836939120979067

Mitchell, R. (2023) How to open a nursery business, Rangewell. Available at: https://rangewell.com/childrens-day-nurseries/guides/how-to-set-up-a-nursery  (Accessed: 11 October 2023).

Morton,M. 2023.Article: How to set up an inspirational and cosy baby room in a nursery, Journal title Early Years Educator, Publication date 02/10/2023

https://www.citethisforme.com/cite/sources/journalautociteeval#:~:text=How%o%20set%20up%20an%20inspirational%20and%20cosy%20baby%20room%20in%20a%20nursery

National Planning Policy Framework, 2023.Gov.uk. National Planning Policy Framework was published on 27 March 2012 and revised in 2018, 2019, 2021 and most recently 5 September 2023. https://www.gov.uk/government/collections/planning-practice-guidance#:~:text=National%20Planning%20Policy%20Framework%20was%20published%20on%2027%20March%202012%20and%20revised%20in%202018%2C%202019%2C%202021%20and%20most%20recently%205%20September%202023.

Needham, M. (2012, March). Child well-being. Understanding children’s lives. International Journal of Early Years Education, 20(1), 97–99. https://doi.org/10.1080/09669760.2012.665647

(Nursing Research, 1976) Article: COMMUNITY HEALTH SERVICES (Including Home Care Services, Home Health Agencies, and Health Maintenance Organizations). Publication year1976, March. https://www.citethisforme.com/cite/sources/journalautociteeval#:~:text=COMMUNITY%20HEALTH%20SERVICES%20(Including%20Home%20Care%20Services%2C%20Home%20Health%20Agencies%2C%20and%20Health%20Maintenance%20Organizations)

Play-based learning | EEF - Education Endowment Foundation (2023) 7, February, Website. https://educationendowmentfoundation.org.uk/education-evidence/early-years-toolkit/play-based-learning#:~:text=Foundation%3APlay%2Dbased%20learning-,Play%2Dbased%20learning,Moderate%20impact%20for%20very%20low%20cost%20based%20on%20very%20limited%20evidence,-Implementation%20cost

Safeguarding and Welfare Requirements for nursery. The Health and Safety at Work Act 1974  (The Management of Health and Safety at Work Regulations 1999  The Reporting of Injuries, Diseases and Dangerous Occurrences Regulations 1995 (RIDDOR)  Safety Representatives and Safety Committees Regulations 1977 (a) and The Health and Safety (Consultation with employees) Regulations 1996 (b)  https://www.bing.com/search?pglt=43&q=for+nursery+regolation+%E2%80%8FExpert+Employees%E2%80%8F+Security+and+Safety%2C%E2%80%8F&cvid=49792eb2b2d04407a042b93abf12cca3&gs_lcrp=EgZjaHJvbWUyBggAEEUYOdIBCTIyNDUzajBqMagCALACAA&FORM=ANNTA1&PC=NMTS#:~:text=%C2%A0%C2%B7%20PDF%20file-,Children%E2%80%99s%20safety%20and%20Security%20in%20the%20nursery%20%2D%20Small%20World%20Nursery,We%20maintain%20the%20highest%20possible%20security%20of%20our%20nursery%20premises%20to,-ensure%20that%20each

Sakr,M. 2023 Making time for leadership development when leaders' time is scarce

Published Online:18 Jul 2023https://doi.org/10.12968/eyed.2023.24.1.17

Salon D, Boarnet MG, Handy S, et al. (2012) How do local actions affect VMT? A critical review of the empirical evidence. Transportation Research Part D: Transport and Environment 17(7): 495–508. https://journals.sagepub.com/doi/full/10.1177/0042098020951001#bibr33-0042098020951001:~:text=Salon%20D%2C%20Boarnet%20MG%2C%20Handy%20S%2C%20et%20al.%20(2012)%20How%20do%20local%20actions%20affect%20VMT%3F%20A%20critical%20review%20of%20the%20empirical%20evidence.%20Transportation%20Research%20Part%20D%3A%20Transport%20and%20Environment%2017(7)%3A%20495%E2%80%93508

Stanley & Bradbury, P (2021). Posted on30 June 2021

https://www.ceredigion.gov.uk/resident/children-young-peopleservices/childcare/childcare https://socialcareinspection.blog.gov.uk/2021/06/30/the-early-years-sector-a-changing picture/#:~:text=The%20early%20years%20sector%20%E2%80%93%20a%20changing%20picture

Sword, R. (2022) How to start a nursery business, The Hub | High Speed Training. Available at: https://www.highspeedtraining.co.uk/hub/how-to-start-a-nursery-business/ (Accessed: 10 October 2023).

The Childcare Act of (2006) Childcare Sufficiency Assessment (CSA) sufficiency/#: ~:text=Childcare%20Sufficiency%20Assessment-, Childcare%20Sufficiency%20Assessment, -The%20local%20authority