Student name: Cecile Abuzour

Student ID: 2218610

Lecturer: Dr Zainab Atta

Module Name: Project management

Module code: LCBB6006_LON

Project Plan: Lewisham 2-to-4 Bedroom HMO Conversion

Table of Contents

1.	Introduction	3

1.1 Methodology Justification	3

2.	Project Definition and Scope	3

2.1 Project Aim and Objectives	3

2.2 Project Scope (including and excluding)	4

3.	Project Outputs and Breakdown: Work Breakdown Structure (WBS)	4

4.	Project Scheduling and Timeline:	6

4.1 Key Milestones	6

4.2 Critical Path Analysis	7

5.Ressource and Cost Planning	7

5.1 Personal Resource Breakdown Structure	7

5.2 Material and Fixed Cost Breakdown	8

6.Risk and Stakeholder Management	8

6.1 Project Risks	9

6.2 Stakeholder Analysis and communication management	9

7.Conclusion	10

Reference	11

# Introduction

## 1.1 Methodology Justification

This project will adopt a Waterfall methodology, a sequential design process in which progress is seen as flowing steadily downwards (like a waterfall) through the phases of conception, initiation, analysis, design, construction, testing, deployment and maintenance. This choice is driven by the high regulatory risk and fixed scope of the project. The requirement for a single, upfront Planning Permission approval from Lewisham Council  necessitates a linear, non-iterative approach. Unlike software development, where Agile methodologies allow for flexibility, construction projects with significant structural changes cannot accommodate iterative changes to the core design once regulatory approval is granted (Jado and al-Sayyid, 2024).

This academic report details the Project Plan for the conversion of a 2-bedroom residential property in Lewisham, London, into a 4-bedroom, 2-bathroom House in Multiple Occupation (HMO). The project is initiated by a private investor seeking to maximize rental yield through a high-quality, compliant property conversion. This plan applies established project management methodologies, including the Work Breakdown Structure (WBS) and Critical Path Method (CPM), to ensure the project is delivered efficiently, on time, and within budget (Kerzner, 2025). The core challenge is navigating the regulatory environment of Lewisham Council while executing complex structural work.

# Project Definition and Scope

A clear project definition is essential for managing stakeholder expectations and controlling the project's boundaries, particularly in construction projects where scope creep is a common risk (Association for Project Management., Holmes 2015)

## 2.1 Project Aim and Objectives

The Aim of this project is to successfully convert a 2 bedroom in Lewisham into a high-quality living, fully compliant 4 bedroom, 2-bathroom HMO rental property, focusing on maximizing usable space and tenant appeal.

The project's success will be measured against the following SMART Objectives. The budget and timeline are based on current London construction cost guides for complex loft conversions (Resi, 2025).

| Objective | Matric | Target | Timeframe |
| --- | --- | --- | --- |
| O1 (Time) | Project Completion | Handover of the fully certified property | Within 28 weeks of project initiation. |
| O2 (Quality) | Regulatory Compliance | Obtain Planning Permission and HMO License | 100% success rate. |
| O3 (Financial) | Budget Adherence | Complete the project | Within the allocated budget of £120,000. |
| O4 (Performance) | Rental Readiness | Achieve 100% occupancy of all 4 rooms | Within 4 weeks of project completion. |

## 2.2 Project Scope (including and excluding)

The project assumes the existing house structure is in good condition, allowing the scope to focus on conversion rather than full refurbishment.

| Scope Item | Status | Descriptions |
| --- | --- | --- |
| Structural Work | IN | Full loft conversion, internal reconfiguration to create new rooms, and installation of one new bathroom. |
| Specialized Storage | IN | Installation of built-in wardrobes and integrated storage units in all 4 bedrooms to maximize tenant space. |
| Permitting | IN | Application for Planning Permission (due to Lewisham's Article 4 Direction) and Building Control approval (Lewisham Council, 2025). |
| Full System Replacement | OUT | Full electrical rewire, new plumbing, and new central heating system are excluded, as the existing systems are assumed to be in good working order. |
| Furnishing | OUT | The purchase and installation of loose furniture (beds, desks, chairs) is excluded from this project plan. |

# Project Outputs and Breakdown: Work Breakdown Structure (WBS)

The WBS is the hierarchical decomposition of the project scope, ensuring all work packages are defined and manageable (Project Management Institute, 2022) 4. The WBS below is structured into five major phases, following a phase-based approach which is standard for construction projects where work is naturally grouped by the Project Life Cycle (PLC) stages (ProjectManager.com, 2025)

| WBS ID | Deliverable | Work Package (Task) | Duration (Days) |
| --- | --- | --- | --- |
| 1.1 | Initiation & Regulatory Compliance |  |  |
| 1.1.1 | Project Definition & Plan | Finalize Project Plan (WBS, Budget, Schedule) | 3 |
| 1.1.2 | Design & Permitting | Appoint Architect & Structural Engineer | 2 |
|  |  | Produce Detailed Architectural Drawings (Incl. Storage) | 12 |
|  |  | Submit Planning Permission Application | 1 |
|  |  | Receive Planning Permission Approval (M1) | 60 |
| 1.1.3 | Procurement | Tender & Select Main Contractor | 7 |
|  |  | Finalize Contracts & Insurance (M2) | 3 |
| 1.2 | Pre-Construction & Demolition |  |  |
| 1.2.1 | Site Setup | Erect Site Hoarding & Safety Signage | 1 |
|  |  | Protect Existing Finishes (Floors, Walls) | 1 |
| 1.2.2 | Targeted Demolition | Demolish Internal Walls for Reconfiguration | 3 |
|  |  | Create Openings for Loft Staircase | 2 |
| 1.3 | Structural & First Fix Construction |  |  |
| 1.3.1 | Loft Conversion Shell | Install Structural Beams & Floor Joists | 8 |
|  |  | Construct Dormer and Roof Structure | 12 |
| 1.3.2 | Internal Reconfiguration | Build New Internal Stud Walls (4 Bedrooms, 2 Bathrooms) | 5 |
| 1.3.3 | First Fix Services | T Extend Electrical Wiring (First Fix) | 7 |
|  |  | Extend Plumbing & Heating System (First Fix) | 7 |

| WBS ID | Deliverable | Work Package (Task) | Duration (Days) |
| --- | --- | --- | --- |
| 1.4 | Second Fix & Finishing |  |  |
| 1.4.1 | Insulation & Plastering | Install Insulation & Plasterboard | 5 |
|  |  | Plastering & Skimming | 7 |
| 1.4.2 | Specialized Storage Installation | Install Built-in Wardrobes & Under-Bed Storage | 10 |
|  |  | Install Integrated Bathroom Storage Units | 3 |
| 1.4.3 | Second Fix Services | Install Sockets, Switches, & Light Fittings | 3 |
|  |  | Install Sanitaryware & Tiling | 5 |
| 1.4.4 | Final Finishes | Final Decoration (Painting) & Flooring | 7 |
| 1.5 | Handover & Closure |  |  |
| 1.5.1 | Final Inspections | Building Control Final Inspection (M3) | 1 |
|  |  | HMO License Application & Inspection | 5 |
| 1.5.2 | Project Closure | Site Clean-up & Snagging List Completion | 3 |
|  |  | Final Handover to Client (M4) | 1 |

# Project Scheduling and Timeline:

The project schedule is defined by the dependencies between tasks, with the 60-day planning approval period forming the longest and most critical initial dependency. The total project duration is estimated at 142 working days (approx 28.4 weeks).

## 4.1 Key Milestones

| Milestone ID | Description | WBS Deliverable | Target Completion (Working Day) |
| --- | --- | --- | --- |
| M1 | Planning Permission Approved | 1.1.2 | Day 63 |
| M2 | Main Contractor Contract Signed | 1.1.3 | Day 70 |
| M3 | Building Control Final Sign-off | 1.5.1 | Day 138 |
| M4 | Final Handover to Client | 1.5.2 | Day 142 (End of Week 28) |

## 4.2 Critical Path Analysis

The Critical Path is the sequence of activities that determines the earliest completion date of the project (Jado and al-Sayyid, 2024). For this project, the critical path is primarily driven by the regulatory approval process and the sequential nature of the structural work:

Receive Approval → Site Setup → Demolition → Structural Beams → Dormer Construction → Stud Walls → Plastering → Storage Installation → Final Finishes → HMO Inspection.

The 60-day planning approval period is the most significant risk to the schedule.

# 5.Ressource and Cost Planning

Resource allocation is based on a blended approach, utilizing specialized consultants for the design and regulatory phases and a Main Contractor for the construction phase (Cerezo-Narváez, 2020).

## 5.1 Personal Resource Breakdown Structure

The personnel costs are based on typical daily rates for specialized contractors and consultants in the London area, reflecting the high-cost environment of the project location (Larson and Gray, 2018). The Main Contractor's cost is a blended rate covering all sub-trades for the 102-day construction period.

| Role | Responsibility | Estimated Effort (Days) | Daily Rate (£) | Total Cost (£) |
| --- | --- | --- | --- | --- |
| Project Manager (PM) | Client liaison, regulatory oversight, contract management. | 25 | 400 | 10,000 |
| Architect | Detailed design, planning submission. | 15 | 350 | 5,250 |
| Structural Engineer | Structural calculations for loft. | 5 | 400 | 2,000 |
| Main Contractor (MC) | Manages all construction tasks (1.2 - 1.4). | 102 | 600 | 61,200 |
| Total Personnel Cost |  | 147 |  | £78,450 |

## 5.2 Material and Fixed Cost Breakdown

The project budget of £120,000 is set against an industry benchmark of £130,000 for a complex loft conversion in London (Resi, 2025). The material and fixed costs are estimated to align with this benchmark, with the cost variance (R4) being a key risk to manage (Biskupek, 2018).

| Resource Type | Description | Cost in £ |
| --- | --- | --- |
| Construction Materials | Timber, plasterboard, insulation, roofing, plumbing, electrical extensions. | 25,000 |
| Fixtures & Fittings | Sanitaryware, kitchen units, specialized built-in storage. | 10,000 |
| Regulatory Fees | Planning Application Fee, Building Control Fee, HMO License Fee. | 3,500 |
| Contingency Reserve | 10% of total estimated cost (for unforeseen issues) | 11,695 |
| Total Material/Fixed Cost |  | £50,195 |
| Total Estimated Project Cost | £128,645 |  |
| Project Budget (O3) | £120,000 |  |
| Variance | -£8,645 |  |

# 6.Risk and Stakeholder Management

The project's success hinges on proactive risk management, particularly concerning regulatory compliance and cost control (Biskupek, 2018).

## 6.1 Project Risks

The risk register is developed using a qualitative risk analysis approach, where risks are assessed based on their Probability (P) and Impact (I) to determine a risk score (R-Score) (Project Management Institute, 2022). The response strategies are chosen based on the four primary risk responses: Avoid, Mitigate, Transfer, and Accept (P. Franklin and G. Berlin, 2024)

| Risk ID | Risk Description | Probability (P) | Impact (I) | R-Score (P x I) | Response Strategy |
| --- | --- | --- | --- | --- | --- |
| R1 | Planning Refusal: Lewisham Council rejects the HMO conversion application. | High (0.7) | High (0.9) | 0.63 | Mitigation: Pre-application advice from the Council. Contingency: Appeal or redesign to a 3-bed, 2-bath configuration. |
| R2 | Unforeseen Structural Issues: Hidden defects are found during demolition (e.g., rot, asbestos). | Medium (0.5) | High (0.8) | 0.40 | Mitigation: Detailed structural survey prior to purchase. Contingency: Use the Contingency Reserve (£11,695) to cover remediation costs. |
| R3 | Main Contractor Delay: Construction work is delayed due to resource or supply chain issues. | Medium (0.6) | Medium (0.7) | 0.42 | Transfer: Include liquidated damages (penalty clauses) in the contract . Mitigation: Weekly progress meetings with the Main Contractor. |
| R4 | Budget Overrun: The actual cost exceeds the allocated budget (Variance: -£8,645). | High (0.9) | Medium (0.7) | 0.63 | Mitigation: Immediately present the cost variance to the Client and negotiate a revised budget or reduce the scope of high-cost items (e.g., specialized storage). |

## 6.2 Stakeholder Analysis and communication management

The stakeholder analysis uses the Power/Interest Grid to categorize key project participants, a fundamental tool in the Project Management Body of Knowledge (Project Management Institute, 2022). The communication strategy is based on the principle that effective communication is essential for successful project execution (Galli, 2020).

| Stakeholder | Power | Interest | Strategy | Management Approach |
| --- | --- | --- | --- | --- |
| Client/Investor | High | High | Manage Closely | Weekly formal status reports focusing on budget and schedule adherence (O1, O3). |
| Lewisham Council (Planning/Building Control) | High | High | Manage Closely | Proactive communication, ensuring all submissions are complete and compliant with local policy (O2). |
| Main Contractor | High | Medium | Keep Satisfied | Clear contract, timely payments, and prompt resolution of site issues. |
| Future Tenants | Low | High | Keep Informed | Their needs (storage, quality, safety) are represented by the Architect and Project Manager in the design phase. |

# 7.Conclusion

This Project Plan provides a comprehensive and realistic roadmap for the "Lewisham 2-to-4 Bedroom HMO Conversion," successfully applying core project management principles to a complex construction scenario. The project's scope was meticulously defined to achieve the client's objective of maximizing rental yield through a compliant 4-bedroom, 2-bathroom configuration, justified by UK HMO standards (government uk , 2025).

The plan utilizes a Waterfall methodology due to the sequential nature of the work and the critical dependency on the 60-day Planning Permission approval. The detailed Work Breakdown Structure (WBS) and the 28-week timeline are grounded in current London market data, demonstrating a practical application of scheduling techniques.

A key finding is the Budget Overrun (R4), which is addressed through a procurement strategy utilizing a Fixed-Price Contract to transfer cost risk to the Main Contractor. The project's success is ultimately dependent on the proactive management of the regulatory risk (R1) and the effective communication with high-power stakeholders. Upon completion, a formal Project Evaluation will ensure that the project is closed successfully and that all objectives are met, providing valuable lessons for future investment projects.

# Reference

Article 4 (1) direction on small HMOs (2025) Lewisham Council. Available at: https://lewisham.gov.uk/myservices/housing/private-tenants-and-landlords/landlords/hmo/article-4-direction-on-small-hmos (Accessed: 25 November 2025).

Association for Project Management. and Holmes, G. (2015) Planning, scheduling, monitoring and control : the practical project management of time, cost and risk. Princes Risborough, Buckinghamshire: Association For Project Manageme

BISKUPEK, A., 2018. Risk Management in IT Projects – Case Study. Trendy Ekonomiky a Managementu, 12(32), pp. 21-33.

CEREZO-NARVÁEZ, A., PASTOR-FERNÁNDEZ, A., OTERO-MATEO, M. and BALLESTEROS-PÉREZ, P., 2020. Integration of Cost and Work Breakdown Structures in the Management of Construction Projects. Applied Sciences, 10(4), pp. 1386.

Galli, B. (2020) 'Effective Strategies for Communication Management in a Project Management Environment', International Journal of Applied Logistics,10(2) Available at: https://doi.org/10.4018/IJAL.2020070105.

government uk (2025) House in multiple occupation licence: London Borough of Lewisham - GOV.UK, Www.gov.uk. Available at: https://www.gov.uk/find-licences/house-in-multiple-occupation-licence/lewisham (Accessed: 29 November 2025).

HSE (2015) The Construction (Design and Management) Regulations 2015: Overview - HSE, Hse.gov.uk. Available at: https://www.hse.gov.uk/construction/cdm/2015/overview.htm (Accessed: 25 November 2025).

Jado, N.G. and al-Sayyid, N.A. (2024) ‘Agility opportunities in construction project management: exploring opportunities in construction projects in integration with waterfall methodology’, Journal of Engineering Research - Egypt, 8(3), pp. 1–8.

Kerzner, H., 2025. Project management: a systems approach to planning, scheduling, and controlling. John Wiley & Sons.

P. Franklin and G. Berlin (2024) 'Early Risk Assessment Based on Partial Information'1–3.

Resi (2025) Resi.co.uk. Available at: https://resi.co.uk/advice/loft-conversions/loft-conversion-cost (Accessed: 29 November 2025).

The Standard for Project Management and a Guide to the Project Management Body of Knowledge (PMBOK Guide), 7th Edition (2022) Copyright Clearance Center.

‌