## Tracker
Final Collaborative Document Progress Tracker | [7 empty] | Final Assignment Hand-in: |  | 2024-05-01
Key: Owner
| JL - James Lloyd | SH - Somma Howard |  | Project : | Steel Museum |  |  |  | Overall Progress : | 72%
| MC - Mathew Catlin | IS - Inderdeep Sidhu |  | Last Updated : | 2024-02-14
| AW - Ayesha Williams |  |  | 25% - Data Gathered, 50% - First Draft Completed & 100% - Final Draft Collated | [5 empty] | 26
Item Ref | Description |  | Owner (Initials) | Commodity Type | Date Discussed | Status | Lead-in Period (Weeks) | First Draft Dealine | Progress (%) | Final Completion Date
1 | Introduction & Masterplan Appraisal
1.01 | The Need |  | JL |  | 2024-02-14 | Y | 2 | 2024-02-28 | 50 | 2024-05-01
1.02 | Location (including history & context) |  | JL |  | 2024-02-14 | Y | 2 | 2024-02-28 | 50 | 2024-05-01
1.03 | Constraints |  | AW |  | 2024-02-14 | Y | 2 | 2024-02-28 | 50 | 2024-05-01
1.04 | Ground Investigation |  | SH |  | 2024-02-14 | Y | 2 | 2024-02-28 | 50 | 2024-05-01 | Green(100%) = Printed out physical copy for folder
1.05 | EIA |  | JL |  | 2024-02-14 | Y | 2 | 2024-02-28 | 50 | 2024-05-01 | Yellow(50%) = Work completed (NOT PRINTED)
1.06 | Feasibility Study |  | All |  | 2024-02-14 | Y | 2 | 2024-02-28 | 100 | 2024-05-01
1.07 | BIM Strategy / Capabilities |  | MC |  | 2024-02-14 | Y | 2 | 2024-02-28 | 100 | 2024-05-01
2 | Landmark Building: Design aspects with sustainable solutions
3.01 | BIM Execution Plan in response to EIRs |  | MC |  | 2024-02-14 | Y | 2 | 2024-02-28 | 100 | 2024-05-01
3.02 | Environmental Factors |  | SH |  |  | Y | 2 | 2024-02-28 | 25 | 2024-05-01
3.03 | Energy |  | AW |  |  | Y | 2 | 2024-02-28 | 50 | 2024-05-01
3.04 | Social Aspects |  | IS |  |  | Y | 2 | 2024-02-28 | 100 | 2024-05-01
3.05 | Economic Comparisons for the Client |  | AW |  |  |  |  | 2024-03-20 | 50 | 2024-05-01
3.06 | Aesthetics |  | JL |  |  | Y | 2 | 2024-03-20 | 50 | 2024-05-01
3.07 | Method Statement |  | MC |  | 2024-02-28 | Y | 4 | 2024-03-20 | 100 | 2024-05-01
3.08 | H&S Risk Assessments |  | MC |  |  | Y | 4 | 2024-03-20 | 100 | 2024-05-01
3.09 | Full Schedule of Works |  | SH & IS |  |  |  |  | 2024-04-17 | 25 | 2024-05-01
3.1 | Distribution of labour and resources (Materials & Equipment) along time, with specific milestones
3.11 | Cash-flow Forecast Analysis |  | JL |  |  |  |  | 2024-04-17 | 0 | 2024-05-01
3.12 | Site Layout at Different Stages of Works |  | IS |  |  |  |  | 2024-03-20 | 50 | 2024-05-01
3.13 | Technical and Non-Technical Specifications |  | IS |  |  |  |  | 2024-04-03 | 25 | 2024-05-01
3.14 | Material Costings with Comparisons |  | JL |  |  |  |  | 2024-03-20 | 50 | 2024-05-01
3.15 | Summary Project Costings |  | JL |  |  |  |  | 2024-04-17 | 50 | 2024-05-01
3.16 | Foundations Substantitation |  | MC |  |  |  |  | 2024-04-17 | 100 | 2024-05-01
3 | Landmark Building: Structural Schematic & Calculations to highlight your solution in drafts and final drawings. NB: Architectural Plans provided
3.01 | Plan |  | AW |  |  |  |  | 2024-04-17 | 50 | 2024-05-01
3.02 | Principle Elevations |  | AW |  |  |  |  | 2024-04-17 | 50 | 2024-05-01
3.03 | Cross Sections / Details |  | AW |  |  |  |  | 2024-04-17 | 50 | 2024-05-01
3.04 | Structural Calcs |  | MC |  |  |  |  | 2024-04-24 | 100 | 2024-05-01
4 | Construction Materials and Methods
4.01 | Identify the different materials and/or components used, considering material options for your selected building, plus hard & soft landscaping |  | JL |  |  |  |  | 2024-04-24 | 0 | 2024-05-01
4.02 | Identify the construction methods and machinery used |  | MC |  |  |  |  | 2024-04-24 | 100 | 2024-05-01
4.03 | Justifications of selections |  | MC/JL |  |  |  |  | 2024-04-24 | 0 | 2024-05-01
Formulas:
Steel Museum = [First Draft Dealine]-([Lead-in Period (Weeks)]*7)