Title

Event Strategic Planning and Delivery Considerations for an International Meeting

Module Code:

BMIH6007

Module Name:

International Meetings Management for the Hotel Industry

Module Lead:

Kathryn Flynn

Student Name:

Madalin Liviu Noada

Student ID number:

2232425

Table of Contents

Introduction	3

The Event Cycle	3

The Event Cycle and Its Significance	3

Application to the Event	3

Event Concept and Itinerary	5

Key Features of the Event	5

Event Schedule	5

Aim and Objectives of the Meeting/Event	6

Aim	6

SMART Objectives for the Symposium	6

Event Management Considerations	7

Operational Activities	7

Strategic Planning Activities for Event Success:	7

Strategic Marketing Approach for Maximum Engagement:	8

Event Budget and Financial Analysis	8

Industry Trends, Issues, and Impacts	9

Trends Influencing the Symposium	9

Challenges and Issues Impacting the Symposium:	9

Situational and Cultural Considerations (SWOT Analysis)	10

SWOT Analysis	10

Conclusion and Recommendations	11

Conclusion	11

Recommendations	11

References	12

References………………………………………………………………………………………………………………………………………. 13

Introduction

The Empowering Equality: A MICE Industry Symposium on Inclusion and Diversity in the Workplace is a brand-new event that aims to rectify the lack of EDI in the working world. The conference is to be held at ExCeL London, which is a world-class venue for many influential events that attract people from all over the world (Ziakas, 2023). In the contemporary world, the role of EDI goes beyond being a moral imperative for organizations it is a strategic imperative for business success, as workforce productivity, innovation, and sustainability depend on it (Dashper and Finkel, 2020).

They justify this event by arguing that organizations with diverse leadership perform 25% better than their counterparts (McKinsey & Company, 2020). While laws like the UK Equality Act 2010 are in place, several industries remain stratified by structure, requiring a systematic approach like this symposium. In its essence, the event aims to bring the existing corporate EDI policies into practical practice by offering a platform for their exchange (Singh and Deri, 2024). From a strategic perspective, it can be linked to corporate social responsibility (CSR) programs to strengthen the commitment to ethical management. In addition, a sustainable EDI strategy contributes to staff satisfaction, talent attraction, and retention, as well as company brand, and thus organizational performance in the globalized economy.

# The Event Cycle

## The Event Cycle and Its Significance

According to Getz (2019), the Event Cycle refers to the systematic and cyclic process of designing, conducting, and Assessing an event. It has four major stages: conceptualization and inception, planning and design, operations, and controlling and assessment. It means maximizing all resources and minimizing risks at each event and its stages taking into account its goals and objectives. Its importance in event management is to productivity, stakeholders, and business continuity (Getz, 2008). Through this way of event management, the Event Cycle proves the ability to optimize the strategies of event management, as well as to enhance attendees’ experience and raise the rates of measurable ROI for long-term industry outcomes (Ziakas, 2023).

## Application to the Event

Concept & Initiation

The first step in the Event Cycle can be referred to as the initiation of the strategic plan, goals, and the plausibility of the event. Empowering from Equality is a symposium designed to overcome these barriers and look at the translation of EDI policies into the workplace. This phase entails a market analysis of HR professionals, business executives, and policymakers to determine the viability of the market (Dashper and Finkel, 2020). Also, financial viability is established through ticket sales, sponsorship, and exhibition stand revenues. Facilities like ExCeL London are chosen for accessibility, sustainability, and compatibility with the type and rank of the event.

Planning & Development

The next step that follows after feasibility is planning. Conference logistics deals with the spatial and temporal organization of the conference, including facility setup, food and beverage services, accessibility, and technology setup for both in-person and online participation. Marketing campaigns are created, alongside the use of digital media platforms, industry collaborations, and influencer marketing. Budgeting is important as it aims to control expenditures on speakers’ fees, promoting activities and operations to the expected revenue sources (Singh and Deri, 2024). Self-assessments are also made which reveal risks like low turn-up, technical hitches, or inadequate funds.

Implementation

This smoothly moves planning into action, which is practised to execute the events. The activity management process is central, navigating day-to-day responsibilities and managing speakers, panels, workshops, and mingling periods (Getz, 2008). But for any unpredicted disturbances, backup AV systems, contingency speakers, and crisis communication measures are adopted.

Post-Event Evaluation

The last indicator is to assess event success in quantitative terms. Engagement analysis, sponsorships, and media coverage also help measure the level of satisfaction among attendees and how much they have grasped. Post-event reports present recommendations on the way forward to improve on post-future execution of such strategized events (Ziakas, 2023).

# Event Concept and Itinerary

## Key Features of the Event

The event is planned to be quite a transformational event, which aims at providing a learning experience, skills enhancement, new contacts, and opportunities. The opening plenary presentations established the conference theme by including key stakeholders in industry, policy, and diversity who offer broad perspectives on the current and future state of EDI (Finkel and Dashper, 2020). These thought leaders will discuss the challenges of inclusion and corporate governance and share evidence-based insights into how organizations can advance EDI beyond compliance-based models (Getz, 2008).

Workshops will include a focus on intersectionality and inclusive leadership, an area of diversity that is frequently overlooked. These sessions will unpack the conventional leadership paradigms and dismantle the prejudices inherent in organizational systems while highlighting the experiences of marginalized identities. Speakers will provide case studies and practical examples of diversity management, with all its successes and pitfalls to consider (Finkel et al., 2019). The symposium also includes live workshops that allow attendees to learn by doing when it comes to developing, putting into practice, and evaluating EDI initiatives. These workshops are conducted by HR analytics professionals, behavioural psychologists, and inclusive policymakers and thinkers to provide both conceptual understanding and practical strategies (Slocum, 2023).

## Event Schedule

Day 1

The first day of the Empowering Equality symposium aims to establish the theoretical and tactical framework for inclusiveness and diversity in the workforce. The opening remarks will introduce the goals of the event and stress the significance of EDI in creating sustainable organizations that excel in performance. This will be accompanied by an opening address by an industry titan who will explain the relationship between EDI and business performance, staff engagement, and creativity (Ziakas, 2023).

A keynote session will be held to discuss intersectionality and leadership, exploring why EDI strategies fail to lead to tangible change in workplaces. Diversity scholars will analyze the blind spots of corporate diversity policies and how discrimination continues to persist despite frameworks. Following the networking lunch, participants will be taken through policy implementation, bias reduction measures, and measurement of inclusion efforts (Getz, 2008). These sessions are designed to provide working professionals with tangible resources to foster inclusion in the workplace.

Day 2

The second day transitions from the theoretical to the practical, with breakout sessions that offer sector-based EDI information for business sectors such as finance, technology, and hospitality. Practical sessions will allow participants to learn how to design and enhance effective employment policies for people with disabilities, using examples and exercises. The closing session will be held to provide an overview of the main points, recommendations, and long-term plans (Bladen et al., 2022). By the end of the event, the attending delegates will have tangible ideas for action and a clear plan of how to make the change.

# Aim and Objectives of the Meeting/Event

## Aim

The Empowering Equality is designed to present entirely a ground-breaking event that will provide organizations with amazing strategies that implement the equality agenda into practice. Combined with HR professionals, corporate personnel and executives, and policy-makers, the event encourages idea-sharing, discussion, and transformation (Getz, 2008). Keynote speeches, panel discussions, and sessions, including hands-on workshops, ensure that EDI does not stay locked within policy discourses but provides theoretical as well as tangible frameworks for making organizations operate in the globalized environment to display equity with efficiency (Ziakas, 2023).

## SMART Objectives for the Symposium

Objective 1: Enhancing Understanding of EDI Strategies

A core goal of the Empowering Equality symposium is to ensure that at least 80% of attendees leave with a greater understanding of EDI frameworks, challenges, and solutions. This will be achieved through data-driven keynote speeches, expert panel discussions, and interactive sessions that dissect the complexities of workplace inclusivity (Bladen et al., 2022). The success of this objective will be measured through post-event feedback surveys, assessing participants’ knowledge improvement and confidence in applying EDI strategies within their organizations (Getz, 2008).

Objective 2: Strengthening Professional Networks

Networking is an essential driver of industry-wide change in EDI. The symposium aims to facilitate at least 50 new professional connections per delegate, creating an ecosystem where leaders, HR professionals, and policymakers can collaborate beyond the event. Structured networking sessions, industry-specific breakout groups, and digital networking tools will be leveraged to enhance engagement and long-term partnerships (Getz, 2008).

Objective 3: Driving Actionable Change Through Workshops

Beyond theoretical discussions, the symposium will equip attendees with practical toolkits for implementing EDI strategies. Through hands-on workshops, participants will learn bias mitigation techniques, inclusive policy design, and data analytics for tracking EDI progress. The target outcome is for at least 70% of attendees to adopt one new EDI initiative within their workplace, ensuring a lasting impact (Goldblatt, 2011).

# Event Management Considerations

## Operational Activities

The Empowering Equality community program needs proper planning and arrangement of the venue to set up an atmosphere of progress and unity. ExCeL London has been chosen as it provides better facilities, flexibility of layout and accessibility. The layout of the venue will allow for the discussions of panels, workshops, areas for break and interaction, as well as exhibition space. Catering services will provide a variety of meals and non-vegan options like vegan, halal, kosher, allergen, etc (Bladen et al., 2022). Also, it is an accessible event that has provided priority seating for wheelchairs sign language interpreters and assistive listening systems. This will help improve the event experience by integrating an event app for timetables, notifications, and AI-based networking which will help attendees connect and network effectively (Disimulacion, 2024).

## Strategic Planning Activities for Event Success:

A Gantt chart is the best way to organize all the activities that need to take place during the event and the timeline for them. This time-bound planning approach helps the event team to focus on important targets, including venue, speakers, sponsors, and marketing activities while allowing for flexibility. Risk management is an important factor in planning any event since it helps address unexpected difficulties that may arise (Disimulacion, 2024). Low attendance risks are also dealt with in a comprehensive contingency strategy by early bird registrants, special promotions and targeted efforts. Technical issues are addressed by duplicative AV systems, IT support teams, and both synchronous and asynchronous modality configurations (Pernecky, 2015).

## Strategic Marketing Approach for Maximum Engagement:

To attract high-profile attendees and ensure the maximum industry turnout, it is vital to launch a multi-channel digital campaign. The symposium will utilize LinkedIn, Twitter, and Instagram to reach the targeted professionals, share event content, involve industry influencers, and post live updates. Email marketing will be used to send targeted invitations, sneak peek at what is new, and gradual steps approach (Disimulacion, 2024). Furthermore, partnerships with other professional bodies like CIPD and SHRM will help reach out to more HR professionals and key decision-makers. Based on these considerations, the symposium will use tiered pricing to encourage early registrations and engagement and bonus registration for people to bring friends (Pernecky, 2015). These strategies help create a diverse audience base, enhancing the symposium’s networking and knowledge-sharing effectiveness.

# Event Budget and Financial Analysis

| Projected Income |  | Projected Expenditure |  |
| --- | --- | --- | --- |
| Ticket Sales | 100,000 | Venue Hire | 80,000 |
| Sponsorships | 150,000 | Speaker Fees | 50,000 |
| Exhibitor Fees | 75,000 | Marketing | 40,000 |
| Government Grants | 50,000 | Catering | 30,000 |
|  |  | Staff Wages | 60,000 |
|  |  | Technical Setup | 25,000 |
| Total | =375,000 | Total | =285,000 |

# Industry Trends, Issues, and Impacts

## Trends Influencing the Symposium

Empowering Equality is defined by trends that are emerging in the workplace that assert the growing significance of EDI as a business imperative. This is supported by Stoudemire (2024) research stating that diverse boards and executive teams are said to deliver up to 25% more than their counterparts. It was very helpful to attend an event like the symposium and be able to see other organizations putting out their inclusion frameworks and integrating them into their governance structures (Rogers and Wynn-Moylan, 2022). Moreover, hybrid event models have changed the definition of industry engagement as well. Virtual participation increases inclusiveness and makes it possible for people from all over the world to attend. This shift offers convenience, a higher yield for sponsors, and improved digital connection possibilities (Allen et al., 2022). Incorporating hybrid accessibility tools makes the symposium responsible for sustainability because it reduces the carbon footprint in travel and increases the participants’ engagement and influence.

## Challenges and Issues Impacting the Symposium:

A primary concern for the Empowering Equality symposium is to guarantee that the inclusion of minorities does not remain a mere formality. Most companies go for symbolic gestures instead of true systemic changes, which makes it a spectacle of allyship instead of real progress (Goldblatt, 2011). To address this, the symposium focuses on the use of data, the need for leadership engagement, and models and frameworks for assessing EDI impact (Rogers and Wynn-Moylan, 2022). Attendees will be able to actively discuss how to overcome barriers to equality, making diversity a sustainable not just an exercise in checking the box.

The other challenge is the economic instability and austerity which affects event sponsorship and attendance. For large industry events, funding is becoming more difficult to come by as many businesses are shifting their financial focus (Merrilees and Marles, 2011). The symposium does this through a variety of revenue sources, flexible participation structures, and corporate sponsorship packages promising concrete value to sponsors (Allen et al., 2022). The event remains financially sustainable as it offers several levels of engagement and has a high industry impact.

# Situational and Cultural Considerations (SWOT Analysis)

## SWOT Analysis

Strengths

Another advantage is that the market has a high need for events associated with EDI. Due to the emergence of workplace diversity as an important corporate and regulatory issue, companies are looking for ways to compare and contrast different practices and strategies (Getz, 2025). It also has keynote speakers and industry sponsors which increases its credibility and the quality of delegates that it attracts. This increases its credibility since it collaborates with other HR leaders, policymakers, and corporate executives who influence the sector (Allen et al., 2022).

Weaknesses:

However, the symposium has budget constraints which limit it from carrying out an elaborate marketing campaign all over the world. However, due to financial restrictions, it may be impossible to expand the range of invitations and advertising compared to industry conferences (Sterling, 2016). Moreover, the management of events entails highly skilled professionals who would be able to cater for the issues of diversity without escalating prejudice (Goldblatt, 2011). This means there is a need for skilled moderators, panelists, and content curators which can be a problem in terms of quality and focus.

Opportunities:

This has great potential for growth through linkages with international EDI organizations. Cooperating with other institutions, non-governmental organizations, and governmental bodies can improve credibility, which means more participants and financing (Goldblatt, 2011). Also, the success of this event could lead to the establishment of a global series of such events and the creation of an annual event focusing on workplace inclusion (Leach, 2021).

Threats:

The threat of rivalry from other highly developed events like the Diversity & Inclusion Leaders’ Summit makes it difficult to make the symposium stand out. Also, issues such as the delay in visa processing may hamper attendance from foreign individuals or organizations, making provision for virtual attendance a necessity (Goldblatt, 2011).

# Conclusion and Recommendations

## Conclusion

The Empowering Equality symposium is feasible due to the increasing need for EDI-focused events by corporations and the sound financial support from sponsorships, exhibitor fees, and ticket sales. The Event Cycle model guarantees the symposium follows cyclic planning concerning logistic, operational, and marketing aspects. Further, the involvement of keynote speakers, workshops, and business meetings also increases the event’s industry focus and the participants’ interest. However, to enhance long-term results and sustainability, the event should meet such gaps as financial challenges, audience targeting, and positioning. Implementation and follow-up measures are therefore important to ensure the symposium is more than just a series of debates.

## Recommendations

Strengthen Digital Marketing for Better Outreach

To expand its reach and attract a wider audience, the symposium should enhance its digital marketing efforts. This includes leveraging AI-driven personalized content, targeted social media campaigns, and strategic partnerships with industry influencers and organizations (Manoharan et al., 2024).

Expand Sponsorships to Mitigate Financial Risks

Diversifying sponsorship models—such as tiered sponsorship packages, media partnerships, and corporate grants—can reduce financial dependency on ticket sales and ensure long-term financial stability. Engaging global EDI organizations as sponsors will further enhance the event’s credibility (Ziakas, 2023).

Implement Post-Event Engagement Strategies

To ensure continuous knowledge-sharing and sustained industry impact, the symposium should introduce post-event initiatives such as follow-up webinars, exclusive newsletters, and an online resource hub (Monroy-Rodríguez and Caro-Carretero, 2023). These strategies will maintain engagement with attendees, track the implementation of EDI initiatives, and foster an ongoing professional community.

# References

Allen, J., Harris, R. and Jago, L. (2022) Festival & special event management. John Wiley & Sons.

Bladen, C. et al. (2022) Events management: An introduction. Routledge.

Dashper, K. and Finkel, R. (2020) ‘Accessibility, diversity, and inclusion in the UK meetings industry’, Journal of Convention & Event Tourism, 21(4).

Disimulacion, M. (2024) ‘Innovating the MICE Industry through Creative Tourism: Opportunities and Future Directions’, International Journal of Sustainable Competitiveness on Tourism, 3(1), pp. 54–62.

Finkel, R. and Dashper, K. (2020) ‘Accessibility, diversity and inclusion in events’, in The Routledge handbook of events. Routledge, pp. 475–490.

Finkel, R., Sharp, B. and Sweeney, M. (2019) Accessibility, inclusion, and diversity in critical event studies. Abingdon: Routledge.

Getz, D. (2008) ‘Event design and management’, The sage handbook of hospitality management, pp. 518–40.

Getz, D. (2025) ‘Festival and event tourism’, in Encyclopedia of tourism. Cham: Springer International Publishing, pp. 391–395.

Goldblatt, S. (2011) The complete guide to greener meetings and events. John Wiley & Sons.

Leach, V. (2021) The Financial Times Guide to Inclusion and Diversity. Pearson UK.

Manoharan, A., Madera, J.M. and Singal, M. (2024) The Routledge handbook of diversity, equity, and inclusion management in the hospitality industry. Routledge.

Merrilees, B. and Marles, K. (2011) ‘Green business events: Profiling through a case study’, Event Management, 15(4), pp. 361–372. Available at: https://doi.org/10.3727/152599511X13175676722609.

Monroy-Rodríguez, S. and Caro-Carretero, R. (2023) ‘Congress tourism: Characteristics and application to sustainable tourism to facilitate collective action towards achieving the SDGs’, Cogent Business & Management, 10(3).

Pernecky, T. (2015) ‘Sustainable leadership in event management’, Event Management, 19(1), pp. 109–121. Available at: https://doi.org/10.3727/152599515X14229071393188.

Rogers, T. and Wynn-Moylan, P. (2022) Conferences and conventions: A global industry. Routledge.

Singh, A. and Deri, M. (2024) ‘Exploring the Use of Virtual and Hybrid Events for MICE Sector: Trends and Opportunities’, in New Technologies in Virtual and Hybrid Events. IGI Global, pp. 47–70.

Slocum, S. (2023) Inclusion in Tourism: Understanding Institutional Discrimination and Bias. Taylor & Francis.

Sterling, R. (2016) ‘Promoting diversity leadership: Strategies and tools to improve equity and access’, in Handbook of Research on Race, Gender, and the Fight for Equality. IGI Global, pp. 321–334.

Stoudemire, T. (2024) Diversity done right: Navigating cultural difference to create positive change in the workplace. John Wiley & Sons.

Ziakas, V. (2023) Cases for event management and event tourism. Routledge.