EXERCISE 3. DELAY ANALYSIS

You are working as the project manager for the client, and you are working on a new development in Swansea. The project has been delayed for 4 weeks and the main contractor is asking for an extension of time. According to your records, make your delay analysis and take a coherent decision about it.

As programmed:

| Task | Duration |
| --- | --- |
| 1-2 | 4 weeks |
| 1-3 | 6 weeks |
| 1-4 | 3 weeks |
| 2-5 | 6 weeks |
| 3-5 | 6 weeks |
| 4-6 | 5 weeks |
| 5-7 | 8 weeks |
| 6-7 | 5 weeks |

Your records show the following delays:

| Activity | Delay | Reason |
| --- | --- | --- |
| 2-5 | +3 weeks | Incomplete design |
| 1-4 | +2 weeks | Bad weather |
| 5-7 | +3 weeks | Modification of project, works had to stop |
| 6-7 | +1 week | Subcontractor was delayed, not skilled enough |