Project Management Exercise

Using the data below you are required to undertake the following tasks: -

- Construct a network diagram and determine the duration of the project

- Determine the critical path of the project

- Calculate the cost of each activity and the total cost of the project.

| Activity | Resources | Duration (Days) |
| --- | --- | --- |
| 1 – 2 | 1M, 2C, 1L | 15 |
| 2 – 4 | 2L | 5 |
| 4 – 9 | 2L | 6 |
| 9 – 13 | 1C | 3 |
| 4 – 13 | 1M, 1C | 5 |
| 4 – 7 | 1M, 1C | 10 |
| 7 – 11 | 1C | 3 |
| 11 – 13 | 1C, 1L | 2 |
| 13 – 15 | 1L | 1 |
| 15 – 17 | 2L | 2 |
| 1 – 3 | 2C, 2L | 10 |
| 3 – 8 | 2C, 2L | 10 |
| 8 – 12 | 1L | 5 |
| 12 – 14 | 1L | 2 |
| 3 – 6 | 1M | 5 |
| 6 – 14 | 2C | 7 |
| 14 – 16 | 1L | 1 |
| 16 – 17 | 1L | 2 |
| 1 – 5 | 2C | 10 |
| 5 – 10 | 2C, 2L | 8 |
| 17 - 18 | 1M | 5 |

1M = £150 per day

1C = £250 per day

1L = £95 per day

| Activity | Optimistic | Most Likely | Pessimistic | PERT Value |
| --- | --- | --- | --- | --- |
| 1 – 2 | 10 | 15 | 18 | 14.6 |
| 2 – 4 | 4 | 5 | 8 | 5.3 |
| 4 – 9 | 2 | 6 | 8 |  |
| 9 – 13 | 2 | 3 | 5 |  |
| 4 – 13 | 3 | 5 | 9 |  |
| 4 – 7 | 7 | 10 | 15 | 10.3 |
| 7 – 11 | 1 | 3 | 4 | 2.8 |
| 11 – 13 | 1 | 2 | 4 | 2.2 |
| 13 – 15 | 1 | 1 | 2 | 1.7 |
| 15 – 17 | 1 | 2 | 2 | 1.8 |
| 1 – 3 | 8 | 10 | 18 |  |
| 3 – 8 | 5 | 10 | 15 |  |
| 8 – 12 | 3 | 5 | 8 |  |
| 12 – 14 | 1 | 2 | 5 |  |
| 3 – 6 | 3 | 5 | 8 |  |
| 6 – 14 | 5 | 7 | 9 |  |
| 14 – 16 | 1 | 1 | 1 |  |
| 16 – 17 | 1 | 2 | 3 |  |
| 1 – 5 | 5 | 10 | 18 |  |
| 5 – 10 | 6 | 8 | 12 |  |
| 17 - 18 | 4 | 5 | 8 | 5.3 |

PERT Time for each activity is calculated using the following formula

PERT Time = O+4ML+P6

Please remember that PERT analysis is only done on those activities that are on the critical path.