## Query Sheet Nr. 03
Student name: | James Lloyd
Return email: | 1900878@student.uwtsd.ac.uk
Innovation Matrix - Cost Plan
|  |  | Query Sheet Nr. | 03
|  |  | Date : | 2022-12-02
QUERY |  | Answer
1. | When analysing the following drawings, '152481-STL-XX-XX-DR-A-PL_0202-Elevation Detail 01' and '152481-STL-XX-XX-DR-A-PL_0203-Elevation Detail 02', I am unable to identify the roofing material. Could you provide some clarity on this please as the key and elevation drawings suggest that it is to be the same material as the cladded external walls, 'Kingspan Box Profiled insulated Wall Panel KS1000 FCColour TBC. Shown RAL 8019'? | Please include £450/m2 for the roof covering as a composite panel
2. | Can you provide the dimensions of the 'Day-Lite Trapezoidal Rooflight Plus KS1000 DLTR Plus' Rooflights? Unfortunately, using the drawings provided, I am unable to submit an accurate price without the length of the rooflight (unavailable due to pitch) | Please include an allowance of £3,000 for each rooflight
3. | Have you got a specification for the required uPVC fascia, soffits and rainwater goods? If not yet considered, may I propose an anthracite grey colour scheme and standard fascia, soffits and accessories? | Yes please
4. | Can you provide a window schedule, including window specification for the building? I can alternatively take-off and measure the integrated window systems however a specification or schedule of requirements would be greatly appreciated. | Please include £550/m2 for the glazing.
5. | As identifiable on drawing '152481-STL-XX-00-DR-A-PL_0103-Ground Floor Shell & Core' I can identify the basic requirements for external doors using the notable labels. Can you provide further information on these, most notably the rotating door? | Please include £2,800/ for each external door unit. Please include a Provisional Sum of £15,000 for each rotating door.
6. | … | …
7. | … | …
8. | … | …
9. | … | …
10. | … | …