## Sheet1
Joseph Ogden | Summer |  |  | Block One (Sep 16 - Oct 11) |  |  |  | Prep Week | Block Two (Oct 21 - Nov 15) |  |  |  | Prep Week | Block 3 (Nov 25 - Dec 20) |  |  |  | Christmas Period | Block 4 (Jan 6 - 31) |  |  |  | Prep Week | Block 5 (Feb 10 - Mar 6) |  |  |  | Prep Week | Block 6 (Mar 16 - Apr 10) |  |  |  | Week Apr 13 | Week Apr 20 | Deadline May 1
1704684 |  |  |  | W1 | W2 | W3 | W4 |  | W1 | W2 | W3 | W4 |  | W1 | W2 | W3 | W4 |  | W1 | W2 | W3 | W4 |  | W1 | W2 | W3 | W4 |  | W1 | W2 | W3 | W4
Task
Initial Research (20 secondary sources)
Read core primary source material
Supervisor Meetings
Give Supervisor Chapters for Feedback | [18 empty] | Lit Review | [8 empty] | Chapter 1
My Modules
Project Plan and Management Chart
Presentation
Further Research
Complete Introduction
Complete Methodology
Complete Literature Review
Chapter 1.1
Chapter 1.2
Chapter 2.1
Chapter 2.2
Complete Conclusion
Printing and Binding
Finished!
Key
Completed
Assigned/In progress
Deadline/Milestone